## Command Center
MIDWEST DESIGN GROUP — Executive Command Center
CEO / CFO view • Live QuickBooks + Knowify • As of 2026-06-17 • All figures real, reconciled to source
YTD REVENUE |  | GROSS MARGIN |  | NET INCOME |  | CASH | TRADE A/R | BACKLOG | LOC USE
28774215.27 |  | 35.58% |  | 5340196.8 |  | -54623.3 | 12986875.87 | 21887687.17 | 68%
through 2026-06-17 |  | GP $10,238,582 |  | 18.6% margin |  | BS cash | + $3,136,194 retainage | 308 active jobs | $5,440,077 drawn
2026 FORECAST REV |  | 2026 FORECAST NI |  | MANAGED JOBS |  | JOBS FADING | OVERBILLED | UNDERBILLED | BBC HEADROOM
58434358.32 |  | 7989027.96 |  | 84 |  | 80 | 2614934.61 | 1085234512.46 | 2559923.05
run-rate ×5mo complete |  | 13.7% margin |  | of 308 active |  | margin fade < -2% | billed ahead of work | work ahead of billing | borrowing-base avail
2026 Monthly Trend (verified single-month QuickBooks P&L)
Month | Revenue | Gross Profit | Net Income | GM %
2026-01 | 4471974.17 | 1304448.48 | 186406.72 | 29.17%
2026-02 | 4949310.29 | 1261426.04 | 467881.55 | 25.49%
2026-03 | 5290349.77 | 1673497.09 | 790908.56 | 31.63%
2026-04 | 4593904.49 | 1350991.82 | 677429.81 | 29.41%
2026-05 | 5042110.58 | 1724275.13 | 1206135.01 | 34.2%
Division Contribution (Knowify active jobs)
Division | Contract | Invoiced | Profit $ | Profit %
Tenant Improvement | 23623992.86 | 20986986.32 | 7920870.84 | 33.53%
Multi-Family | 41385804.97 | 22703258.15 | 5593999.63 | 13.52%
Drywall | 2247021.73 | 2037196.92 | 652801.83 | 29.05%
Unallocated | 1481553.28 | 1123244.28 | -289343.44 | -19.53%
⚠ EXCEPTIONS
• 80 managed jobs with profit fade worse than -2% |  |  |  |  | Project Tracker
• Cash position negative: $-54,623 |  |  |  |  | Cash & Liquidity
• LOC utilization 68% ($5,440,077 of $8,000,000) |  |  |  |  | Cash & Liquidity
• Overbilling $2,614,935 — billed ahead of work (cash borrowed from jobs) |  |  |  |  | WIP & Profit Fade
• 221 active jobs with no Project Manager assigned |  |  |  |  | Data Health
• 220 active jobs with no budget loaded |  |  |  |  | Data Health
• $0 GL in UNALLOCATED division |  |  |  |  | Data Health

## P&L
Profit & Loss
Company P&L from QuickBooks • FY2024 / FY2025 / YTD2026 • reconciled to QB section totals
Line | FY2024 | FY2025 | YTD2026 (2026-06-17)
Revenue | 39537774.9 | 40491815.42 | 28774215.27
Billable Expense Income | 10032 | 543 | 0
Doors and Windows | 237386.66 | 4594.5 | 0
Drywall Division Delivery Income | 1062721.25 | 201.04 | 0
Drywall Division Material Income | 2840679.74 | 2824148.9 | 20720.33
Drywall Sales Income | -6863.55 | 0 | 0
Drywall Service Income | 3983560.92 | 3358176.13 | 426214.72
Drywall Supply Arbor Income | 0 | 959002.74 | 880039.92
Drywall Supply Century Income | 0 | 105734.39 | 0
Drywall Supply HD Boom Scatter Income | 0 | 174372.44 | 0
Drywall Supply Pulte Income | 0 | 6230.22 | 16826.61
Drywall Tax | 348.74 | 67.77 | 0
Engineering Project Income | 16000 | 709295 | 396425
Finishes | 1499889.18 | 76310.01 | 0
Metals | 1715940.63 | 0 | 0
Sales | 4079740.08 | 13469.39 | 4820
Service/Fee Income | 22772419.95 | 33721642.66 | 24484720.25
Specialties | 87799.97 | 2713.5 | 0
Thermal and Moisture Control | 401319.14 | 0 | 0
WIP Adj - Net change | 67516.35 | -1464686.27 | 2544448.44
Wood and Plastics | 769283.84 | 0 | 0
Cost of Goods Sold | 28435216.93 | 27755136.44 | 18535632.98
Gross Profit | 11102557.97 | 12736678.98 | 10238582.29
Gross Margin % | 28.08% | 31.45% | 35.58%
Operating Expenses | 8249044.14 | 10032604.11 | 4772731.89
Other Income | 68846.33 | 0 | 55196.91
Other Expense | 23197.6 | 0 | 180850.51
NET INCOME | 2899162.56 | 2704074.87 | 5340196.8
Net Margin % | 7.333% | 6.678% | 18.56%
Annual Revenue / Gross Profit / Net Income
Period | Revenue | Gross Profit | Net Income
FY2024 | 39537774.9 | 11102557.97 | 2899162.56
FY2025 | 40491815.42 | 12736678.98 | 2704074.87
YTD2026 | 28774215.27 | 10238582.29 | 5340196.8

## Division Performance
Division Performance
Per-division contract, billing, cost & margin (Knowify active jobs)
Division | Jobs | Contract | Invoiced | Budget Cost | Actual Cost | Profit $ | Profit % | WIP Net
Tenant Improvement | 62 | 23623992.86 | 20986986.32 | 14432142.97 | 13561203.47 | 7920870.84 | 33.53% | 1005043.92
Multi-Family | 22 | 41385804.97 | 22703258.15 | 28976033.19 | 18096438.15 | 5593999.63 | 13.52% | 1370719.21
Drywall | 213 | 2247021.73 | 2037196.92 | 0 | 1384395.09 | 652801.83 | 29.05% | -2037196.92
Unallocated | 11 | 1481553.28 | 1123244.28 | 414032 | 1412587.72 | -289343.44 | -19.53% | 1082281011.64

## Project Tracker
Project Tracker — Profit Fade Watch
84 managed jobs ranked worst-fade first • fade = forecast margin − as-bid budget margin
Job | Div | PM | Customer | Contract | % Comp | Proj Margin | Est Margin | Profit Fade | WIP Net | Open A/R
2025.986 FedEx Hub | TI | Tommy Cohoat | Dalmatian Fire | 6000 | 16.99% | 1.47% | 88.33% | -86.86% | -4980.6 | 0
2025.997 Belmont St Warehouse Clear Out 250-408 | TI | Spencer Anderson | DEEM, LLC | 54090 | 216.6% | 0.15% | 79.83% | -79.68% | 63074.35 | 0
2025.980 Avon Bldg. 1 Canopies & Pavilion | TI | Spencer Anderson | The Peterson Company, LLC | 116280 | 100.7% | 0.06% | 65.37% | -65.32% | 779.08 | 0
MF.2024.903 Mirka Office Buildout | MF | Cole Garriott | DEEM, LLC | 175330 | 100% | 0.04% | 64.11% | -64.07% | 0 | 0
2025.1031 Pita Way | TI | Spencer Anderson | Kort Builders, Inc | 9745 | 90.11% | 0.64% | 62.4% | -61.76% | -963.78 | 0
2024.929 DEEM Warehouse | TI | Tommy Cohoat | DEEM, LLC | 659384.05 | 98.9% | 0.01% | 60.57% | -60.56% | -7253.22 | 0
2023.795 Upland Brewery Clay Terrace | TI | Tommy Cohoat | Bischoff Construction, LLC | 101530 | 126.1% | 0.06% | 59.16% | -59.11% | 26529.79 | 0
2025.1015 WBP Lot 4 | TI | Tommy Cohoat | Patch Development | 175400 | 98.67% | 0.03% | 58.04% | -58.01% | -2332.82 | 0
2025.1016 WBP Lot C | TI | Tommy Cohoat | Patch Development | 125700 | 205.5% | 0.05% | 57.49% | -57.45% | 132651.21 | 13081.87
2023.816 Upland Broad Ripple | TI | Tommy Cohoat | Bischoff Construction, LLC | 14450 | 181.4% | 0.39% | 56.06% | -55.67% | 11768.08 | 0
2026.1043 Deer Creek Building 1 | TI | Tommy Cohoat | Patch Development | 135000 | 82.94% | 0.04% | 55.7% | -55.66% | -23031 | 13500
2025.967 Bunge Project Flex | TI | Ben Garza | Bunge North America (East), LLC | 993046 | 100% | 0.01% | 54.44% | -54.44% | 0 | 99304.6
2026.1041 Whiteland Building 2 - Blackhawk | TI | Spencer Anderson | Patch Development | 187650 | 65.65% | 0.03% | 52.14% | -52.11% | -33228.07 | 44532.3
2026.1052 Project Panther | TI | Spencer Anderson | ARCO Design/Build | 900893 | 5.61% | 0.01% | 50.89% | -50.89% | 50540.1 | 0
2024.920 SMC Mezzanine HVAC | TI | Trevor Anderson | DEEM, LLC | 2028 | 100% | 2.63% | 53.39% | -50.76% | 0 | 0
2025.999 Romet PWSI | TI | Tommy Cohoat | The Peterson Company, LLC | 372490 | 100.4% | 0.01% | 49.05% | -49.03% | 1340.96 | 0
2024.957 SanMar AWR | TI | Cole Garriott | The Peterson Company, LLC | 34964 | 100% | 0.14% | 48.73% | -48.59% | 0 | 0
2025.1027 Indy Boat Co | TI | Trevor Anderson | Raley Wake, LLC | 242452.3 | 96.96% | 0.02% | 47.02% | -47% | 98735.85 | 0
2023.731 Park 133 - ITS - TI Tenant Buildout | TI | Tommy Cohoat | The Peterson Company, LLC | 759684 | 100.8% | 0.01% | 46.5% | -46.5% | 6153.44 | 0
2026.1034 Stella's Ice Cream Shop | TI | Shawn Welcher | The ACTS Collaborative, LLC | 69155 | 73.02% | 0.07% | 46.53% | -46.46% | -11742.52 | 28129.5
2026.1053 Lot 32 Vacant TI | TI | Spencer Anderson | Holladay Construction Group | 126210 | 35.44% | 0.04% | 45.93% | -45.89% | 44728.82 | 0
2024.953 Motorworks | TI | Tommy Cohoat | Precision Dry Wall | 2605.74 | 100% | 1.83% | 47.62% | -45.79% | 0 | 0
2025.969 Carson | TI | Spencer Anderson | DEEM, LLC | 287418 | 99.89% | 0.02% | 45.73% | -45.71% | -316.16 | 0
2025.1006 Keller Office | TI | Ben Garza | ARCO Design/Build | 276600 | 102.4% | 0.02% | 45.14% | -45.12% | 92076.54 | 191272.5
2026.1051 Park 130 Building 8 | TI | Spencer Anderson | The Peterson Company, LLC | 294700 | 22.05% | 0.01% | 43.99% | -43.97% | 64981.35 | 0
2025.1023 Vikan Products BTS | TI | Cole Garriott | The Peterson Company, LLC | 734790 | 84.11% | 0.01% | 43.82% | -43.81% | -43279.12 | 293268.15
2025.979 Groundbreakers | TI | Trevor Anderson | Patch Development | 288504.91 | 100% | 0.02% | 43.73% | -43.72% | 839.51 | 0
2026.1040 Lakeside Books | TI | Trevor Anderson | The Peterson Company, LLC | 10020 | 100% | 0.44% | 44.08% | -43.64% | 0 | 10020
2026.1047 Springdale Building 4 Demising Walls | TI | Tommy Cohoat | The Peterson Company, LLC | 148800 | 82.35% | 0.03% | 42.81% | -42.78% | -26263.2 | 148800
2025.1013 Lucas Oil Corydon | TI | Shawn Welcher | Meyer Najem | 103243.16 | 100% | 0.04% | 42.52% | -42.48% | 3243.16 | 100000
2024.913 Walmart Phoenix | TI | Cole Garriott | DEEM, LLC | 2945439.34 | 94.59% | 0% | 42.15% | -42.15% | 253838.16 | 28912.51
2022.639 Radial TI - Avon Building 2 | TI | Tommy Cohoat | The Peterson Company, LLC | 758779 | 116.7% | 0.01% | 41.94% | -41.94% | 126943.73 | 0
2026.1045 First OnSite (Ameriplex) | TI | Spencer Anderson | Holladay Construction Group | 128000 | 110.7% | 0.03% | 41.9% | -41.87% | 13708.8 | 95060
2025.1028 Northpoint | TI | Trevor Anderson | Patch Development | 243696 | 49.16% | 0.02% | 41.88% | -41.87% | 102385.95 | 0
MF.2025.1019 Town & Country Apartments (NY MF Project - 22 bldgs) | MF | Kelden Tyson | Marous Brothers Construction | 8064307.39 | 35.23% | 0% | 41.51% | -41.51% | 257210.76 | 555463.41
2023.843 Walmart Frederick | TI | Cole Garriott | DEEM, LLC | 2978233.94 | 100% | 0% | 41.46% | -41.46% | 0 | 0
2026.1036 Port Laredo Trade Center | TI | Ben Garza | ARCO Design/Build | 108475 | 100% | 0.04% | 41.41% | -41.38% | 0 | 108475
2025.1001 Evolve Transporters | TI | Cole Garriott | Compass Commercial Construction Group | 1317620 | 101% | 0% | 40.22% | -40.22% | 13439.72 | 133103
MF.2025.1007 The Approach | MF | Kelden Tyson | KCG | 5643379.34 | 0.06% | 0% | 40.18% | -40.18% | 3386.03 | 0
2026.1042 SND2 at ILP Bldg IV Whitestown | TI | Trevor Anderson | Compass Commercial Construction Group | 443007.26 | 54.14% | 0.01% | 39.69% | -39.68% | -116883.21 | 192058.3
2025.966 C5 Bullitt III Logistics Center Warehouse | TI | Trevor Anderson | The Peterson Company, LLC | 415930 | 100.1% | 0.01% | 39.15% | -39.14% | 499.12 | 0
2022.617 The Junction Phase II | TI | Ted Wells | EquiTeam LLC | 304058.89 | 100% | 0.01% | 39.04% | -39.02% | 0 | 0
2026.1056 Senator Banks Office | TI | Dustin Hurt | BW Facility Management, LLC | 47609 | 31.24% | 0.08% | 39.02% | -38.94% | -19570.96 | 34444.01
2026.1046 Automatic Distributors (Park 130 Bldg 6) | TI | Cole Garriott | The Peterson Company, LLC | 171900 | 60.76% | 0.02% | 38.51% | -38.49% | -50263.56 | 122013
2025.1011 Airport South Logistics Bldg. A | TI | Spencer Anderson | ARCO Design/Build | 134480 | 0.05% | 0.03% | 38.43% | -38.4% | 67.24 | 0
2024.912 Upland Columbus | TI | Tommy Cohoat | Bischoff Construction, LLC | 116545 | 99.4% | 0.03% | 37.17% | -37.14% | -699.27 | 2020
2022.690 Klarity, Mind, & Body | TI | Ted Wells | EquiTeam LLC | 66336.42 | 87.51% | 0.06% | 36.68% | -36.62% | -8285.43 | 0
2026.1033 Avon Demising Wall | TI | Ben Garza | The Peterson Company, LLC | 181500 | 100% | 0.02% | 35.14% | -35.13% | 0 | 181500
2025.994 Stotan Port Laredo Spec Offices | TI | Ben Garza | ARCO Design/Build | 699328 | 100% | 0.01% | 35.08% | -35.07% | 0 | 114932.8
2024.869 Prospect Lake Clean Water Center | TI | Cole Garriott | Patterson Horth, Inc. | 427542 | 100% | 0.01% | 34.61% | -34.6% | 0 | 42754.2
MF.2025.989-1 Springdale Cinema - Paint | MF | Ben Garza | MILHAUS Construction | 875000 | 75.06% | 0% | 33.68% | -33.68% | 49725 | 551610
MF.2026.1050 AC Hotel | MF | Ben Garza | Holladay Construction Group | 1244040 | 20.98% | 0% | 32.7% | -32.69% | 58348.92 | 202650.67
MF.2025.975 The Eleven - Monon Square | MF | Shawn Welcher | Centric Projects, LLC | 465610 | 19.98% | 0.01% | 31.44% | -31.43% | -159182.53 | 252211.41
2025.1032 65 Commerce Park Building 7 | TI | Trevor Anderson | Compass Commercial Construction Group | 133900 | 88.77% | 0.02% | 31.27% | -31.25% | 47548.83 | 71314.2
2023.847 Ireland Home | TI | Tommy Cohoat | Bischoff Construction, LLC | 52636.92 | 111.2% | 0.06% | 30.95% | -30.89% | 5911.13 | 0
MF.2026.1044 Everstead Apartments | MF | Ben Garza | Grand Contracting | 4391740 | 0% | 0% | 30.52% | -30.52% | 0 | 0
MF.2025.992 Young's Creek Apartments | MF | Kelden Tyson | Shiel Sexton | 488752.35 | 100% | 0.01% | 30.26% | -30.25% | 0 | 272493.11
MF.2025.972 Union Flats - Fishers | MF | Ben Garza | Thompson Thrift Construction | 3838166 | 87.36% | 0% | 30.11% | -30.11% | 626945.67 | 1141266.15
MF.2024.928 Holliday Farms Assisted Living - Zionsville | MF | Ben Garza | Avenue Construction, Inc. | 2731383.75 | 100.1% | 0% | 29.86% | -29.86% | 3823.94 | 392366.31
MF.2025.963 Home 2 Suites | MF | Kelden Tyson | Meyer Najem | 580227.88 | 100% | 0.01% | 29.64% | -29.64% | 0 | 58022.79
MF.2025.976 Firefly Youth Housing | MF | Spencer Anderson | Stenz Corp | 250736.11 | 100% | 0.01% | 28.14% | -28.13% | 25073.61 | 73125
2025.1021 Convivio | TI | Shawn Welcher | The Peterson Company, LLC | 87788.26 | 100% | 0.03% | 28.09% | -28.06% | 0 | 0
2025.960 Langham Whiteland South Lockers | TI | Spencer Anderson | DEEM, LLC | 72797 | 101% | 0.04% | 27.13% | -27.09% | 735.25 | 0
2022.625 Walmart 7611 | TI | Cole Garriott | Massa Multimedia Architecture (MMA) | 983441 | 100% | 0% | 27.03% | -27.03% | 1300 | 0
2025.1024 Metro Lion | TI | Ben Garza | DEEM, LLC | 786710 | 100% | 0% | 26.87% | -26.87% | 0 | 1300
MF.2024.927 Jeffersonian Apartments | MF | Ben Garza | Stenz Corp | 461337.65 | 100% | 0.01% | 26.77% | -26.77% | 0 | 46133.76
MF.2024.894 Hamilton County Jail Boiler Mechanical Pad | MF | Dustin Hurt | DEEM, LLC | 3515 | 92.59% | 0.74% | 26.03% | -25.29% | -260.46 | 0
MF.2025.977 Civic Square Condos | MF | Trevor Anderson | Novo Development Group, LLC | 603098 | 99.84% | 0% | 24.66% | -24.65% | -964.96 | 60309.8
MF.2024.906 Shamrock Elementary LGI Classrooms | MF | Dustin Hurt | LTB Construction, Inc. | 8830 | 39.35% | 0.28% | 24.8% | -24.52% | -5355.4 | 0
2025.1012 Airport South Logistics Bldg. B | TI | Spencer Anderson | ARCO Design/Build | 128180 | 100.4% | 0.02% | 24.03% | -24.01% | 25473.06 | 93376.8
MF.2024.941 Oak Trace | MF | Dustin Hurt | Westfield Community Management, LLC | 76730 | 100.1% | 0.03% | 22.86% | -22.83% | 61.38 | 0
2022.654 Upland Brewery Northside | TI | Tommy Cohoat | Seven Four Construction | 175860.53 | 98.6% | 0.01% | 20.79% | -20.78% | -2462.05 | 0
MF.2023.840 Paint at 804 14th Ave Nashville | MF | Kelden Tyson | ZMX Inc. | 280782.67 | 101.1% | 0.01% | 18.72% | -18.72% | 3116.69 | -19741.84
2026.1037 CV - Castle Rock | TI | Ben Garza | Bischoff Construction, LLC | 127451 | 100% | 0.01% | 18.59% | -18.57% | 0 | 2000
2023.776 Keefe Group TI | TI | Tommy Cohoat | The Peterson Company, LLC | 113525 | 99.63% | 0.02% | 18.42% | -18.41% | -420.04 | 0
MF.2023.785 Drywall at 804 14th Ave Nashville | MF | Kelden Tyson | ZMX Inc. | 739513.88 | 100.4% | 0% | 17.77% | -17.77% | 3032.01 | 10646.9
MF.2024.875 Purdue Student Housing | MF | Kelden Tyson | Marous Brothers Construction | 6171928.99 | 100.2% | 0% | 15.95% | -15.95% | 11726.67 | 0
MF.2024.892 The Lofts at Headwaters Park | MF | Ben Garza | J.C. Hart Company, Inc. | 4286845.96 | 99.77% | 0% | 15.67% | -15.67% | 497203.69 | 159486.39
2025.1026 HNTB Buildout (Salesforce Tower) | TI | Ben Garza | Skender Construction of Indiana LLC | 476552.38 | 99.9% | 0% | 13.64% | -13.63% | 27006.23 | 325965.98
2023.839 Hamilton County National Guard Readiness Center | TI | Tommy Cohoat | Patterson Horth, Inc. | 1538998.61 | 109.1% | 0% | 12.88% | -12.88% | 139587.17 | 107210.99
2026.1039 Upland Prospect Street | TI | Tommy Cohoat | Bischoff Construction, LLC | 6500 | 99.31% | 0.02% | 1.54% | -1.51% | -44.85 | 0
MF.2024.924 Monon Trail Elementary | MF | Dustin Hurt | LTB Construction, Inc. | 4550 | 30.29% | -0.31% | -14.29% | 13.97% | -3171.81 | 0
2025.993 Batesville Public Library | TI | Shawn Welcher | Meyer Najem | 63852.15 | 100% | -0.03% | -16.32% | 16.3% | 1177.15 | 60528
2024.874 Noblesville HS Academic Addition & Renovation | TI | Trevor Anderson | The Peterson Company, LLC | 154487 | 100% | -0.02% | -30.07% | 30.05% | 0 | -14964

## WIP & Profit Fade
WIP & Profit Fade — by Project Manager
Over/under-billing and margin fade concentration • Knowify AJR
Project Manager | Jobs | Contract | Earned Rev | Invoiced | Overbilled | Underbilled | Profit $ | Avg Fade
Kelden Tyson | 7 | 21968892.5 | 11123522.66 | 10845050.5 | 0 | 278472.16 | 2529065.16 | -27.72%
Ben Garza | 15 | 21478175.74 | 15400262.83 | 14045132.84 | 0 | 1355129.99 | 3727694.98 | -31.3%
Cole Garriott | 9 | 9769260.28 | 9439140.04 | 9264104.84 | 93542.68 | 268577.88 | 3995964.28 | -42.27%
Tommy Cohoat | 18 | 5263888.85 | 5647287.31 | 5263888.85 | 67487.05 | 450885.51 | 1713382.65 | -43.39%
(Unassigned) | 221 | 3511824.01 | 1083403815.14 | 3160441.2 | 2093979.59 | 1082337353.53 | 442799.46 | 0%
Spencer Anderson | 14 | 2902929.11 | 1408311.75 | 1153658.1 | 34508.01 | 289161.66 | 426035.54 | -46.53%
Trevor Anderson | 10 | 2537123.47 | 2187191.93 | 2055030.84 | 117848.17 | 250009.26 | 619877.32 | -33.17%
Shawn Welcher | 5 | 789648.57 | 398409.43 | 564914.17 | 170925.05 | 4420.31 | 297582.31 | -26.43%
Ted Wells | 3 | 370396.31 | 362550.67 | 370395.32 | 8285.43 | 440.78 | 68931.9 | -37.82%
Dustin Hurt | 6 | 146234 | 99771.77 | 128069.01 | 28358.63 | 61.38 | 56995.26 | -19.52%

## AR Aging
Accounts Receivable Aging
By customer & bucket (QuickBooks, as of 2026-06-17) • retainage shown separately
Customer | Current | 1-30 | 31-60 | 61-90 | 91+ | Total
The Peterson Company, LLC | 1164329.53 | 54936.18 | 702311.21 | 0 | 0 | 1921576.92
Skender Construction of Indiana LLC | 647564.65 | 708983.51 | 134622.54 | 111708.94 | 46273.32 | 1649152.96
MILHAUS Construction | 509895 | 206955 | 510367.5 | 256635 | 0 | 1483852.5
Thompson Thrift Construction | 569642.4 | 571623.75 | 0 | 0 | 51060 | 1192326.15
Clark Construction | 889172 | 129947 | 0 | 0 | 0 | 1019119
Old Town Construction | 352057.58 | 0 | 407993.89 | 0 | 0 | 760051.47
Marous Brothers Construction | 119746.42 | 435716.98 | 0.01 | 0 | 0 | 555463.41
ARCO Design/Build | 385369.33 | 26117.77 | 73818 | 0 | 22752 | 508057.1
Avenue Construction, Inc. | 387512.38 | 0 | 66047.2 | 0 | 0 | 453559.58
Compass Commercial Construction Group | 352621.67 | 0 | 68841.54 | 0 | 0 | 421463.21
Garmong Construction Services | 141648.31 | 236453.93 | 0 | 0 | 0 | 378102.24
ACS-Affiliated Construction Services, Inc. | 45416.23 | 36620.15 | 72880.67 | 0 | 144737.82 | 299654.87
Holladay Construction Group | 202650.67 | 82260 | 0 | 0 | 0 | 284910.67
Shiel Sexton | 24028.81 | 0 | 248464.3 | 0 | 0 | 272493.11
Centric Projects, LLC | 174505.69 | 77705.72 | 0 | 0 | 0 | 252211.41
Meyer Najem | 6267.5 | 0 | 0 | 26925.21 | 188023.46 | 221216.17
J.C. Hart Company, Inc. | 96132.92 | 63353.47 | 0 | 0 | 0 | 159486.39
Patterson Horth, Inc. | 0 | 0 | 0 | 0 | 143724.99 | 143724.99
Arbor Homes | 112439.58 | 0 | 0 | 20386.58 | -12094.76 | 120731.4
Flores Drywall and Remodeling LLC | 91048.9 | 15112.12 | 0 | 0 | 0 | 106161.02
DEEM, LLC | 61895.38 | 2000 | 4225.5 | 28757.01 | 5000.03 | 101877.92
Patch Development | 15211.87 | 44532.3 | 1350 | 0 | 39000 | 100094.17
Stenz Corp | 9190.37 | 9000 | 36934.63 | 18000 | 0 | 73125
Novo Development Group, LLC | 60165.16 | 0 | -1973.34 | 0 | 0 | 58191.82
GSI - Gregory Scott Inabnit LLC | 0 | 0 | 0 | 0 | 52867.87 | 52867.87
County Prestress & Precast, LLC | 30500 | 0 | 22000 | 0 | 0 | 52500
Precision Dry Wall | 26295.22 | 16327.53 | 0 | 0 | 0 | 42622.75
BW Facility Management, LLC | 34444.01 | 0 | 0 | 0 | 0 | 34444.01
Kjt General Construction | 0 | 0 | 0 | 2072.89 | 26152.31 | 28225.2
The ACTS Collaborative, LLC | 28129.5 | 0 | 0 | 0 | 0 | 28129.5
Pro Fix Drywaller, LLC | 0 | 0 | 0 | 0 | 22972.34 | 22972.34
Mitsch Design | 0 | 0 | 0 | 0 | 19000 | 19000
Yaggi's White Glove Delivery, LLC | 0 | 0 | 0 | 0 | 18935.33 | 18935.33
Daniel T Swanson | 0 | 16000 | 0 | 0 | 0 | 16000
Becknell Industries | 13100 | 0 | 0 | 0 | 2500 | 15600
Community Drywall | 0 | 0 | 0 | 0 | 13844.41 | 13844.41
Big Dawg Drywall | 0 | 5928.42 | 0 | 0 | 7365.93 | 13294.35
Michael Valentine | 0 | 0 | 0 | 0 | 12430.13 | 12430.13
ZMX Inc. | 0 | 0 | 0 | 0 | 10646.9 | 10646.9
Cargo Loop, LLC | 10417 | 0 | 0 | 0 | 0 | 10417
Indiana Steel Fabricating | 8000 | 0 | 0 | 0 | 0 | 8000
Cornerstone Flooring | 0 | 0 | 0 | 7500 | 0 | 7500
JRA Architecture, LLC | 0 | 6000 | 0 | 0 | 0 | 6000
Lauth Group, Inc. | 0 | 0 | 0 | 0 | 5000 | 5000
MDG Holdings, LLC | 0 | 0 | 0 | 0 | 4708.82 | 4708.82
DLR Group | 0 | 0 | 4500 | 0 | 0 | 4500
Total Drywall Solutions Inc | 0 | 0 | 0 | 0 | 4485.21 | 4485.21
Bischoff Construction, LLC | 4020 | 0 | 0 | 0 | 0 | 4020
Forge Construction, LLC | 3600 | 0 | 0 | 0 | 0 | 3600
Enviro-Max | 0 | 0 | 0 | 3500 | 0 | 3500
Convivio Italian Artisan Cuisine (SPIGA Noblesville) | 2555.2 | 0 | 0 | 0 | 0 | 2555.2
Diaz Gutter and Drywall, LLC | 0 | 0 | 0 | 0 | 2399.42 | 2399.42
Indianapolis Fire Department | 0 | 0 | 0 | 0 | 768.35 | 768.35
Priority Constructors | 0 | 0 | 0 | 0 | 720.06 | 720.06
The Home Depot, Inc. | 0 | 0 | 0 | 0 | 585.54 | 585.54
TOTAL TRADE A/R | 6579573.28 | 2745573.83 | 2352383.65 | 475485.63 | 833859.48 | 12986875.87
Retainage Receivable (held, not aging) | [5 empty] | 3136194.46

## AP Aging
Accounts Payable Aging
By vendor & bucket (QuickBooks, as of 2026-06-17)
Vendor | Current | 1-30 | 31-60 | 61-90 | 91+ | Total
Foundation Building Materials (FBM) | 832567.56 | 0 | -620.94 | 0 | -2979.13 | 828967.49
Home Depot (HD Pro) | 739119.02 | 0 | 0 | 0 | 0 | 739119.02
Lowe's | 303594.49 | 14199.9 | 20320.44 | 0 | 76.41 | 338191.24
Sherwin Williams | 203177.5 | 1839.06 | -10.27 | -486.97 | -494.67 | 204024.65
United (GMS)/Cherokee Building Materials | 177526.44 | 0 | 0 | 0 | 0 | 177526.44
Mendoza Construction LLC (V) | 146738.27 | 3000 | 3736.5 | 0 | 9485.38 | 162960.15
Interior Supply Inc (ISI) | 129139.47 | 0 | 13.37 | 0 | 0 | 129152.84
Internal Drywall Division | 113560.43 | 0 | 0 | 0 | 0 | 113560.43
Prime Drywall Services LLC | 92882.96 | 0 | 3000 | 404.64 | 3200.56 | 99488.16
Nemix Painting & Construction LLC | 60338.96 | 1985.5 | 0 | 11248.05 | 8485.76 | 82058.27
Home Depot | 71539.66 | 0 | 0 | 0 | 0 | 71539.66
Jose Antonio Gallegos Alvarez | 54757.04 | 1260 | 1962.2 | 6076.3 | 7185.34 | 71240.88
AZS General Construction Corp | 39860.36 | 6800 | 6663.8 | 2568.19 | 7604.3 | 63496.65
United Rentals Inc. | 50995.72 | 0 | 0 | 0 | 0 | 50995.72
MacAllister Rentals (R) | 47500.09 | 0 | 0 | 0 | -133.75 | 47366.34
Mendoza Innovations, LLC | 0 | 46637.84 | 0 | 0 | 0 | 46637.84
C&C Martinez Drywall LLC | 38293.86 | 0 | 0 | 3310.96 | 1305.46 | 42910.28
GTZ Builders, LLC (Paulo) | 30842.4 | 0 | 0 | 0 | 0 | 30842.4
Iracheta Drywall LLC | 25249.02 | 0 | 0 | 0 | 1972.98 | 27222
Indy Pro Painters Services, LLC | 11669.8 | 0 | 1800 | 3822.5 | 9740 | 27032.3
LH Industrial | 20346.53 | 0 | 0 | -117.52 | 0 | 20229.01
Haines, Jones, & Cadbury, LLC | 18675.29 | 0 | 0 | 0 | 0 | 18675.29
Riteway Tool & Fasteners | 17855.06 | 0 | 0 | 0 | -44.73 | 17810.33
Sandra Yanett Ayala LLC | 5476.52 | 0 | 2668.78 | 7456.06 | 0 | 15601.36
ABC Supply Interiors, Inc. (L&W) | 18002.12 | 0 | 0 | 0 | -3711.8 | 14290.32
BA Construction Remodeling LLC | 12443 | 0 | 0 | 0 | 0 | 12443
Saravia Drywall, LLC | 11280 | 0 | 0 | 0 | 0 | 11280
Barahona Painting LLC | 10397.46 | 0 | 0 | 0 | 0 | 10397.46
JR Woodworks and Custom Cabinets LLC | 6010 | 3890 | 0 | 0 | 0 | 9900
Interior Product Supply (IPS) GMS Co (Cherokee BM) | 9710.52 | 0 | 0 | 0 | 0 | 9710.52
GTO Drywall & Metal Framing LLC | 3325.4 | 6089.4 | 0 | 0 | 0 | 9414.8
Kjt General Construction LLC (V) | 8971.91 | 0 | 0 | 0 | 0 | 8971.91
4BRO Construction LLC | 8825.79 | 0 | 0 | 0 | 0 | 8825.79
Professional Handling and Distribution | 8356.22 | 0 | 0 | 0 | 0 | 8356.22
Osorio Construction LLC (Rene) | 8015 | 0 | 0 | 0 | 0 | 8015
Bro's Drywall LLC | 7732 | 0 | 48 | 0 | 24 | 7804
Escot Painting LLC | 0 | 0 | 0 | 7700 | 0 | 7700
ADL Design & Construction LLC | 0 | 0 | 0 | 0 | 6316.5 | 6316.5
Top Team Quality Building LLC | 5378.2 | 0 | 819.2 | 0 | 0 | 6197.4
Ociel Medina (Gem Interiors) | 6101.04 | 0 | 0 | 0 | 0 | 6101.04
Precision Doors & Hardware | 0 | 0 | 0 | 0 | 6000 | 6000
Mariona Construction LLC | 5328.35 | 0 | 0 | 0 | 0 | 5328.35
Oliverio Mejia H, LLC | 2821.6 | 2385 | 0 | 0 | 0 | 5206.6
Lion's Construction LLC | 3942.55 | 0 | 0 | 0 | 617.1 | 4559.65
Deem | 3325 | 0 | 0 | 0 | 0 | 3325
Lot Construction, LLC (Omar) | 1858.7 | 0 | 1293.6 | 0 | 0 | 3152.3
JC Drywall LLC (JCD) | 70 | 0 | 0 | 0 | 3077.1 | 3147.1
Precise Tile and Stone LLC | 3099.87 | 0 | 0 | 0 | 0 | 3099.87
LL Herrera LLC | 3056.61 | 0 | 0 | 0 | 0 | 3056.61
Miracle Painting LLC - Jose Otoya | 3054.15 | 0 | 0 | 0 | 0 | 3054.15
Central Indiana Hardware (CIH) | 2952.13 | 0 | 0 | 0 | 0 | 2952.13
Lanmor Services | 2945.15 | 0 | 0 | 0 | 0 | 2945.15
Jordan Birge | 2764.19 | 0 | 0 | 0 | 0 | 2764.19
Construction Specialties, Inc. | 2754.18 | 0 | 0 | 0 | 0 | 2754.18
Hilti | 2689.56 | 0 | 0 | 0 | 0 | 2689.56
Browning Chapman, LLC | 2550 | 0 | 0 | 0 | 0 | 2550
Castillo (Victor) Drywall & Scrap LLC | 2471.9 | 0 | 0 | 0 | 0 | 2471.9
Best Way of Indiana, Inc. | 2408.11 | 0 | 0 | 0 | 0 | 2408.11
RWR 504 Construction LLC | 2280 | 0 | 0 | 0 | 0 | 2280
Shaevitz Construction Inc. | 2277.46 | 0 | 0 | 0 | 0 | 2277.46
Sunbelt Rentals Inc. | 1907.34 | 0 | 0 | 0 | 0 | 1907.34
ProMasters Drywall & Painting | 0 | 1770 | 0 | 0 | 0 | 1770
Alejandro Gonzalez-Rubio | 1650 | 0 | 0 | 0 | 0 | 1650
DIVISION 7 MTLS | 1525.82 | 0 | 0 | 0 | 0 | 1525.82
6twenty-six inc | 1337.5 | 0 | 0 | 0 | 0 | 1337.5
On-Site Supply | 1143.4 | 0 | 0 | 0 | 0 | 1143.4
Southwest Solutions Group, Inc. | 1080 | 0 | 0 | 0 | 0 | 1080
Oaks Dumpster Rental | 960.22 | 0 | 0 | 0 | 0 | 960.22
Garza Towing LLC | 0 | 875 | 0 | 0 | 0 | 875
7R Lawn Solutions, LLC | 0 | 836 | 0 | 0 | 0 | 836
The Best Tile Installation (Nagio Company LLC) | 833.75 | 0 | 0 | 0 | 0 | 833.75
Brother's Carpentry (Gustavo Gutierrez) | 145.05 | 0 | 0 | 0 | 652 | 797.05
CraneWorks ¦ CW Intermediate Holdco, LLC | 789.4 | 0 | 0 | 0 | 0 | 789.4
Indianapolis Propane Exchange LLC | 583.14 | 0 | 0 | 0 | 0 | 583.14
White Cap, L.P. | 467.79 | 0 | 0 | 0 | 0 | 467.79
Julio Juarez (Expenses) | 400 | 0 | 0 | 0 | 0 | 400
Pomp's Tire Service, Inc. | 383.71 | 0 | 0 | 0 | 0 | 383.71
RGT Construction LLC | 0 | 0 | 0 | 0 | 346.5 | 346.5
Gauge Telematics, Inc | 345 | 0 | 0 | 0 | 0 | 345
Garners Towing & Transport | 0 | 0 | 0 | 312.5 | 0 | 312.5
Reliable Access LLC | 0 | 275 | 0 | 0 | 0 | 275
ARC Document Solutions, LLC | 259.57 | 0 | 0 | 0 | 0 | 259.57
Chris Taylor | 250 | 0 | 0 | 0 | 0 | 250
Enterprise Rent a Car | 227.01 | 0 | 0 | 0 | 0 | 227.01
Mirabito Energy Products | 110.13 | 100.84 | 0 | 0 | 0 | 210.97
ABM Parking Services | 180 | 0 | 0 | 0 | 0 | 180
Victor Garza (Expenses) | 0 | 0 | 165.68 | 0 | 0 | 165.68
Concentra | 0 | 0 | 0 | 125 | 0 | 125
Luis Ruiz (Expenses) | 0 | 100 | 0 | 0 | 0 | 100
Indy Crush Brothers, LLC (Indy Crusher) | 0 | 0 | 0 | 0 | 10.8 | 10.8
Armstrong World Industries, Inc. | 0 | 0 | 0 | 0 | -150.69 | -150.69
Kelley Bros Hardware Corp | 0 | 0 | 0 | 0 | -369.15 | -369.15
Cherokee Building Materials, Inc. (GMS) | 0 | 0 | 0 | 0 | -627.67 | -627.67
Valley Interior Products (GMS) | 302.7 | 0 | 0 | 0 | -1141.64 | -838.94
84 Lumber | 0 | 0 | 0 | 0 | -1222.78 | -1222.78
TOTAL A/P | 3423786.15 | 92043.54 | 41860.36 | 42419.71 | 55224.18 | 3655333.94

## Cash & Liquidity
Cash & Liquidity — Covenant View
QuickBooks cash + LOC • covenant inputs are USER-MAINTAINED (see yellow) • as of 2026-06-17
Cash Balance | -54623.3 | QuickBooks balance sheet
Operating Cash Flow (YTD) | 1708994.16 | QB cash flow statement
Investing Cash Flow (YTD) | 212852.1
Financing Cash Flow (YTD) | -1650418.17
Net Cash Change (YTD) | 271428.09
LOC Drawn | 5440076.95 | QB — Forum Line of Credit (0874)
LOC Limit | 8000000 | USER INPUT — set your Forum commitment
LOC Utilization | 68% | drawn / limit
Advance Rate | 80% | USER INPUT — borrowing-base advance rate
Eligible A/R | 12986875.87 | USER INPUT — eligible borrowing base (default = trade A/R)
BBC Availability (headroom) | 2559923.05 | min(EligibleAR×Advance, Limit) − Drawn
Liquidity Status | Healthy

## Balance Sheet
Balance Sheet
QuickBooks, as of 2026-06-17
Account | Section | Amount
Cash | Assets | -54623.3
Accounts Receivable | Assets | 12986875.87
Retainage Receivable | Assets | 3136194.46
Drywall Inventory | Assets | 593395.59
WIP Underbillings | Assets | 2889941.58
Other Current Assets (net) | Assets | 82113.84
Fixed Assets | Assets | 694113.61
Other Assets | Assets | 2223043.34
TOTAL ASSETS |  | 22551054.99
Accounts Payable | Liabilities | 3655333.94
Credit Cards | Liabilities | 15836.29
Line of Credit (Forum 0874) | Liabilities | 5440076.95
CapX Line of Credit (Forum 1708) | Liabilities | 333834.01
WIP Overbillings | Liabilities | 1651664.83
Other Current Liabilities (net) | Liabilities | 2747267.42
Long-term Liabilities | Liabilities | 8372.29
TOTAL LIABILITIES |  | 13852385.73
Total Equity | Equity | 8698669.26
TOTAL EQUITY |  | 8698669.26

## Data Health
Data Health & Refresh
Trust panel — surfaces data-hygiene issues that would distort the numbers
Check | Value | Note
Last data refresh (as-of) | 2026-06-17
Active jobs (Knowify) | 308 | JobsReport Total = 308
Managed jobs (PM + budget + ≥$1k) | 84
Active jobs missing a PM | 221 | assign in Knowify
Active jobs missing a budget | 220 | load budget in Knowify
GL $ in UNALLOCATED division | $0 | fix QuickBooks Class tagging
YTD2026 Revenue ties to QB | $28,774,215 | QB P&L 28,774,215.27
YTD2026 Net Income ties to QB | $5,340,197 | QB cash flow 5,340,196.80
Trade A/R ties to balance sheet | $12,986,876 | QB BS A/R 12,986,876
A/P ties to balance sheet | $3,655,334 | QB BS A/P 3,655,334
Total assets (QB) | $22,551,055

## » Fact_GL
Account | Period | PeriodEnd | DivKey | Amount | Category
Billable Expense Income | FY2024 | 2024-12-31 | ALL | 10032 | Revenue
Doors and Windows | FY2024 | 2024-12-31 | ALL | 237386.66 | Revenue
Drywall Sales Income | FY2024 | 2024-12-31 | DW | -6863.55 | Revenue
Drywall Service Income | FY2024 | 2024-12-31 | DW | 3983560.92 | Revenue
Drywall Division Delivery Income | FY2024 | 2024-12-31 | DW | 1062721.25 | Revenue
Drywall Division Material Income | FY2024 | 2024-12-31 | DW | 2840679.74 | Revenue
Drywall Tax | FY2024 | 2024-12-31 | DW | 348.74 | Revenue
Engineering Project Income | FY2024 | 2024-12-31 | EN | 16000 | Revenue
Finishes | FY2024 | 2024-12-31 | ALL | 1499889.18 | Revenue
Metals | FY2024 | 2024-12-31 | ALL | 1715940.63 | Revenue
Sales | FY2024 | 2024-12-31 | ALL | 4079740.08 | Revenue
Service/Fee Income | FY2024 | 2024-12-31 | ALL | 22772419.95 | Revenue
Specialties | FY2024 | 2024-12-31 | ALL | 87799.97 | Revenue
Thermal and Moisture Control | FY2024 | 2024-12-31 | ALL | 401319.14 | Revenue
WIP Adj - Net change | FY2024 | 2024-12-31 | ALL | 67516.35 | Revenue
Wood and Plastics | FY2024 | 2024-12-31 | ALL | 769283.84 | Revenue
Cost of labor - Contractors | FY2024 | 2024-12-31 | ALL | 8808010.66 | COGS
Cost of labor - Direct Labor | FY2024 | 2024-12-31 | ALL | 184100.65 | COGS
Drywall Supply External Expense | FY2024 | 2024-12-31 | DW | 5816123.6 | COGS
Drywall Supply Internal Expense | FY2024 | 2024-12-31 | DW | 3968871.29 | COGS
Job Site Expenses | FY2024 | 2024-12-31 | ALL | 8775597.67 | COGS
Equipment Rental | FY2024 | 2024-12-31 | ALL | 920967.55 | COGS
Per Diem Job Expense | FY2024 | 2024-12-31 | ALL | 1500 | COGS
Shipping, Freight & Delivery - COS | FY2024 | 2024-12-31 | ALL | 50 | COGS
Vendor Discounts | FY2024 | 2024-12-31 | ALL | -40004.49 | COGS
Advertising & Marketing | FY2024 | 2024-12-31 | ALL | 95529.38 | Operating Expense
Bad Debt | FY2024 | 2024-12-31 | ALL | 23833.47 | Operating Expense
Bank Charges & Fees | FY2024 | 2024-12-31 | ALL | 6245.61 | Operating Expense
Car & Truck | FY2024 | 2024-12-31 | ALL | 295631.01 | Operating Expense
DEF - Boom Truck | FY2024 | 2024-12-31 | ALL | 53.48 | Operating Expense
DOT Boom Trucks Compliance | FY2024 | 2024-12-31 | ALL | 156.66 | Operating Expense
Fuel Diesel - Boom Truck | FY2024 | 2024-12-31 | ALL | 43432.76 | Operating Expense
Fuel Truck - Company Pickup | FY2024 | 2024-12-31 | ALL | 602.67 | Operating Expense
Service - Boom Truck | FY2024 | 2024-12-31 | ALL | 8302.63 | Operating Expense
Charitable Contributions | FY2024 | 2024-12-31 | ALL | 9650 | Operating Expense
Contractors | FY2024 | 2024-12-31 | ALL | 29907.28 | Operating Expense
Depreciation | FY2024 | 2024-12-31 | ALL | 159278.79 | Operating Expense
Drywall Division Labor - Subcontractors | FY2024 | 2024-12-31 | DW | 147790.5 | Operating Expense
Dues & subscriptions | FY2024 | 2024-12-31 | ALL | 4350.79 | Operating Expense
Equipment/Vehicle Rental | FY2024 | 2024-12-31 | ALL | 8828.66 | Operating Expense
Freight | FY2024 | 2024-12-31 | ALL | 1800 | Operating Expense
Insurance | FY2024 | 2024-12-31 | ALL | 186947.02 | Operating Expense
Interest Paid | FY2024 | 2024-12-31 | ALL | 240799.34 | Operating Expense
Job Supplies | FY2024 | 2024-12-31 | ALL | 31581.94 | Operating Expense
Legal & Professional Services | FY2024 | 2024-12-31 | ALL | 236680.09 | Operating Expense
Meals & Entertainment | FY2024 | 2024-12-31 | ALL | 166308.92 | Operating Expense
Melio Credit card fee | FY2024 | 2024-12-31 | ALL | 60 | Operating Expense
Office Supplies & Software | FY2024 | 2024-12-31 | ALL | 171877.26 | Operating Expense
Software Subscription/Use Fee | FY2024 | 2024-12-31 | ALL | 249.99 | Operating Expense
Other Business Expenses | FY2024 | 2024-12-31 | ALL | 3875.79 | Operating Expense
Outsourced IT Services | FY2024 | 2024-12-31 | ALL | 49394.22 | Operating Expense
Bonus | FY2024 | 2024-12-31 | ALL | 307801.24 | Operating Expense
Commission | FY2024 | 2024-12-31 | ALL | 95163.98 | Operating Expense
Employee Benefits | FY2024 | 2024-12-31 | ALL | 222721.47 | Operating Expense
Health Insurance | FY2024 | 2024-12-31 | ALL | 18452.01 | Operating Expense
Payroll Fees | FY2024 | 2024-12-31 | ALL | 50898.56 | Operating Expense
Taxes | FY2024 | 2024-12-31 | ALL | 359219.18 | Operating Expense
Wages | FY2024 | 2024-12-31 | ALL | 4255653.27 | Operating Expense
Property Tax | FY2024 | 2024-12-31 | ALL | 26000 | Operating Expense
Reimbursable Expenses | FY2024 | 2024-12-31 | ALL | 12195.98 | Operating Expense
Rent & Lease | FY2024 | 2024-12-31 | ALL | 553295.17 | Operating Expense
Repairs & Maintenance | FY2024 | 2024-12-31 | ALL | 100368.49 | Operating Expense
Small Tools & Equipment | FY2024 | 2024-12-31 | ALL | 67494.59 | Operating Expense
Taxes & Licenses | FY2024 | 2024-12-31 | ALL | 82933.23 | Operating Expense
Travel | FY2024 | 2024-12-31 | ALL | 133886.05 | Operating Expense
Utilities | FY2024 | 2024-12-31 | ALL | 39792.66 | Operating Expense
Credit Card Rewards | FY2024 | 2024-12-31 | ALL | 1630.56 | Other Income
Interest Earned | FY2024 | 2024-12-31 | ALL | 0.18 | Other Income
Other Income | FY2024 | 2024-12-31 | ALL | 45680.23 | Other Income
Subletter Rent Income | FY2024 | 2024-12-31 | ALL | 19535.36 | Other Income
Subletter Utility Income | FY2024 | 2024-12-31 | ALL | 2000 | Other Income
Gain or Loss on Assets | FY2024 | 2024-12-31 | ALL | 23197.6 | Other Expense
Billable Expense Income | FY2025 | 2025-12-31 | ALL | 543 | Revenue
Doors and Windows | FY2025 | 2025-12-31 | ALL | 4594.5 | Revenue
Drywall Service Income | FY2025 | 2025-12-31 | DW | 3358176.13 | Revenue
Drywall Division Delivery Income | FY2025 | 2025-12-31 | DW | 201.04 | Revenue
Drywall Division Material Income | FY2025 | 2025-12-31 | DW | 2824148.9 | Revenue
Drywall Supply Arbor Income | FY2025 | 2025-12-31 | DW | 959002.74 | Revenue
Drywall Supply Century Income | FY2025 | 2025-12-31 | DW | 105734.39 | Revenue
Drywall Supply HD Boom Scatter Income | FY2025 | 2025-12-31 | DW | 174372.44 | Revenue
Drywall Supply Pulte Income | FY2025 | 2025-12-31 | DW | 6230.22 | Revenue
Drywall Tax | FY2025 | 2025-12-31 | DW | 67.77 | Revenue
Engineering Project Income | FY2025 | 2025-12-31 | EN | 709295 | Revenue
Finishes | FY2025 | 2025-12-31 | ALL | 76310.01 | Revenue
Sales | FY2025 | 2025-12-31 | ALL | 13469.39 | Revenue
Service/Fee Income | FY2025 | 2025-12-31 | ALL | 33721642.66 | Revenue
Specialties | FY2025 | 2025-12-31 | ALL | 2713.5 | Revenue
WIP Adj - Net change | FY2025 | 2025-12-31 | ALL | -1464686.27 | Revenue
Cost of labor - Contractors | FY2025 | 2025-12-31 | ALL | 9409610.39 | COGS
Warranty Labor Expense | FY2025 | 2025-12-31 | ALL | 471.77 | COGS
Cost of labor - Direct Labor | FY2025 | 2025-12-31 | ALL | 212902.67 | COGS
Drywall Supply Arbor Expense | FY2025 | 2025-12-31 | DW | 753899.54 | COGS
Drywall Supply Century Expense | FY2025 | 2025-12-31 | DW | 103164.28 | COGS
Drywall Supply External Expense | FY2025 | 2025-12-31 | DW | 2526119.47 | COGS
Drywall Supply Internal Expense | FY2025 | 2025-12-31 | DW | 2861149.12 | COGS
Drywall Supply Pulte Expense | FY2025 | 2025-12-31 | DW | 5904.27 | COGS
Job Site Expenses | FY2025 | 2025-12-31 | ALL | 8194535.74 | COGS
Drywall Project (Material) Expense - Internal | FY2025 | 2025-12-31 | DW | 2788639.15 | COGS
Drywall Project (Tax) Expense - Internal | FY2025 | 2025-12-31 | DW | 174956.68 | COGS
Equipment Rental | FY2025 | 2025-12-31 | ALL | 669802.45 | COGS
Warranty Material Expense | FY2025 | 2025-12-31 | ALL | 148.15 | COGS
Per Diem Job Expense | FY2025 | 2025-12-31 | ALL | 64983 | COGS
Vendor Discounts | FY2025 | 2025-12-31 | ALL | -11150.24 | COGS
Advertising & Marketing | FY2025 | 2025-12-31 | ALL | 109327.23 | Operating Expense
Bad Debt | FY2025 | 2025-12-31 | ALL | 4583.55 | Operating Expense
Bank Charges & Fees | FY2025 | 2025-12-31 | ALL | 7808.93 | Operating Expense
Car & Truck | FY2025 | 2025-12-31 | ALL | 26351.78 | Operating Expense
DEF - Boom Truck | FY2025 | 2025-12-31 | ALL | 2696.79 | Operating Expense
DOT Boom Trucks Compliance | FY2025 | 2025-12-31 | ALL | 10905.77 | Operating Expense
Fuel Diesel - Boom Truck | FY2025 | 2025-12-31 | ALL | 104966.51 | Operating Expense
Drywall Supply HD Boom Scatter Diesel - Boom Truck | FY2025 | 2025-12-31 | DW | 7361.89 | Operating Expense
Fuel Truck - Company Pickup | FY2025 | 2025-12-31 | ALL | 14158.5 | Operating Expense
Service - Boom Truck | FY2025 | 2025-12-31 | ALL | 84192.67 | Operating Expense
Service - Boom Truck 1103 Volvo | FY2025 | 2025-12-31 | ALL | 34700.32 | Operating Expense
Service - Boom Truck 1107 Western Star | FY2025 | 2025-12-31 | ALL | 25081.77 | Operating Expense
Service - Boom Truck 1109 Freightliner 16 | FY2025 | 2025-12-31 | ALL | 24433.04 | Operating Expense
Service - Boom Truck 1110 Peterbilt 18 | FY2025 | 2025-12-31 | ALL | 20257.62 | Operating Expense
Service - Boom Truck 1111 Freightliner | FY2025 | 2025-12-31 | ALL | 518.59 | Operating Expense
Service - Boom Truck 1112 Peterbilt 17 | FY2025 | 2025-12-31 | ALL | 23433.72 | Operating Expense
Service - Company Truck | FY2025 | 2025-12-31 | ALL | 19306.29 | Operating Expense
Charitable Contributions | FY2025 | 2025-12-31 | ALL | 3313.04 | Operating Expense
Contractors | FY2025 | 2025-12-31 | ALL | 51647.33 | Operating Expense
Depreciation | FY2025 | 2025-12-31 | ALL | 190161.95 | Operating Expense
Drywall Division Labor - Subcontractors | FY2025 | 2025-12-31 | DW | 697055 | Operating Expense
Drywall Division Supplies Expense | FY2025 | 2025-12-31 | DW | 19211.23 | Operating Expense
Drywall Supply HD Boom Scatter Expense | FY2025 | 2025-12-31 | DW | 14857.55 | Operating Expense
Drywall Supply HD Boom Scatter Labor | FY2025 | 2025-12-31 | DW | 145428.75 | Operating Expense
Drywall Supply HD Boom Scatter Travel | FY2025 | 2025-12-31 | DW | 24614.8 | Operating Expense
Dues & subscriptions | FY2025 | 2025-12-31 | ALL | 5234.38 | Operating Expense
Equipment/Vehicle Rental | FY2025 | 2025-12-31 | ALL | 5868.22 | Operating Expense
Insurance | FY2025 | 2025-12-31 | ALL | 248733.08 | Operating Expense
Interest Paid | FY2025 | 2025-12-31 | ALL | 286637.57 | Operating Expense
Job Supplies | FY2025 | 2025-12-31 | ALL | 32962.99 | Operating Expense
Legal & Professional Services | FY2025 | 2025-12-31 | ALL | 213655.55 | Operating Expense
Meals & Entertainment | FY2025 | 2025-12-31 | ALL | 192274.77 | Operating Expense
Entertainment | FY2025 | 2025-12-31 | ALL | 18665.18 | Operating Expense
Office Supplies & Software | FY2025 | 2025-12-31 | ALL | 62125.49 | Operating Expense
Software Subscription/Use Fee | FY2025 | 2025-12-31 | ALL | 111775.41 | Operating Expense
Other Business Expenses | FY2025 | 2025-12-31 | ALL | 9413.48 | Operating Expense
Outsourced IT Services | FY2025 | 2025-12-31 | ALL | 74239.8 | Operating Expense
Outsourced Safety | FY2025 | 2025-12-31 | ALL | 2775.39 | Operating Expense
Bonus | FY2025 | 2025-12-31 | ALL | 374819.06 | Operating Expense
Commission | FY2025 | 2025-12-31 | ALL | 30018.33 | Operating Expense
Employee Benefits | FY2025 | 2025-12-31 | ALL | 281502.41 | Operating Expense
Health Insurance | FY2025 | 2025-12-31 | ALL | 12490.53 | Operating Expense
Payroll Fees | FY2025 | 2025-12-31 | ALL | 58838.35 | Operating Expense
Taxes | FY2025 | 2025-12-31 | ALL | 395840.67 | Operating Expense
Wages | FY2025 | 2025-12-31 | ALL | 4495102.3 | Operating Expense
Property Tax | FY2025 | 2025-12-31 | ALL | 34572.38 | Operating Expense
Reimbursable Expenses | FY2025 | 2025-12-31 | ALL | 510.9 | Operating Expense
Rent & Lease | FY2025 | 2025-12-31 | ALL | 1089976.37 | Operating Expense
Expenses — Unitemized | FY2025 | 2025-12-31 | ALL | 328196.88 | Operating Expense
Drywall Service Income | YTD2026 | 2026-06-17 | DW | 426214.72 | Revenue
Drywall Division Material Income | YTD2026 | 2026-06-17 | DW | 20720.33 | Revenue
Drywall Supply Arbor Income | YTD2026 | 2026-06-17 | DW | 880039.92 | Revenue
Drywall Supply Pulte Income | YTD2026 | 2026-06-17 | DW | 16826.61 | Revenue
Engineering Project Income | YTD2026 | 2026-06-17 | EN | 396425 | Revenue
Sales | YTD2026 | 2026-06-17 | ALL | 4820 | Revenue
Service/Fee Income | YTD2026 | 2026-06-17 | ALL | 24484720.25 | Revenue
WIP Adj - Net change | YTD2026 | 2026-06-17 | ALL | 2544448.44 | Revenue
Cost of labor - Contractors | YTD2026 | 2026-06-17 | ALL | 7895791.6 | COGS
Cost of labor - Direct Labor | YTD2026 | 2026-06-17 | ALL | 55994.93 | COGS
Drywall Supply External Expense | YTD2026 | 2026-06-17 | DW | 1044464.67 | COGS
Drywall Supply Internal Expense | YTD2026 | 2026-06-17 | DW | 2506052.68 | COGS
Job Site Expenses | YTD2026 | 2026-06-17 | ALL | 6333530.14 | COGS
Drywall Project (Material) Expense - Internal | YTD2026 | 2026-06-17 | DW | 4608.22 | COGS
Equipment Rental | YTD2026 | 2026-06-17 | ALL | 678220.74 | COGS
Per Diem Job Expense | YTD2026 | 2026-06-17 | ALL | 16970 | COGS
Advertising & Marketing | YTD2026 | 2026-06-17 | ALL | 51280.58 | Operating Expense
Ask My Accountant | YTD2026 | 2026-06-17 | ALL | 6860.41 | Operating Expense
Bad Debt | YTD2026 | 2026-06-17 | ALL | 129.56 | Operating Expense
Bank Charges & Fees | YTD2026 | 2026-06-17 | ALL | 1396.51 | Operating Expense
Car & Truck | YTD2026 | 2026-06-17 | ALL | 13052.56 | Operating Expense
DEF - Boom Truck | YTD2026 | 2026-06-17 | ALL | 789.69 | Operating Expense
Fuel Diesel - Boom Truck | YTD2026 | 2026-06-17 | ALL | 46511.46 | Operating Expense
Fuel Truck - Company Pickup | YTD2026 | 2026-06-17 | ALL | 14864.02 | Operating Expense
Service - Boom Truck | YTD2026 | 2026-06-17 | ALL | 4427.04 | Operating Expense
Service - Boom Truck 1109 Freightliner 16 | YTD2026 | 2026-06-17 | ALL | 20089.71 | Operating Expense
Service - Boom Truck 1110 Peterbilt 18 | YTD2026 | 2026-06-17 | ALL | 1744.4 | Operating Expense
Service - Boom Truck 1111 Freightliner | YTD2026 | 2026-06-17 | ALL | 4073.21 | Operating Expense
Service - Boom Truck 1112 Peterbilt 17 | YTD2026 | 2026-06-17 | ALL | 7459.83 | Operating Expense
Service - Company Truck | YTD2026 | 2026-06-17 | ALL | 18202.24 | Operating Expense
Charitable Contributions | YTD2026 | 2026-06-17 | ALL | 2500 | Operating Expense
Charitable Contributions - Non-Deductible | YTD2026 | 2026-06-17 | ALL | 1000 | Operating Expense
Contractors | YTD2026 | 2026-06-17 | ALL | 20900 | Operating Expense
Depreciation | YTD2026 | 2026-06-17 | ALL | 82317.22 | Operating Expense
Drywall Division Labor - Subcontractors | YTD2026 | 2026-06-17 | DW | 295694.45 | Operating Expense
Drywall Division Supplies Expense | YTD2026 | 2026-06-17 | DW | 1145.07 | Operating Expense
Drywall Supply HD Boom Scatter Labor | YTD2026 | 2026-06-17 | DW | 6750 | Operating Expense
Dues & subscriptions | YTD2026 | 2026-06-17 | ALL | 9937.75 | Operating Expense
Equipment/Vehicle Rental | YTD2026 | 2026-06-17 | ALL | 38424.43 | Operating Expense
Insurance | YTD2026 | 2026-06-17 | ALL | 67365.99 | Operating Expense
Interest Paid | YTD2026 | 2026-06-17 | ALL | 121195.1 | Operating Expense
Job Supplies | YTD2026 | 2026-06-17 | ALL | 10135.83 | Operating Expense
Legal & Professional Services | YTD2026 | 2026-06-17 | ALL | 61725.77 | Operating Expense
Meals & Entertainment | YTD2026 | 2026-06-17 | ALL | 51854.83 | Operating Expense
Entertainment | YTD2026 | 2026-06-17 | ALL | 39782.22 | Operating Expense
Meals | YTD2026 | 2026-06-17 | ALL | 9826.07 | Operating Expense
Office Supplies & Software | YTD2026 | 2026-06-17 | ALL | 69745.94 | Operating Expense
Software Subscription/Use Fee | YTD2026 | 2026-06-17 | ALL | 18150.82 | Operating Expense
Other Business Expenses | YTD2026 | 2026-06-17 | ALL | 672 | Operating Expense
Outsourced IT Services | YTD2026 | 2026-06-17 | ALL | 30498.71 | Operating Expense
Outsourced Safety | YTD2026 | 2026-06-17 | ALL | 3690.86 | Operating Expense
Bonus Accrual Expense | YTD2026 | 2026-06-17 | ALL | 280000 | Operating Expense
Commission | YTD2026 | 2026-06-17 | ALL | -36779.33 | Operating Expense
Misc / Spot Bonus Expense | YTD2026 | 2026-06-17 | ALL | 18413.44 | Operating Expense
Wage Accrual | YTD2026 | 2026-06-17 | ALL | 55000 | Operating Expense
Employee Benefits | YTD2026 | 2026-06-17 | ALL | 105098.32 | Operating Expense
Health Insurance | YTD2026 | 2026-06-17 | ALL | 7586.33 | Operating Expense
Payroll Fees | YTD2026 | 2026-06-17 | ALL | 22819.3 | Operating Expense
Taxes | YTD2026 | 2026-06-17 | ALL | 178252.15 | Operating Expense
Wages | YTD2026 | 2026-06-17 | ALL | 2023303.48 | Operating Expense
Property Tax | YTD2026 | 2026-06-17 | ALL | 2415.99 | Operating Expense
Rent & Lease | YTD2026 | 2026-06-17 | ALL | 730466.97 | Operating Expense
Repairs & Maintenance | YTD2026 | 2026-06-17 | ALL | 67548.41 | Operating Expense
Small Tools & Equipment | YTD2026 | 2026-06-17 | ALL | 8304.62 | Operating Expense
Taxes & Licenses | YTD2026 | 2026-06-17 | ALL | 32442.25 | Operating Expense
Training & Education | YTD2026 | 2026-06-17 | ALL | 8981.1 | Operating Expense
Travel | YTD2026 | 2026-06-17 | ALL | 83545.36 | Operating Expense
Travel - Fuel | YTD2026 | 2026-06-17 | ALL | 854.75 | Operating Expense
Travel - Meals | YTD2026 | 2026-06-17 | ALL | 4474.73 | Operating Expense
Uncategorized Expense | YTD2026 | 2026-06-17 | ALL | 263.49 | Operating Expense
Utilities | YTD2026 | 2026-06-17 | ALL | 45546.25 | Operating Expense
Credit Card Rewards | YTD2026 | 2026-06-17 | ALL | 1236.4 | Other Income
Interest Earned | YTD2026 | 2026-06-17 | ALL | 0.09 | Other Income
Other Income | YTD2026 | 2026-06-17 | ALL | 318.41 | Other Income
Vendor Rebate Income | YTD2026 | 2026-06-17 | ALL | 53642.01 | Other Income
Gain or Loss on Assets | YTD2026 | 2026-06-17 | ALL | 180850.51 | Other Expense

## » Fact_WIP
SnapshotDate | ProjectId | Job | DivKey | PMName | Customer | Status | ContractTotal | ChangeOrders | Invoiced | PaymentsInvoices | BudgetTotal | ActualCost | PctComplete | EarnedRevenue | WIPNet | KnowifyWIP | Overbilled | Underbilled | ProfitAmount | ProfitPct | ProjectedProfit | ProjectedProfitPct | EstMarginPct | ProfitFadePct | Retainage | OpenAR | HasBudget | Managed
2026-06-17 | 2902164 | DS.2026.2440 Liberty Assisted Living 0612 | UN | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 8481.92 | 0 | 8481.92 | 0 | 0 | 7188.44 | 0 | 0 | -8481.92 | 0 | 8481.92 | 0 | 1293.48 | 0.1525 | 100 | 0.0118 | 0 | 0 | 0 | 8481.92 | FALSE | FALSE
2026-06-17 | 2894730 | 2026.1059 Westfield Community Schools | UN | Dustin Hurt | LTB Construction, Inc. | ACTIVE | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0.02 | 0 | 0 | 0 | 0 | FALSE | FALSE
2026-06-17 | 2893583 | 2026.1058 Patch McCordsville Building 1 | UN | Spencer Anderson | Patch Development | ACTIVE | 211750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0.0005 | 0 | 0 | 0 | 0 | FALSE | FALSE
2026-06-17 | 2889499 | DS.2026.2439 2335 Treesdale Circle | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 527.31 | 0 | 527.31 | 0 | 0 | 378.63 | 0 | 0 | -527.31 | 0 | 527.31 | 0 | 148.68 | 0.282 | 100 | 0.1896 | 0 | 0 | 0 | 527.31 | FALSE | FALSE
2026-06-17 | 2888259 | DS.2026.2438 10806 McPherson St | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 3124.93 | 0 | 3124.93 | 0 | 0 | 1833.96 | 0 | 0 | -3124.93 | 0 | 3124.93 | 0 | 1290.97 | 0.4131 | 100 | 0.032 | 0 | 0 | 0 | 3124.93 | FALSE | FALSE
2026-06-17 | 2888192 | DS.2026.2437 970 Starkey Ave | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 8372.52 | 0 | 8372.52 | 0 | 0 | 5495.96 | 0 | 0 | -8372.52 | 0 | 8372.52 | 0 | 2876.56 | 0.3436 | 100 | 0.0119 | 0 | 0 | 0 | 8372.52 | FALSE | FALSE
2026-06-17 | 2887165 | MDG Warehouse Demising Wall | UN | (Unassigned) | MDG Real Estate LLC | ACTIVE | 75000 | 0 | 0 | 0 | 0 | 6847.14 | 0 | 0 | 0 | 0 | 0 | 0 | -6847.14 | 0 | 100 | 0.0013 | 0 | 0 | 0 | 0 | FALSE | FALSE
2026-06-17 | 2887151 | DS.2026.2436 25 Harper Estates | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 5768.6 | 0 | 5768.6 | 0 | 0 | 4226.3 | 0 | 0 | -5768.6 | 0 | 5768.6 | 0 | 1542.3 | 0.2674 | 100 | 0.0173 | 0 | 0 | 0 | 5768.6 | FALSE | FALSE
2026-06-17 | 2887141 | DS.2026.2435 21 Harper Estates | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 6176 | 0 | 6176 | 0 | 0 | 4487.52 | 0 | 0 | -6176 | 0 | 6176 | 0 | 1688.48 | 0.2734 | 100 | 0.0162 | 0 | 0 | 0 | 6176 | FALSE | FALSE
2026-06-17 | 2887107 | DS.2026.2434 19 Harper Estates | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 6043.1 | 0 | 6043.1 | 0 | 0 | 4392.06 | 0 | 0 | -6043.1 | 0 | 6043.1 | 0 | 1651.04 | 0.2732 | 100 | 0.0165 | 0 | 0 | 0 | 6043.1 | FALSE | FALSE
2026-06-17 | 2872036 | DS.2026.2433 Liberty Assisted Living 0529 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 9607.6 | 0 | 9607.6 | 0 | 0 | 7386.98 | 0 | 0 | -9607.6 | 0 | 9607.6 | 0 | 2220.62 | 0.2311 | 100 | 0.0104 | 0 | 0 | 0 | 9607.6 | FALSE | FALSE
2026-06-17 | 2872017 | DS.2026.2432 Liberty Assisted LIving 0528 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 12455.2 | 0 | 12455.2 | 0 | 0 | 8760.96 | 0 | 0 | -12455.2 | 0 | 12455.2 | 0 | 3694.24 | 0.2966 | 100 | 0.008 | 0 | 0 | 0 | 12455.2 | FALSE | FALSE
2026-06-17 | 2872004 | DS.2026.2431 123 Centre Place | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 3188.13 | 0 | 3188.13 | 0 | 0 | 2336.22 | 0 | 0 | -3188.13 | 0 | 3188.13 | 0 | 851.91 | 0.2672 | 100 | 0.0314 | 0 | 0 | 0 | 3188.13 | FALSE | FALSE
2026-06-17 | 2871958 | DS.2026.2430 119 Centre Place | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 3188.13 | 0 | 3188.13 | 0 | 0 | 2336.22 | 0 | 0 | -3188.13 | 0 | 3188.13 | 0 | 851.91 | 0.2672 | 100 | 0.0314 | 0 | 0 | 0 | 3188.13 | FALSE | FALSE
2026-06-17 | 2871926 | DS.2026.2429 108 Centre Place | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 3468.6 | 0 | 3468.6 | 0 | 0 | 2537.94 | 0 | 0 | -3468.6 | 0 | 3468.6 | 0 | 930.66 | 0.2683 | 100 | 0.0288 | 0 | 0 | 0 | 3468.6 | FALSE | FALSE
2026-06-17 | 2871859 | DS.2026.2428 9 Centre Place | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 4637.64 | 0 | 4637.64 | 0 | 0 | 3598.89 | 0 | 0 | -4637.64 | 0 | 4637.64 | 0 | 1038.75 | 0.224 | 100 | 0.0216 | 0 | 0 | 0 | 4637.64 | FALSE | FALSE
2026-06-17 | 2863766 | DS.2026.2427 Dapp Garage | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 1892.4 | 0 | 1892.4 | 0 | 0 | 1278.6 | 0 | 0 | -1892.4 | 0 | 1892.4 | 0 | 613.8 | 0.3244 | 100 | 0.0528 | 0 | 0 | 0 | 1892.4 | FALSE | FALSE
2026-06-17 | 2863755 | DS.2026.2426 121 Centre Place | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 5159.58 | 0 | 5159.58 | 0 | 0 | 3802.57 | 0 | 0 | -5159.58 | 0 | 5159.58 | 0 | 1357.01 | 0.263 | 100 | 0.0194 | 0 | 0 | 0 | 5159.58 | FALSE | FALSE
2026-06-17 | 2863752 | DS.2026.2425 14 Parks | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 5159.58 | 0 | 5159.58 | 0 | 0 | 3802.57 | 0 | 0 | -5159.58 | 0 | 5159.58 | 0 | 1357.01 | 0.263 | 100 | 0.0194 | 0 | 0 | 0 | 5159.58 | FALSE | FALSE
2026-06-17 | 2863728 | DS.2026.2424 10566 Coppergate | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 3628.78 | 0 | 3628.78 | 0 | 0 | 2212.54 | 0 | 0 | -3628.78 | 0 | 3628.78 | 0 | 1416.24 | 0.3903 | 100 | 0.0276 | 0 | 0 | 0 | 3628.78 | FALSE | FALSE
2026-06-17 | 2863715 | DS.2026.2423 10816 McPherson St | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 2440.48 | 0 | 2440.48 | 0 | 0 | 1410.6 | 0 | 0 | -2440.48 | 0 | 2440.48 | 0 | 1029.88 | 0.422 | 100 | 0.041 | 0 | 0 | 0 | 2440.48 | FALSE | FALSE
2026-06-17 | 2863703 | DS.2026.2422 10814 McPherson St | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 2440.48 | 0 | 2440.48 | 0 | 0 | 1410.6 | 0 | 0 | -2440.48 | 0 | 2440.48 | 0 | 1029.88 | 0.422 | 100 | 0.041 | 0 | 0 | 0 | 2440.48 | FALSE | FALSE
2026-06-17 | 2863678 | DS.2026.2421 Flores Ohio Job | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 8624.08 | 0 | 8624.08 | 0 | 0 | 6153 | 0 | 0 | -8624.08 | 0 | 8624.08 | 0 | 2471.08 | 0.2865 | 100 | 0.0116 | 0 | 0 | 0 | 8624.08 | FALSE | FALSE
2026-06-17 | 2852408 | DS.2026.2420 7508 Central Ave | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 4040.48 | 0 | 4040.48 | 0 | 0 | 2427.56 | 0 | 0 | -4040.48 | 0 | 4040.48 | 0 | 1612.92 | 0.3992 | 100 | 0.0247 | 0 | 0 | 0 | 4040.48 | FALSE | FALSE
2026-06-17 | 2852375 | DS.2026.2419 120 Centre Place | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 3804.32 | 0 | 3804.32 | 0 | 0 | 3804.32 | 0 | 0 | -3804.32 | 0 | 3804.32 | 0 | 0 | 0 | 100 | 0.0263 | 0 | 0 | 0 | 3804.32 | FALSE | FALSE
2026-06-17 | 2844284 | DS.2026.2418 118 Centre Place | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 5159.58 | 0 | 5159.58 | 0 | 0 | 3802.57 | 0 | 0 | -5159.58 | 0 | 5159.58 | 0 | 1357.01 | 0.263 | 100 | 0.0194 | 0 | 0 | 0 | 5159.58 | FALSE | FALSE
2026-06-17 | 2844272 | DS.2026.2417 117 Centre Place | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 3804.32 | 0 | 3804.32 | 0 | 0 | 2778.55 | 0 | 0 | -3804.32 | 0 | 3804.32 | 0 | 1025.77 | 0.2696 | 100 | 0.0263 | 0 | 0 | 0 | 3804.32 | FALSE | FALSE
2026-06-17 | 2844253 | DS.2026.2416 52 Centre Place | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 5159.58 | 0 | 5159.58 | 0 | 0 | 3802.57 | 0 | 0 | -5159.58 | 0 | 5159.58 | 0 | 1357.01 | 0.263 | 100 | 0.0194 | 0 | 0 | 0 | 5159.58 | FALSE | FALSE
2026-06-17 | 2844241 | DS.2026.2415 10826 McPherson St | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 2440.48 | 0 | 2440.48 | 0 | 0 | 1410.6 | 0 | 0 | -2440.48 | 0 | 2440.48 | 0 | 1029.88 | 0.422 | 100 | 0.041 | 0 | 0 | 0 | 2440.48 | FALSE | FALSE
2026-06-17 | 2844222 | DS.2026.2414 10824 McPherson St | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 2440.48 | 0 | 2440.48 | 0 | 0 | 1410.6 | 0 | 0 | -2440.48 | 0 | 2440.48 | 0 | 1029.88 | 0.422 | 100 | 0.041 | 0 | 0 | 0 | 2440.48 | FALSE | FALSE
2026-06-17 | 2834059 | DS.2026.2413 Precision Pickup 0501 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 1025.01 | 0 | 1025.01 | 0 | 0 | 735.21 | 0 | 0 | -1025.01 | 0 | 1025.01 | 0 | 289.8 | 0.2827 | 100 | 0.0976 | 0 | 0 | 0 | 1025.01 | FALSE | FALSE
2026-06-17 | 2834016 | DS.2026.2412 10732 Heaven Cove Way | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 9353.41 | 0 | 9353.41 | 0 | 0 | 6102.17 | 0 | 0 | -9353.41 | 0 | 9353.41 | 0 | 3251.24 | 0.3476 | 100 | 0.0107 | 0 | 0 | 0 | 9353.41 | FALSE | FALSE
2026-06-17 | 2818141 | DS.2026.2411 Clark Remodel | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 3518.56 | 0 | 3518.56 | 3764.86 | 0 | 2632.94 | 0 | 0 | -3518.56 | 0 | 3518.56 | 0 | 885.62 | 0.2517 | 100 | 0.0284 | 0 | 0 | 0 | -246.3 | FALSE | FALSE
2026-06-17 | 2803284 | 2026.1053 Lot 32 Vacant TI | TI | Spencer Anderson | Holladay Construction Group | ACTIVE | 126210 | 0 | 0 | 0 | 68244 | 24185.09 | 0.3544 | 44728.82 | 44728.82 | 44727.74 | 0 | 44728.82 | -24185.09 | 0 | 45.93 | 0.0004 | 0.4593 | -0.4589 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2796562 | DS.2026.2410 Courtyards of Russell Oaks 113 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 7088.8 | 0 | 7088.8 | 7585.02 | 0 | 5604.04 | 0 | 0 | -7088.8 | 0 | 7088.8 | 0 | 1484.76 | 0.2095 | 100 | 0.0141 | 0 | 0 | 0 | -496.22 | FALSE | FALSE
2026-06-17 | 2796526 | DS.2026.2409 Precision Pickup 0410 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 100.8 | 0 | 100.8 | 107.86 | 0 | 94.08 | 0 | 0 | -100.8 | 0 | 100.8 | 0 | 6.72 | 0.0667 | 100 | 0.9921 | 0 | 0 | 0 | -7.06 | FALSE | FALSE
2026-06-17 | 2782708 | DS.2026.2408 Courtyards of Westfield 107 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6501.79 | 0 | 6501.79 | 6956.92 | 0 | 4825.36 | 0 | 0 | -6501.79 | 0 | 6501.79 | 0 | 1676.43 | 0.2578 | 100 | 0.0154 | 0 | 0 | 0 | -455.13 | FALSE | FALSE
2026-06-17 | 2782668 | DS.2026.2407 Courtyards of Russel Oaks 126 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5540.58 | 0 | 5540.58 | 0 | 0 | 4142.66 | 0 | 0 | -5540.58 | 0 | 5540.58 | 0 | 1397.92 | 0.2523 | 100 | 0.018 | 0 | 0 | 0 | 5540.58 | FALSE | FALSE
2026-06-17 | 2763556 | DS.2026.2406 Premier Custom Homes Quote | UN | (Unassigned) | Premier Custom Homes | ACTIVE | 16133.4 | 0 | 16133.4 | 17262.74 | 0 | 13255.7 | 0 | 0 | -16133.4 | 0 | 16133.4 | 0 | 2877.7 | 0.1784 | 100 | 0.0062 | 0 | 0 | 0 | -1129.34 | FALSE | FALSE
2026-06-17 | 2762554 | DS.2026.2405 21569 Anchor Bay Drive | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 6573.38 | 0 | 6573.38 | 7033.52 | 0 | 4396.3 | 0 | 0 | -6573.38 | 0 | 6573.38 | 0 | 2177.08 | 0.3312 | 100 | 0.0152 | 0 | 0 | 0 | -460.14 | FALSE | FALSE
2026-06-17 | 2761732 | 2026.1051 Park 130 Building 8 | TI | Spencer Anderson | The Peterson Company, LLC | ACTIVE | 294700 | 0 | 0 | 0 | 165074.41 | 36401.41 | 0.2205 | 64981.35 | 64981.35 | 64985.82 | 0 | 64981.35 | -36401.41 | 0 | 43.99 | 0.0001 | 0.4399 | -0.4397 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2759560 | DS.2026.2404 Flores Sandhu Res | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 19488.46 | 0 | 19488.46 | 20852.65 | 0 | 14485.4 | 0 | 0 | -19488.46 | 0 | 19488.46 | 0 | 5003.06 | 0.2567 | 100 | 0.0051 | 0 | 0 | 0 | -1364.19 | FALSE | FALSE
2026-06-17 | 2750306 | DS.2026.2403 Big Dawg Pickup 0327 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 4955.6 | 0 | 4955.6 | 5302.49 | 0 | 3306.1 | 0 | 0 | -4955.6 | 0 | 4955.6 | 0 | 1649.5 | 0.3329 | 100 | 0.0202 | 0 | 0 | 0 | -346.89 | FALSE | FALSE
2026-06-17 | 2750278 | DS.2026.2402 Courtyards of Cielo Ranch 17 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 7053.88 | 224.64 | 7053.88 | 7547.65 | 0 | 5265.64 | 0 | 0 | -7053.88 | 0 | 7053.88 | 0 | 1788.24 | 0.2535 | 100 | 0.0142 | 0 | 0 | 0 | -493.77 | FALSE | FALSE
2026-06-17 | 2750126 | DS.2026.2401 Flores Kenneland | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 10704.98 | 0 | 10704.98 | 11454.33 | 0 | 7733.81 | 0 | 0 | -10704.98 | 0 | 10704.98 | 0 | 2971.17 | 0.2776 | 100 | 0.0093 | 0 | 0 | 0 | -749.35 | FALSE | FALSE
2026-06-17 | 2733362 | DS.2026.2400 Courtyards of Russell Oaks 115 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 7145.56 | 0 | 7145.56 | 7645.75 | 0 | 5280.52 | 0 | 0 | -7145.56 | 0 | 7145.56 | 0 | 1865.04 | 0.261 | 100 | 0.014 | 0 | 0 | 0 | -500.19 | FALSE | FALSE
2026-06-17 | 2733343 | DS.2026.2399 Courtyards of Russell Oaks 74 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5783.55 | 1486.44 | 5783.55 | 6156.42 | 0 | 4560.77 | 0 | 0 | -5783.55 | 0 | 5783.55 | 0 | 1222.78 | 0.2114 | 100 | 0.0173 | 0 | 0 | 0 | -372.87 | FALSE | FALSE
2026-06-17 | 2733326 | DS.2026.2398 Courtyards of Ceilo Ranch 26 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6800.59 | 0 | 6800.59 | 7276.63 | 0 | 4827.91 | 0 | 0 | -6800.59 | 0 | 6800.59 | 0 | 1972.68 | 0.2901 | 100 | 0.0147 | 0 | 0 | 0 | -476.04 | FALSE | FALSE
2026-06-17 | 2726249 | 2026.1047 Springdale Building 4 Demising Walls | TI | Tommy Cohoat | The Peterson Company, LLC | ACTIVE | 148800 | 0 | 148800 | 0 | 85100 | 70081.74 | 0.8235 | 122536.8 | -26263.2 | -26259.9 | 26263.2 | 0 | 78718.26 | 0.529 | 42.81 | 0.0003 | 0.4281 | -0.4278 | 0 | 148800 | TRUE | TRUE
2026-06-17 | 2726122 | DS.2026.2397 Courtyards of Cielo Ranch 26 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 336.96 | 0 | 336.96 | 360.55 | 0 | 233.28 | 0 | 0 | -336.96 | 0 | 336.96 | 0 | 103.68 | 0.3077 | 100 | 0.2968 | 0 | 0 | 0 | -23.59 | FALSE | FALSE
2026-06-17 | 2715709 | 2026.1046 Automatic Distributors (Park 130 Bldg 6) | TI | Cole Garriott | The Peterson Company, LLC | ACTIVE | 171900 | 0 | 154710 | 32697 | 105700 | 64219.57 | 0.6076 | 104446.44 | -50263.56 | -67459.66 | 50263.56 | 0 | 107680.43 | 0.6264 | 38.51 | 0.0002 | 0.3851 | -0.3849 | 17190 | 122013 | TRUE | TRUE
2026-06-17 | 2712233 | 2026.1045 First OnSite (Ameriplex) | TI | Spencer Anderson | Holladay Construction Group | ACTIVE | 128000 | 3000 | 128000 | 32940 | 74368.27 | 82331.75 | 1.1071 | 141708.8 | 13708.8 | 0 | 0 | 13708.8 | 45668.25 | 0.3568 | 41.9 | 0.0003 | 0.419 | -0.4187 | 0 | 95060 | TRUE | TRUE
2026-06-17 | 2703041 | DS.2026.2396 6252 West Turtle Hill Ct | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 5858.41 | 0 | 5858.41 | 6268.5 | 0 | 4720.53 | 0 | 0 | -5858.41 | 0 | 5858.41 | 0 | 1137.88 | 0.1942 | 100 | 0.0171 | 0 | 0 | 0 | -410.09 | FALSE | FALSE
2026-06-17 | 2702940 | DS.2026.2395 Courtyards of Westfield 103 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 252.72 | 0 | 252.72 | 270.41 | 0 | 174.96 | 0 | 0 | -252.72 | 0 | 252.72 | 0 | 77.76 | 0.3077 | 100 | 0.3957 | 0 | 0 | 0 | -17.69 | FALSE | FALSE
2026-06-17 | 2701256 | 2026.1043 Deer Creek Building 1 | TI | Tommy Cohoat | Patch Development | ACTIVE | 135000 | 0 | 135000 | 121500 | 59800 | 49599.2 | 0.8294 | 111969 | -23031 | -23028.56 | 23031 | 0 | 85400.8 | 0.6326 | 55.7 | 0.0004 | 0.557 | -0.5566 | 0 | 13500 | TRUE | TRUE
2026-06-17 | 2686749 | DS.2026.2394 5778 Marvie Drive | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 8024.34 | 0 | 8024.34 | 8586.04 | 0 | 5837.56 | 0 | 0 | -8024.34 | 0 | 8024.34 | 0 | 2186.78 | 0.2725 | 100 | 0.0125 | 0 | 0 | 0 | -561.7 | FALSE | FALSE
2026-06-17 | 2684477 | DS.2026.2393 Precision Pickup 0216 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 235.52 | 0 | 235.52 | 0 | 0 | 207.36 | 0 | 0 | -235.52 | 0 | 235.52 | 0 | 28.16 | 0.1196 | 100 | 0.4246 | 0 | 0 | 0 | 235.52 | FALSE | FALSE
2026-06-17 | 2681998 | 2026.1056 Senator Banks Office | TI | Dustin Hurt | BW Facility Management, LLC | ACTIVE | 47609 | 0 | 34444.01 | 0 | 29030 | 9068.32 | 0.3124 | 14873.05 | -19570.96 | -23399.14 | 19570.96 | 0 | 29202.8 | 0.7631 | 39.02 | 0.0008 | 0.3902 | -0.3894 | 3827.11 | 34444.01 | TRUE | TRUE
2026-06-17 | 2676832 | DS.2026.2392 3705 Holiday Farms Blvd - Precision | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 7844.42 | 0 | 7844.42 | 8393.53 | 0 | 5379.42 | 0 | 0 | -7844.42 | 0 | 7844.42 | 0 | 2465 | 0.3142 | 100 | 0.0127 | 0 | 0 | 0 | -549.11 | FALSE | FALSE
2026-06-17 | 2676780 | DS.2026.2391 0218 Jose Iracheta | UN | (Unassigned) | Kjt General Construction | ACTIVE | 1937.28 | 0 | 1937.28 | 0 | 0 | 1383.36 | 0 | 0 | -1937.28 | 0 | 1937.28 | 0 | 553.92 | 0.2859 | 100 | 0.0516 | 0 | 0 | 0 | 1937.28 | FALSE | FALSE
2026-06-17 | 2676758 | DS.2026.2390 510 W Pine St | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 2331.84 | 0 | 2331.84 | 2495.07 | 0 | 1538.64 | 0 | 0 | -2331.84 | 0 | 2331.84 | 0 | 793.2 | 0.3402 | 100 | 0.0429 | 0 | 0 | 0 | -163.23 | FALSE | FALSE
2026-06-17 | 2675379 | DS.2026.2389 Courtyards of Russell Oaks 145 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 8107.43 | 280 | 8107.43 | 8674.95 | 0 | 5651.42 | 0 | 0 | -8107.43 | 0 | 8107.43 | 0 | 2456.01 | 0.3029 | 100 | 0.0123 | 0 | 0 | 0 | -567.52 | FALSE | FALSE
2026-06-17 | 2675217 | DS.2026.2388 Courtyards of Cielo Ranch 13 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5878.68 | 0 | 5878.68 | 6290.19 | 0 | 4386.92 | 0 | 0 | -5878.68 | 0 | 5878.68 | 0 | 1491.76 | 0.2538 | 100 | 0.017 | 0 | 0 | 0 | -411.51 | FALSE | FALSE
2026-06-17 | 2665957 | DS.2026.2387 0204 Jose Irachetta | UN | (Unassigned) | Kjt General Construction | ACTIVE | 18783.05 | 0 | 18783.05 | 0 | 0 | 14081.61 | 0 | 0 | -18783.05 | 0 | 18783.05 | 0 | 4701.44 | 0.2503 | 100 | 0.0053 | 0 | 0 | 0 | 18783.05 | FALSE | FALSE
2026-06-17 | 2656341 | 2026.1041 Whiteland Building 2 - Blackhawk | TI | Spencer Anderson | Patch Development | ACTIVE | 187650 | 1500 | 156420.3 | 111888 | 89817.48 | 58964.07 | 0.6565 | 123192.23 | -33228.07 | -50610.41 | 33228.07 | 0 | 114836.26 | 0.6607 | 52.14 | 0.0003 | 0.5214 | -0.5211 | 17380.03 | 44532.3 | TRUE | TRUE
2026-06-17 | 2653588 | 2026.1040 Lakeside Books | TI | Trevor Anderson | The Peterson Company, LLC | ACTIVE | 10020 | 520 | 10020 | 0 | 5603.33 | 5603.33 | 1 | 10020 | 0 | 0 | 0 | 0 | 4416.67 | 0.4408 | 44.08 | 0.0044 | 0.4408 | -0.4364 | 0 | 10020 | TRUE | TRUE
2026-06-17 | 2653377 | DS.2026.2386 Courtyards of Russell Oaks 125 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5904.73 | 0 | 5904.73 | 6318.06 | 0 | 4667.22 | 0 | 0 | -5904.73 | 0 | 5904.73 | 0 | 1237.51 | 0.2096 | 100 | 0.0169 | 0 | 0 | 0 | -413.33 | FALSE | FALSE
2026-06-17 | 2653351 | DS.2026.2385 Courtyards of Russell Oaks 123 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6366.58 | 0 | 6366.58 | 6812.24 | 0 | 5053.67 | 0 | 0 | -6366.58 | 0 | 6366.58 | 0 | 1312.91 | 0.2062 | 100 | 0.0157 | 0 | 0 | 0 | -445.66 | FALSE | FALSE
2026-06-17 | 2653309 | DS.2026.2384 225 N St Ave | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 3992.46 | 0 | 3992.46 | 4271.93 | 0 | 2908.28 | 0 | 0 | -3992.46 | 0 | 3992.46 | 0 | 1084.18 | 0.2716 | 100 | 0.025 | 0 | 0 | 0 | -279.47 | FALSE | FALSE
2026-06-17 | 2652271 | 2026.1039 Upland Prospect Street | TI | Tommy Cohoat | Bischoff Construction, LLC | ACTIVE | 6500 | 0 | 6500 | 6500 | 6400 | 6355.54 | 0.9931 | 6455.15 | -44.85 | -45.15 | 44.85 | 0 | 144.46 | 0.0222 | 1.54 | 0.0002 | 0.0154 | -0.0151 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2645199 | DS.2026.2383 Courtyards of Cielo Ranch 37 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 7213.87 | 0 | 7213.87 | 7718.84 | 0 | 5333.35 | 0 | 0 | -7213.87 | 0 | 7213.87 | 0 | 1880.52 | 0.2607 | 100 | 0.0139 | 0 | 0 | 0 | -504.97 | FALSE | FALSE
2026-06-17 | 2645179 | DS.2026.2382 Cohoat House | DW | (Unassigned) | Mendoza | ACTIVE | 995.75 | 0 | 995.75 | 1065.45 | 0 | 703.81 | 0 | 0 | -995.75 | 0 | 995.75 | 0 | 291.94 | 0.2932 | 100 | 0.1004 | 0 | 0 | 0 | -69.7 | FALSE | FALSE
2026-06-17 | 2644918 | 2026.1037 CV - Castle Rock | TI | Ben Garza | Bischoff Construction, LLC | ACTIVE | 127451 | 40451 | 127451 | 125451 | 103762.97 | 103762.97 | 1 | 127451 | 0 | 0 | 0 | 0 | 23688.03 | 0.1859 | 18.59 | 0.0001 | 0.1859 | -0.1857 | 0 | 2000 | TRUE | TRUE
2026-06-17 | 2644454 | 2026.1036 Port Laredo Trade Center | TI | Ben Garza | ARCO Design/Build | ACTIVE | 108475 | 0 | 108475 | 0 | 63550.88 | 63550.88 | 1 | 108475 | 0 | 0 | 0 | 0 | 44924.12 | 0.4141 | 41.41 | 0.0004 | 0.4141 | -0.4138 | 0 | 108475 | TRUE | TRUE
2026-06-17 | 2640941 | DS.2026.2381 Hunt Addition | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 1497 | 0 | 1497 | 1601.79 | 0 | 1022.88 | 0 | 0 | -1497 | 0 | 1497 | 0 | 474.12 | 0.3167 | 100 | 0.0668 | 0 | 0 | 0 | -104.79 | FALSE | FALSE
2026-06-17 | 2637503 | DS.2026.2380 Mike Valentine 0129 | DW | (Unassigned) | Michael Valentine | ACTIVE | 11616.94 | 0 | 11616.94 | 0 | 0 | 7713.06 | 0 | 0 | -11616.94 | 0 | 11616.94 | 0 | 3903.88 | 0.3361 | 100 | 0.0086 | 0 | 0 | 0 | 11616.94 | FALSE | FALSE
2026-06-17 | 2637443 | DS.2026.2379 124 S A Street | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 2460.4 | 0 | 2460.4 | 2632.63 | 0 | 1651.4 | 0 | 0 | -2460.4 | 0 | 2460.4 | 0 | 809 | 0.3288 | 100 | 0.0406 | 0 | 0 | 0 | -172.23 | FALSE | FALSE
2026-06-17 | 2637384 | DS.2026.2378 Courtyards of Westfield 108 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 7137.73 | 0 | 7137.73 | 273.77 | 0 | 4325.35 | 0 | 0 | -7137.73 | 0 | 7137.73 | 0 | 2812.38 | 0.394 | 100 | 0.014 | 0 | 0 | 0 | 6863.96 | FALSE | FALSE
2026-06-17 | 2637358 | DS.2026.2377 Courtyards of Cielo Ranch 38 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 7078.51 | 0 | 7078.51 | 7574.01 | 0 | 4703.35 | 0 | 0 | -7078.51 | 0 | 7078.51 | 0 | 2375.16 | 0.3355 | 100 | 0.0141 | 0 | 0 | 0 | -495.5 | FALSE | FALSE
2026-06-17 | 2637329 | DS.2026.2376 5724 E Southport Rd | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 16934.23 | 0 | 16934.23 | 18119.63 | 0 | 12365.34 | 0 | 0 | -16934.23 | 0 | 16934.23 | 0 | 4568.89 | 0.2698 | 100 | 0.0059 | 0 | 0 | 0 | -1185.4 | FALSE | FALSE
2026-06-17 | 2637311 | DS.2026.2375 1802 Alabama St | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | 8479.96 | 0 | 8479.96 | 0 | 0 | 6545.15 | 0 | 0 | -8479.96 | 0 | 8479.96 | 0 | 1934.81 | 0.2282 | 100 | 0.0118 | 0 | 0 | 0 | 8479.96 | FALSE | FALSE
2026-06-17 | 2636260 | DS.2026.2374 Precision Pickup 0127 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 1076.05 | 0 | 1076.05 | 1151.37 | 0 | 718.08 | 0 | 0 | -1076.05 | 0 | 1076.05 | 0 | 357.97 | 0.3327 | 100 | 0.0929 | 0 | 0 | 0 | -75.32 | FALSE | FALSE
2026-06-17 | 2623919 | DS.2026.2373 Precision Pickup 0120 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 156.8 | 0 | 156.8 | 167.78 | 0 | 105.84 | 0 | 0 | -156.8 | 0 | 156.8 | 0 | 50.96 | 0.325 | 100 | 0.6378 | 0 | 0 | 0 | -10.98 | FALSE | FALSE
2026-06-17 | 2623903 | DS.2026.2372 Big Dawg Pickup 0115 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 3652.08 | 0 | 3652.08 | 3907.73 | 0 | 2032 | 0 | 0 | -3652.08 | 0 | 3652.08 | 0 | 1620.08 | 0.4436 | 100 | 0.0274 | 0 | 0 | 0 | -255.65 | FALSE | FALSE
2026-06-17 | 2623826 | DS.2026.2371 13429 E 116th St | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 6360.82 | 0 | 6360.82 | 6806.08 | 0 | 4575.9 | 0 | 0 | -6360.82 | 0 | 6360.82 | 0 | 1784.92 | 0.2806 | 100 | 0.0157 | 0 | 0 | 0 | -445.26 | FALSE | FALSE
2026-06-17 | 2623802 | DS.2026.2370 Courtyards of Westfield 106 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5580.89 | 0 | 5580.89 | 5971.55 | 0 | 3915.47 | 0 | 0 | -5580.89 | 0 | 5580.89 | 0 | 1665.42 | 0.2984 | 100 | 0.0179 | 0 | 0 | 0 | -390.66 | FALSE | FALSE
2026-06-17 | 2623780 | DS.2026.2369 Courtyards of Westfield 111 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 7078.51 | 0 | 7078.51 | 7574.01 | 0 | 4978.66 | 0 | 0 | -7078.51 | 0 | 7078.51 | 0 | 2099.85 | 0.2967 | 100 | 0.0141 | 0 | 0 | 0 | -495.5 | FALSE | FALSE
2026-06-17 | 2612889 | DS.2026.2368 Courtyards of Russell Oaks 60 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6769.86 | 0 | 6769.86 | 7243.75 | 0 | 4990.25 | 0 | 0 | -6769.86 | 0 | 6769.86 | 0 | 1779.61 | 0.2629 | 100 | 0.0148 | 0 | 0 | 0 | -473.89 | FALSE | FALSE
2026-06-17 | 2607541 | DS.2026.2367 Courtyards of Russell Oaks 126 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 336.96 | 0 | 336.96 | 360.55 | 0 | 233.28 | 0 | 0 | -336.96 | 0 | 336.96 | 0 | 103.68 | 0.3077 | 100 | 0.2968 | 0 | 0 | 0 | -23.59 | FALSE | FALSE
2026-06-17 | 2601418 | DS.2026.2366 Courtyards of Cielo Ranch 15 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5628.92 | 0 | 5628.92 | 6022.94 | 0 | 4200.66 | 0 | 0 | -5628.92 | 0 | 5628.92 | 0 | 1428.26 | 0.2537 | 100 | 0.0178 | 0 | 0 | 0 | -394.02 | FALSE | FALSE
2026-06-17 | 2594757 | DS.2026.2365 GSI Sackstedor Bloomington | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 10845.01 | 0 | 10845.01 | 0 | 0 | 7813.1 | 0 | 0 | -10845.01 | 0 | 10845.01 | 0 | 3031.91 | 0.2796 | 100 | 0.0092 | 0 | 0 | 0 | 10845.01 | FALSE | FALSE
2026-06-17 | 2594626 | DS.2026.2364 GSI 1-6 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 3516.46 | 0 | 3516.46 | 0 | 0 | 2314.78 | 0 | 0 | -3516.46 | 0 | 3516.46 | 0 | 1201.68 | 0.3417 | 100 | 0.0284 | 0 | 0 | 0 | 3516.46 | FALSE | FALSE
2026-06-17 | 2594581 | DS.2026.2363 Courtyards of Westfield 96 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 7196.75 | 0 | 7196.75 | 7700.52 | 0 | 5327.43 | 0 | 0 | -7196.75 | 0 | 7196.75 | 0 | 1869.32 | 0.2597 | 100 | 0.0139 | 0 | 0 | 0 | -503.77 | FALSE | FALSE
2026-06-17 | 2589539 | DS.2026.2362 Courtyards of Russel Oaks 127 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 280 | 0 | 280 | 299.6 | 0 | 255 | 0 | 0 | -280 | 0 | 280 | 0 | 25 | 0.0893 | 100 | 0.3571 | 0 | 0 | 0 | -19.6 | FALSE | FALSE
2026-06-17 | 2586526 | 2026.1033 Avon Demising Wall | TI | Ben Garza | The Peterson Company, LLC | ACTIVE | 181500 | -150700 | 181500 | 0 | 117712.76 | 117712.76 | 1 | 181500 | 0 | 0 | 0 | 0 | 63787.24 | 0.3514 | 35.14 | 0.0002 | 0.3514 | -0.3513 | 0 | 181500 | TRUE | TRUE
2026-06-17 | 2585536 | DS.2025.2361 Courtyards of Westfield 104 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6977.16 | 0 | 6977.16 | 7465.56 | 0 | 5142.81 | 0 | 0 | -6977.16 | 0 | 6977.16 | 0 | 1834.35 | 0.2629 | 100 | 0.0143 | 0 | 0 | 0 | -488.4 | FALSE | FALSE
2026-06-17 | 2584758 | DS.2025.2360 GSI Duplex Bloomington | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 3176.47 | 0 | 3176.47 | 0 | 0 | 2134.51 | 0 | 0 | -3176.47 | 0 | 3176.47 | 0 | 1041.96 | 0.328 | 100 | 0.0315 | 0 | 0 | 0 | 3176.47 | FALSE | FALSE
2026-06-17 | 2584752 | DS.2025.2359 Courtyards of Westfield 105 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6540.06 | 0 | 6540.06 | 6997.86 | 0 | 4832.67 | 0 | 0 | -6540.06 | 0 | 6540.06 | 0 | 1707.39 | 0.2611 | 100 | 0.0153 | 0 | 0 | 0 | -457.8 | FALSE | FALSE
2026-06-17 | 2584749 | DS.2025.2358 Courtyards of Cielo Ranch 7 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6662.19 | 0 | 6662.19 | 7128.54 | 0 | 4928.52 | 0 | 0 | -6662.19 | 0 | 6662.19 | 0 | 1733.67 | 0.2602 | 100 | 0.015 | 0 | 0 | 0 | -466.35 | FALSE | FALSE
2026-06-17 | 2584742 | DS.2025.2357 3704 South Whetstine Rd | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | 9710.18 | 0 | 9710.18 | 10389.89 | 0 | 7062.38 | 0 | 0 | -9710.18 | 0 | 9710.18 | 0 | 2647.8 | 0.2727 | 100 | 0.0103 | 0 | 0 | 0 | -679.71 | FALSE | FALSE
2026-06-17 | 2579439 | Priority Way Office | UN | (Unassigned) | MDG Real Estate LLC | ACTIVE | 413250 | 0 | 413250 | 413250 | 413250 | 401821.61 | 0.9723 | 401802.98 | -11447.02 | -11428.39 | 11447.02 | 0 | 11428.39 | 0.0277 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | FALSE
2026-06-17 | 2579268 | DS.2025.2356 Courtyards of Ceilo Ranch 127 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 8915.92 | 0 | 8915.92 | 9540.03 | 0 | 6509.72 | 0 | 0 | -8915.92 | 0 | 8915.92 | 0 | 2406.2 | 0.2699 | 100 | 0.0112 | 0 | 0 | 0 | -624.11 | FALSE | FALSE
2026-06-17 | 2579242 | DS.2025.2355 Courtyards of Ceilo Ranch 36 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6701.19 | 0 | 6701.19 | 7170.27 | 0 | 4968.22 | 0 | 0 | -6701.19 | 0 | 6701.19 | 0 | 1732.97 | 0.2586 | 100 | 0.0149 | 0 | 0 | 0 | -469.08 | FALSE | FALSE
2026-06-17 | 2575648 | DS.2025.2354 GSI Triplex | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 11279.53 | 0 | 11279.53 | 0 | 0 | 7717.81 | 0 | 0 | -11279.53 | 0 | 11279.53 | 0 | 3561.72 | 0.3158 | 100 | 0.0089 | 0 | 0 | 0 | 11279.53 | FALSE | FALSE
2026-06-17 | 2575437 | DS.2025.2353 Courtyards of Westfield 95 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 33.28 | 0 | 33.28 | 33.28 | 0 | 25.6 | 0 | 0 | -33.28 | 0 | 33.28 | 0 | 7.68 | 0.2308 | 100 | 3.0048 | 0 | 0 | 0 | 0 | FALSE | FALSE
2026-06-17 | 2569388 | DS.2025.2352 Charlstown Manor Lot 86 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 5697.42 | 0 | 5697.42 | 6096.24 | 0 | 3957.26 | 0 | 0 | -5697.42 | 0 | 5697.42 | 0 | 1740.16 | 0.3054 | 100 | 0.0176 | 0 | 0 | 0 | -398.82 | FALSE | FALSE
2026-06-17 | 2569308 | DS.2025.2351 Courtyards of Cielo Ranch 1 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6786.18 | 0 | 6786.18 | 7261.21 | 0 | 4998.63 | 0 | 0 | -6786.18 | 0 | 6786.18 | 0 | 1787.55 | 0.2634 | 100 | 0.0147 | 0 | 0 | 0 | -475.03 | FALSE | FALSE
2026-06-17 | 2563362 | DS.2025.2350 Courtyards of Westfield 95 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 7163.47 | 0 | 7163.47 | 7664.91 | 0 | 5346.88 | 0 | 0 | -7163.47 | 0 | 7163.47 | 0 | 1816.59 | 0.2536 | 100 | 0.014 | 0 | 0 | 0 | -501.44 | FALSE | FALSE
2026-06-17 | 2563168 | DS.2025.2349 208 N Washington Street | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | 7722.9 | 0 | 7722.9 | 8263.31 | 0 | 5619.97 | 0 | 0 | -7722.9 | 0 | 7722.9 | 0 | 2102.93 | 0.2723 | 100 | 0.0129 | 0 | 0 | 0 | -540.41 | FALSE | FALSE
2026-06-17 | 2560326 | DS.2025.2348 133 First Ave NE | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 6893.5 | 0 | 6893.5 | 7376.05 | 0 | 4819.38 | 0 | 0 | -6893.5 | 0 | 6893.5 | 0 | 2074.12 | 0.3009 | 100 | 0.0145 | 0 | 0 | 0 | -482.55 | FALSE | FALSE
2026-06-17 | 2560223 | DS.2025.2347 807 Spruce St | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | 8379.79 | 355.2 | 8379.79 | 0 | 0 | 6308.25 | 0 | 0 | -8379.79 | 0 | 8379.79 | 0 | 2071.54 | 0.2472 | 100 | 0.0119 | 0 | 0 | 0 | 8379.79 | FALSE | FALSE
2026-06-17 | 2552755 | DS.2025.2346 Jeff West House | DW | (Unassigned) | Jeff West Homes | ACTIVE | 8045.14 | 0 | 8045.14 | 8608.3 | 0 | 6453.13 | 0 | 0 | -8045.14 | 0 | 8045.14 | 0 | 1592.01 | 0.1979 | 100 | 0.0124 | 0 | 0 | 0 | -563.16 | FALSE | FALSE
2026-06-17 | 2552722 | DS.2025.2345 S & W Homes | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 4988.51 | 0 | 4988.51 | 0 | 0 | 3399.75 | 0 | 0 | -4988.51 | 0 | 4988.51 | 0 | 1588.76 | 0.3185 | 100 | 0.02 | 0 | 0 | 0 | 4988.51 | FALSE | FALSE
2026-06-17 | 2552670 | DS.2025.2344 Courtyards of Russel Okas 119 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5555.63 | 0 | 5555.63 | 5944.52 | 0 | 4147.85 | 0 | 0 | -5555.63 | 0 | 5555.63 | 0 | 1407.78 | 0.2534 | 100 | 0.018 | 0 | 0 | 0 | -388.89 | FALSE | FALSE
2026-06-17 | 2552143 | DS.2025.2343 Big Dawg Pickup 12-4 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 4292.44 | 0 | 4292.44 | 4592.91 | 0 | 2804.45 | 0 | 0 | -4292.44 | 0 | 4292.44 | 0 | 1487.99 | 0.3467 | 100 | 0.0233 | 0 | 0 | 0 | -300.47 | FALSE | FALSE
2026-06-17 | 2548777 | DS.2025.2342 Courtyards of Westfield 116 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6540.47 | 1132.8 | 6540.47 | 6919.01 | 0 | 5106.67 | 0 | 0 | -6540.47 | 0 | 6540.47 | 0 | 1433.8 | 0.2192 | 100 | 0.0153 | 0 | 0 | 0 | -378.54 | FALSE | FALSE
2026-06-17 | 2548714 | DS.2025.2341 8677 Bash St | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 12082.18 | 0 | 12082.18 | 12927.93 | 0 | 8742.58 | 0 | 0 | -12082.18 | 0 | 12082.18 | 0 | 3339.6 | 0.2764 | 100 | 0.0083 | 0 | 0 | 0 | -845.75 | FALSE | FALSE
2026-06-17 | 2545375 | DS.2025.2340 1573 Chatham Drive | DW | (Unassigned) | Iracheta Drywall | ACTIVE | 16402.7 | 0 | 16402.7 | 17550.89 | 0 | 11895.1 | 0 | 0 | -16402.7 | 0 | 16402.7 | 0 | 4507.6 | 0.2748 | 100 | 0.0061 | 0 | 0 | 0 | -1148.19 | FALSE | FALSE
2026-06-17 | 2545100 | 2025.1028 Northpoint | TI | Trevor Anderson | Patch Development | ACTIVE | 243696 | 130220 | 17415 | 17415 | 141629.82 | 69626.83 | 0.4916 | 119800.95 | 102385.95 | 100453.72 | 0 | 102385.95 | -50276.83 | -1 | 41.88 | 0.0002 | 0.4188 | -0.4187 | 1935 | 0 | TRUE | TRUE
2026-06-17 | 2541102 | MF.2026.1044 Everstead Apartments | MF | Ben Garza | Grand Contracting | ACTIVE | 4391740 | 0 | 0 | 0 | 3051250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.52 | 0 | 0.3052 | -0.3052 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2541097 | 2025.1026 HNTB Buildout (Salesforce Tower) | TI | Ben Garza | Skender Construction of Indiana LLC | ACTIVE | 476552.38 | 39052.38 | 449069.6 | 123103.62 | 411573.38 | 411177.02 | 0.999 | 476075.83 | 27006.23 | 27023.84 | 0 | 27006.23 | 37892.58 | 0.0844 | 13.64 | 0 | 0.1364 | -0.1363 | 0 | 325965.98 | TRUE | TRUE
2026-06-17 | 2541065 | 2026.1034 Stella's Ice Cream Shop | TI | Shawn Welcher | The ACTS Collaborative, LLC | ACTIVE | 69155 | 3655 | 62239.5 | 34110 | 36976.57 | 27001.17 | 0.7302 | 50496.98 | -11742.52 | -18656.38 | 11742.52 | 0 | 42153.83 | 0.6096 | 46.53 | 0.0007 | 0.4653 | -0.4646 | 6915.5 | 28129.5 | TRUE | TRUE
2026-06-17 | 2540055 | DS.2025.2339 1952 N Central Ave | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | 4609.73 | 630 | 4609.73 | 0 | 0 | 3564.44 | 0 | 0 | -4609.73 | 0 | 4609.73 | 0 | 1045.29 | 0.2268 | 100 | 0.0217 | 0 | 0 | 0 | 4609.73 | FALSE | FALSE
2026-06-17 | 2538950 | DS.2025.2338 7655 W Julia Drive | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 4904.49 | 0 | 4904.49 | 0 | 0 | 3377.83 | 0 | 0 | -4904.49 | 0 | 4904.49 | 0 | 1526.66 | 0.3113 | 100 | 0.0204 | 0 | 0 | 0 | 4904.49 | FALSE | FALSE
2026-06-17 | 2538818 | DS.2025.2337 Courtyards of Cielo Ranch 7 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 336.96 | 0 | 336.96 | 360.55 | 0 | 233.28 | 0 | 0 | -336.96 | 0 | 336.96 | 0 | 103.68 | 0.3077 | 100 | 0.2968 | 0 | 0 | 0 | -23.59 | FALSE | FALSE
2026-06-17 | 2538718 | DS.2025.2336 Courtyards of Cielo Ranch 24 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5961.9 | 0 | 5961.9 | 6379.23 | 0 | 4451.18 | 0 | 0 | -5961.9 | 0 | 5961.9 | 0 | 1510.72 | 0.2534 | 100 | 0.0168 | 0 | 0 | 0 | -417.33 | FALSE | FALSE
2026-06-17 | 2538410 | DS.2025.2335 Courtyards of Cielo Ranch 23 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 4716.44 | 0 | 4716.44 | 5046.59 | 0 | 3538.96 | 0 | 0 | -4716.44 | 0 | 4716.44 | 0 | 1177.48 | 0.2497 | 100 | 0.0212 | 0 | 0 | 0 | -330.15 | FALSE | FALSE
2026-06-17 | 2536742 | DS.2025.2334 Courtyards of Russell Oaks 61 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6990.74 | 224 | 6990.74 | 7464.41 | 0 | 5192.09 | 0 | 0 | -6990.74 | 0 | 6990.74 | 0 | 1798.65 | 0.2573 | 100 | 0.0143 | 0 | 0 | 0 | -473.67 | FALSE | FALSE
2026-06-17 | 2532793 | DS.2025.2333 7814 E Old US 50 | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | 4391.29 | 0 | 4391.29 | 4698.68 | 0 | 3227.84 | 0 | 0 | -4391.29 | 0 | 4391.29 | 0 | 1163.45 | 0.2649 | 100 | 0.0228 | 0 | 0 | 0 | -307.39 | FALSE | FALSE
2026-06-17 | 2532772 | DS.2025.2332 Courtyards of Westfield 109 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5407.67 | 0 | 5407.67 | 5786.21 | 0 | 4321.39 | 0 | 0 | -5407.67 | 0 | 5407.67 | 0 | 1086.28 | 0.2009 | 100 | 0.0185 | 0 | 0 | 0 | -378.54 | FALSE | FALSE
2026-06-17 | 2532740 | DS.2025.2331 Courtyards of Russell Oaks 65 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6766.74 | 0 | 6766.74 | 7240.41 | 0 | 4988.09 | 0 | 0 | -6766.74 | 0 | 6766.74 | 0 | 1778.65 | 0.2629 | 100 | 0.0148 | 0 | 0 | 0 | -473.67 | FALSE | FALSE
2026-06-17 | 2532662 | DS.2025.2330 GSI Stonecrest 11-18 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 4588.23 | 0 | 4588.23 | 4909.41 | 0 | 3224.08 | 0 | 0 | -4588.23 | 0 | 4588.23 | 0 | 1364.15 | 0.2973 | 100 | 0.0218 | 0 | 0 | 0 | -321.18 | FALSE | FALSE
2026-06-17 | 2528354 | DS.2025.2329 Courtyards of Westfield Lot 90 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5372.94 | 0 | 5372.94 | 5749.05 | 0 | 4023.41 | 0 | 0 | -5372.94 | 0 | 5372.94 | 0 | 1349.53 | 0.2512 | 100 | 0.0186 | 0 | 0 | 0 | -376.11 | FALSE | FALSE
2026-06-17 | 2526957 | 2026.1042 SND2 at ILP Bldg IV Whitestown | TI | Trevor Anderson | Compass Commercial Construction Group | ACTIVE | 443007.26 | -11303.74 | 356727.34 | 164669.04 | 267180.2 | 144645.31 | 0.5414 | 239844.13 | -116883.21 | -156529.61 | 116883.21 | 0 | 251718.4 | 0.6351 | 39.69 | 0.0001 | 0.3969 | -0.3968 | 39636.37 | 192058.3 | TRUE | TRUE
2026-06-17 | 2523333 | DS.2025.2328 Walnut Townhouses | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 27480.05 | 0 | 27480.05 | 29403.65 | 0 | 20232.69 | 0 | 0 | -27480.05 | 0 | 27480.05 | 0 | 7247.36 | 0.2637 | 100 | 0.0036 | 0 | 0 | 0 | -1923.6 | FALSE | FALSE
2026-06-17 | 2522921 | DS.2025.2327 Courtyards of Cielo Ranch 12 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5339.63 | 0 | 5339.63 | 5713.4 | 0 | 3961.95 | 0 | 0 | -5339.63 | 0 | 5339.63 | 0 | 1377.68 | 0.258 | 100 | 0.0187 | 0 | 0 | 0 | -373.77 | FALSE | FALSE
2026-06-17 | 2521531 | DS.2025.2326 Courtyards of Russell Oaks 64 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6766.74 | 0 | 6766.74 | 7240.41 | 0 | 4988.09 | 0 | 0 | -6766.74 | 0 | 6766.74 | 0 | 1778.65 | 0.2629 | 100 | 0.0148 | 0 | 0 | 0 | -473.67 | FALSE | FALSE
2026-06-17 | 2520350 | 2025.1024 Metro Lion | TI | Ben Garza | DEEM, LLC | ACTIVE | 786710 | 111490 | 786710 | 785410 | 575332.91 | 575332.91 | 1 | 786710 | 0 | 0 | 0 | 0 | 211377.09 | 0.2687 | 26.87 | 0 | 0.2687 | -0.2687 | 0 | 1300 | TRUE | TRUE
2026-06-17 | 2519527 | DS.2025.2325 6693 E 500 N | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | 3424.59 | 0 | 3424.59 | 3664.31 | 0 | 2352.39 | 0 | 0 | -3424.59 | 0 | 3424.59 | 0 | 1072.2 | 0.3131 | 100 | 0.0292 | 0 | 0 | 0 | -239.72 | FALSE | FALSE
2026-06-17 | 2519463 | DS.2025.2324 6504 N 1200 E | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | 2200.1 | 0 | 2200.1 | 2354.11 | 0 | 1496.64 | 0 | 0 | -2200.1 | 0 | 2200.1 | 0 | 703.46 | 0.3197 | 100 | 0.0455 | 0 | 0 | 0 | -154.01 | FALSE | FALSE
2026-06-17 | 2519426 | DS.2025.2323 11890 E 800 N | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | 1561.15 | 0 | 1561.15 | 998.21 | 0 | 1010.41 | 0 | 0 | -1561.15 | 0 | 1561.15 | 0 | 550.74 | 0.3528 | 100 | 0.0641 | 0 | 0 | 0 | 562.94 | FALSE | FALSE
2026-06-17 | 2517615 | DS.2025.2322 Courtyards of Russell Oaks 124 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5546.04 | 0 | 5546.04 | 5934.26 | 0 | 3962.25 | 0 | 0 | -5546.04 | 0 | 5546.04 | 0 | 1583.79 | 0.2856 | 100 | 0.018 | 0 | 0 | 0 | -388.22 | FALSE | FALSE
2026-06-17 | 2517594 | DS.2025.2321 Courtyards of Cielo Ranch 33 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6549.45 | 0 | 6549.45 | 7007.91 | 0 | 4836.92 | 0 | 0 | -6549.45 | 0 | 6549.45 | 0 | 1712.53 | 0.2615 | 100 | 0.0153 | 0 | 0 | 0 | -458.46 | FALSE | FALSE
2026-06-17 | 2517552 | DS.2025.2320 Courtyards of Cielo Ranch 27 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6589.59 | 252 | 6589.59 | 7050.86 | 0 | 4915.76 | 0 | 0 | -6589.59 | 0 | 6589.59 | 0 | 1673.83 | 0.254 | 100 | 0.0152 | 0 | 0 | 0 | -461.27 | FALSE | FALSE
2026-06-17 | 2510293 | DS.2025.2319 5288 Oak Grove Rd | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | 8606.94 | 0 | 8606.94 | 9209.43 | 0 | 6023.23 | 0 | 0 | -8606.94 | 0 | 8606.94 | 0 | 2583.71 | 0.3002 | 100 | 0.0116 | 0 | 0 | 0 | -602.49 | FALSE | FALSE
2026-06-17 | 2508315 | DS.2025.2318 GSI Stonecrest 11-4 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 4381.98 | 0 | 4381.98 | 4688.72 | 0 | 3055.63 | 0 | 0 | -4381.98 | 0 | 4381.98 | 0 | 1326.35 | 0.3027 | 100 | 0.0228 | 0 | 0 | 0 | -306.74 | FALSE | FALSE
2026-06-17 | 2508262 | DS.2025.2317 Courtyards of Ceilo Ranch 23 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 336.96 | 0 | 336.96 | 360.55 | 0 | 233.28 | 0 | 0 | -336.96 | 0 | 336.96 | 0 | 103.68 | 0.3077 | 100 | 0.2968 | 0 | 0 | 0 | -23.59 | FALSE | FALSE
2026-06-17 | 2505636 | 2025.1023 Vikan Products BTS | TI | Cole Garriott | The Peterson Company, LLC | ACTIVE | 734790 | 39976 | 661310.99 | 368042.84 | 412832.53 | 347251.25 | 0.8411 | 618031.87 | -43279.12 | -116726.43 | 43279.12 | 0 | 387538.75 | 0.5274 | 43.82 | 0.0001 | 0.4382 | -0.4381 | 73479.01 | 293268.15 | TRUE | TRUE
2026-06-17 | 2500441 | DS.2025.2316 Courtyards of Cielo Ranch 8 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 7137.76 | 0 | 7137.76 | 7637.4 | 0 | 5341.14 | 0 | 0 | -7137.76 | 0 | 7137.76 | 0 | 1796.62 | 0.2517 | 100 | 0.014 | 0 | 0 | 0 | -499.64 | FALSE | FALSE
2026-06-17 | 2499386 | DS.2025.2315 GSI Brookville | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 10698.76 | 0 | 10698.76 | 0 | 0 | 7430.01 | 0 | 0 | -10698.76 | 0 | 10698.76 | 0 | 3268.75 | 0.3055 | 100 | 0.0093 | 0 | 0 | 0 | 10698.76 | FALSE | FALSE
2026-06-17 | 2498252 | DS.2025.2314 R18 Holiday Farms | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 16234.41 | 0 | 16234.41 | 17370.82 | 0 | 11943.43 | 0 | 0 | -16234.41 | 0 | 16234.41 | 0 | 4290.98 | 0.2643 | 100 | 0.0062 | 0 | 0 | 0 | -1136.41 | FALSE | FALSE
2026-06-17 | 2498183 | DS.2025.2313 McDowell Residence | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 5783.87 | 0 | 5783.87 | 6188.74 | 0 | 4868.36 | 0 | 0 | -5783.87 | 0 | 5783.87 | 0 | 915.51 | 0.1583 | 100 | 0.0173 | 0 | 0 | 0 | -404.87 | FALSE | FALSE
2026-06-17 | 2498101 | DS.2025.2312 Plantation Drive Flores | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 5430.42 | 0 | 5430.42 | 5810.55 | 0 | 4117.07 | 0 | 0 | -5430.42 | 0 | 5430.42 | 0 | 1313.35 | 0.2419 | 100 | 0.0184 | 0 | 0 | 0 | -380.13 | FALSE | FALSE
2026-06-17 | 2498026 | DS.2025.2311 15111 Mooring Cir W | DW | (Unassigned) | Mendoza | ACTIVE | 398.4 | 0 | 398.4 | 426.29 | 0 | 281.2 | 0 | 0 | -398.4 | 0 | 398.4 | 0 | 117.2 | 0.2942 | 100 | 0.251 | 0 | 0 | 0 | -27.89 | FALSE | FALSE
2026-06-17 | 2497952 | DS.2025.2310 Courtyards of Cielo Ranch 12 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 388.8 | 0 | 388.8 | 416.02 | 0 | 267.84 | 0 | 0 | -388.8 | 0 | 388.8 | 0 | 120.96 | 0.3111 | 100 | 0.2572 | 0 | 0 | 0 | -27.22 | FALSE | FALSE
2026-06-17 | 2491974 | DS.2025.2309 6936 Sun River Drive | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 8722.82 | 0 | 8722.82 | 9333.42 | 0 | 6505.71 | 0 | 0 | -8722.82 | 0 | 8722.82 | 0 | 2217.11 | 0.2542 | 100 | 0.0115 | 0 | 0 | 0 | -610.6 | FALSE | FALSE
2026-06-17 | 2491878 | DS.2025.2308 Courtyards of Westfield 112 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 7135.51 | 0 | 7135.51 | 7635 | 0 | 5703.2 | 0 | 0 | -7135.51 | 0 | 7135.51 | 0 | 1432.31 | 0.2007 | 100 | 0.014 | 0 | 0 | 0 | -499.49 | FALSE | FALSE
2026-06-17 | 2491611 | DS.2025.2307 Mendoza Drywall company-15535 Stony Creek Way | DW | (Unassigned) | Mendoza | ACTIVE | 806.4 | 0 | 806.4 | 862.85 | 0 | 595.2 | 0 | 0 | -806.4 | 0 | 806.4 | 0 | 211.2 | 0.2619 | 100 | 0.124 | 0 | 0 | 0 | -56.45 | FALSE | FALSE
2026-06-17 | 2488150 | DS.2025.2306 Courtyards of Russell Oaks 118 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 4997.24 | 0 | 4997.24 | 5347.05 | 0 | 3994.7 | 0 | 0 | -4997.24 | 0 | 4997.24 | 0 | 1002.54 | 0.2006 | 100 | 0.02 | 0 | 0 | 0 | -349.81 | FALSE | FALSE
2026-06-17 | 2488125 | DS.2025.2305 Courtyards of Russell Oaks 62 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6963.91 | 0 | 6963.91 | 7451.38 | 0 | 5504.18 | 0 | 0 | -6963.91 | 0 | 6963.91 | 0 | 1459.73 | 0.2096 | 100 | 0.0144 | 0 | 0 | 0 | -487.47 | FALSE | FALSE
2026-06-17 | 2488086 | DS.2025.2304 Charlstown Manor 10-22 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 8911.68 | 0 | 8911.68 | 9535.5 | 0 | 6703.02 | 0 | 0 | -8911.68 | 0 | 8911.68 | 0 | 2208.66 | 0.2478 | 100 | 0.0112 | 0 | 0 | 0 | -623.82 | FALSE | FALSE
2026-06-17 | 2481041 | DS.2025.2303 Big Dawg Pickup 10-17 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 1709.9 | 0 | 1709.9 | 1829.59 | 0 | 1342.85 | 0 | 0 | -1709.9 | 0 | 1709.9 | 0 | 367.05 | 0.2147 | 100 | 0.0585 | 0 | 0 | 0 | -119.69 | FALSE | FALSE
2026-06-17 | 2480320 | DS.2025.2302 14 E South St | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 2309.51 | 0 | 2309.51 | 2471.18 | 0 | 1804.75 | 0 | 0 | -2309.51 | 0 | 2309.51 | 0 | 504.76 | 0.2186 | 100 | 0.0433 | 0 | 0 | 0 | -161.67 | FALSE | FALSE
2026-06-17 | 2480064 | DS.2025.2301 Courtyards of Cielo Ranch 39 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6072.33 | 0 | 6072.33 | 6497.39 | 0 | 4863.05 | 0 | 0 | -6072.33 | 0 | 6072.33 | 0 | 1209.28 | 0.1991 | 100 | 0.0165 | 0 | 0 | 0 | -425.06 | FALSE | FALSE
2026-06-17 | 2479977 | DS.2025.2300 Courtyards of Cielo Ranch 10 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6856.72 | 0 | 6856.72 | 7336.69 | 0 | 5424.54 | 0 | 0 | -6856.72 | 0 | 6856.72 | 0 | 1432.18 | 0.2089 | 100 | 0.0146 | 0 | 0 | 0 | -479.97 | FALSE | FALSE
2026-06-17 | 2475602 | DS.2025.2299 4435 Strathmore Lane | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 7225.49 | 0 | 7225.49 | 7731.27 | 0 | 5282.34 | 0 | 0 | -7225.49 | 0 | 7225.49 | 0 | 1943.15 | 0.2689 | 100 | 0.0138 | 0 | 0 | 0 | -505.78 | FALSE | FALSE
2026-06-17 | 2475493 | DS.2025.2298 GSI Bloomington | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 4863.39 | 0 | 4863.39 | 5203.83 | 0 | 3703.67 | 0 | 0 | -4863.39 | 0 | 4863.39 | 0 | 1159.72 | 0.2385 | 100 | 0.0206 | 0 | 0 | 0 | -340.44 | FALSE | FALSE
2026-06-17 | 2475432 | DS.2025.2297 Courtyards of Cielo Ranch 28 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6856.72 | 0 | 6856.72 | 7336.69 | 0 | 5424.54 | 0 | 0 | -6856.72 | 0 | 6856.72 | 0 | 1432.18 | 0.2089 | 100 | 0.0146 | 0 | 0 | 0 | -479.97 | FALSE | FALSE
2026-06-17 | 2472092 | 2025.1031 Pita Way | TI | Spencer Anderson | Kort Builders, Inc | ACTIVE | 9745 | 2745 | 9745 | 9745 | 3664.37 | 3301.8 | 0.9011 | 8781.22 | -963.78 | -964.22 | 963.78 | 0 | 6443.2 | 0.6612 | 62.4 | 0.0064 | 0.624 | -0.6176 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2469780 | DS.2025.2296 4380 Strathmore Lane | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 9268.08 | 0 | 9268.08 | 10216.85 | 0 | 5329.28 | 0 | 0 | -9268.08 | 0 | 9268.08 | 0 | 3938.8 | 0.425 | 100 | 0.0108 | 0 | 0 | 0 | -948.77 | FALSE | FALSE
2026-06-17 | 2469724 | DS.2025.2295 Courtyards of Cielo Ranch 35 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5327.87 | 0 | 5327.87 | 5700.82 | 0 | 4254.91 | 0 | 0 | -5327.87 | 0 | 5327.87 | 0 | 1072.96 | 0.2014 | 100 | 0.0188 | 0 | 0 | 0 | -372.95 | FALSE | FALSE
2026-06-17 | 2469631 | DS.2025.2294 Courtyards of Cielo Ranch 9 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5327.87 | 0 | 5327.87 | 5700.82 | 0 | 4254.91 | 0 | 0 | -5327.87 | 0 | 5327.87 | 0 | 1072.96 | 0.2014 | 100 | 0.0188 | 0 | 0 | 0 | -372.95 | FALSE | FALSE
2026-06-17 | 2468636 | DS.2025.2293 1248 Chatham Ridge Court | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | 1007.06 | 0 | 1007.06 | 1077.55 | 0 | 816.8 | 0 | 0 | -1007.06 | 0 | 1007.06 | 0 | 190.26 | 0.1889 | 100 | 0.0993 | 0 | 0 | 0 | -70.49 | FALSE | FALSE
2026-06-17 | 2468607 | DS.2025.2292 Courtyards of Russell Oaks 121 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5357.27 | 507.6 | 5357.27 | 5732.28 | 0 | 4292.77 | 0 | 0 | -5357.27 | 0 | 5357.27 | 0 | 1064.5 | 0.1987 | 100 | 0.0187 | 0 | 0 | 0 | -375.01 | FALSE | FALSE
2026-06-17 | 2468570 | DS.2025.2291 Courtyards of Russell Oaks 63 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6794.73 | 0 | 6794.73 | 7270.36 | 0 | 5376.04 | 0 | 0 | -6794.73 | 0 | 6794.73 | 0 | 1418.69 | 0.2088 | 100 | 0.0147 | 0 | 0 | 0 | -475.63 | FALSE | FALSE
2026-06-17 | 2468525 | DS.2025.2290 Walnut Town Homes | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 4911.52 | 0 | 4911.52 | 5255.33 | 0 | 4231.46 | 0 | 0 | -4911.52 | 0 | 4911.52 | 0 | 680.06 | 0.1385 | 100 | 0.0204 | 0 | 0 | 0 | -343.81 | FALSE | FALSE
2026-06-17 | 2468496 | DS.2025.2289 Courtyards of Westfield 118 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6689.88 | 0 | 6689.88 | 7158.17 | 0 | 5278.62 | 0 | 0 | -6689.88 | 0 | 6689.88 | 0 | 1411.26 | 0.211 | 100 | 0.0149 | 0 | 0 | 0 | -468.29 | FALSE | FALSE
2026-06-17 | 2463881 | DS.2025.2288 Courtyards of Russell Oaks 120 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 7550.89 | 0 | 7550.89 | 8079.45 | 0 | 5977.12 | 0 | 0 | -7550.89 | 0 | 7550.89 | 0 | 1573.77 | 0.2084 | 100 | 0.0132 | 0 | 0 | 0 | -528.56 | FALSE | FALSE
2026-06-17 | 2459666 | DS.2025.2286 Courtyards of Westfield 117 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5628.92 | 0 | 5628.92 | 6022.94 | 0 | 4174.16 | 0 | 0 | -5628.92 | 0 | 5628.92 | 0 | 1454.76 | 0.2584 | 100 | 0.0178 | 0 | 0 | 0 | -394.02 | FALSE | FALSE
2026-06-17 | 2453104 | DS.2025.2285 GSI - Rushville 5 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 4186.2 | 0 | 4186.2 | 4479.23 | 0 | 2991.68 | 0 | 0 | -4186.2 | 0 | 4186.2 | 0 | 1194.52 | 0.2853 | 100 | 0.0239 | 0 | 0 | 0 | -293.03 | FALSE | FALSE
2026-06-17 | 2452961 | DS.2025.2284 Courtyards of Russell Oaks 59 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5780.19 | 0 | 5780.19 | 6184.8 | 0 | 4302.74 | 0 | 0 | -5780.19 | 0 | 5780.19 | 0 | 1477.45 | 0.2556 | 100 | 0.0173 | 0 | 0 | 0 | -404.61 | FALSE | FALSE
2026-06-17 | 2446907 | DS.2025.2281 Courtyards of Russell Oaks 117 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5285.62 | 0 | 5285.62 | 5655.61 | 0 | 3959.29 | 0 | 0 | -5285.62 | 0 | 5285.62 | 0 | 1326.33 | 0.2509 | 100 | 0.0189 | 0 | 0 | 0 | -369.99 | FALSE | FALSE
2026-06-17 | 2446248 | DS.2025.2280 GSI - E Crestwine Dr | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 9105.65 | 0 | 9105.65 | 9743.05 | 0 | 6483 | 0 | 0 | -9105.65 | 0 | 9105.65 | 0 | 2622.65 | 0.288 | 100 | 0.011 | 0 | 0 | 0 | -637.4 | FALSE | FALSE
2026-06-17 | 2444852 | DS.2025.2279 8810 Bergeson Drive | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | 784.91 | 0 | 784.91 | 839.85 | 0 | 567.3 | 0 | 0 | -784.91 | 0 | 784.91 | 0 | 217.61 | 0.2772 | 100 | 0.1274 | 0 | 0 | 0 | -54.94 | FALSE | FALSE
2026-06-17 | 2444545 | DS.2025.2278 Courtyards of Russell Oaks 52 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 7142.71 | 0 | 7142.71 | 7642.7 | 0 | 5271.78 | 0 | 0 | -7142.71 | 0 | 7142.71 | 0 | 1870.93 | 0.2619 | 100 | 0.014 | 0 | 0 | 0 | -499.99 | FALSE | FALSE
2026-06-17 | 2441368 | DS.2025.2275 Courtyards of Cielo Ranch 9 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 505.44 | 0 | 505.44 | 540.82 | 0 | 349.92 | 0 | 0 | -505.44 | 0 | 505.44 | 0 | 155.52 | 0.3077 | 100 | 0.1978 | 0 | 0 | 0 | -35.38 | FALSE | FALSE
2026-06-17 | 2439356 | DS.2025.2274 Barndo 2 Frankfort | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 2325.89 | 0 | 2325.89 | 2488.7 | 0 | 1704.29 | 0 | 0 | -2325.89 | 0 | 2325.89 | 0 | 621.6 | 0.2673 | 100 | 0.043 | 0 | 0 | 0 | -162.81 | FALSE | FALSE
2026-06-17 | 2438113 | DS.2025.2272 Courtyards of Russell Oaks 48 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 5849.67 | 0 | 5849.67 | 6259.15 | 0 | 4371.5 | 0 | 0 | -5849.67 | 0 | 5849.67 | 0 | 1478.17 | 0.2527 | 100 | 0.0171 | 0 | 0 | 0 | -409.48 | FALSE | FALSE
2026-06-17 | 2438103 | DS.2025.2271 Courtyards of Westfield 113 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 7005.73 | 0 | 7005.73 | 7496.13 | 0 | 5233.09 | 0 | 0 | -7005.73 | 0 | 7005.73 | 0 | 1772.64 | 0.253 | 100 | 0.0143 | 0 | 0 | 0 | -490.4 | FALSE | FALSE
2026-06-17 | 2433725 | DS.2025.2269 GSI Ranch Basement House 9-22 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 6041.4 | 0 | 6041.4 | 6464.3 | 0 | 4279.47 | 0 | 0 | -6041.4 | 0 | 6041.4 | 0 | 1761.93 | 0.2916 | 100 | 0.0166 | 0 | 0 | 0 | -422.9 | FALSE | FALSE
2026-06-17 | 2431674 | DS.2025.2267 GSI Rushville Lot 17 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 3571.1 | 0 | 3571.1 | 3821.08 | 0 | 2655.4 | 0 | 0 | -3571.1 | 0 | 3571.1 | 0 | 915.7 | 0.2564 | 100 | 0.028 | 0 | 0 | 0 | -249.98 | FALSE | FALSE
2026-06-17 | 2431619 | DS.2025.2265 Courtyards of Westfield 42 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6951.57 | 507.6 | 6951.57 | 7402.65 | 0 | 5144.6 | 0 | 0 | -6951.57 | 0 | 6951.57 | 0 | 1806.97 | 0.2599 | 100 | 0.0144 | 0 | 0 | 0 | -451.08 | FALSE | FALSE
2026-06-17 | 2426990 | DS.2025.2264 Maratt Remodel | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 5434.22 | 0 | 5434.22 | 5814.62 | 0 | 3595.46 | 0 | 0 | -5434.22 | 0 | 5434.22 | 0 | 1838.76 | 0.3384 | 100 | 0.0184 | 0 | 0 | 0 | -380.4 | FALSE | FALSE
2026-06-17 | 2426804 | DS.2025.2262 Rushville 2 house pre rock | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 786.08 | 0 | 786.08 | 841.11 | 0 | 477 | 0 | 0 | -786.08 | 0 | 786.08 | 0 | 309.08 | 0.3932 | 100 | 0.1272 | 0 | 0 | 0 | -55.03 | FALSE | FALSE
2026-06-17 | 2426715 | DS.2025.2258 Cavalier Res | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 11550.86 | 0 | 11550.86 | 12359.42 | 0 | 8584.56 | 0 | 0 | -11550.86 | 0 | 11550.86 | 0 | 2966.3 | 0.2568 | 100 | 0.0087 | 0 | 0 | 0 | -808.56 | FALSE | FALSE
2026-06-17 | 2426691 | DS.2025.2257 Courtyards of Russell Oaks 116 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6943.39 | 0 | 6943.39 | 7429.43 | 0 | 5186.83 | 0 | 0 | -6943.39 | 0 | 6943.39 | 0 | 1756.56 | 0.253 | 100 | 0.0144 | 0 | 0 | 0 | -486.04 | FALSE | FALSE
2026-06-17 | 2422257 | 2025.1016 WBP Lot C | TI | Tommy Cohoat | Patch Development | ACTIVE | 125700 | -30000 | 125700 | 112618.13 | 53430 | 109812.99 | 2.0553 | 258351.21 | 132651.21 | 0 | 0 | 132651.21 | 15887.01 | 0.1264 | 57.49 | 0.0005 | 0.5749 | -0.5745 | 0 | 13081.87 | TRUE | TRUE
2026-06-17 | 2414762 | 2025.1013 Lucas Oil Corydon | TI | Shawn Welcher | Meyer Najem | ACTIVE | 103243.16 | 3243.16 | 100000 | 0 | 59346.55 | 59346.55 | 1 | 103243.16 | 3243.16 | 3243.16 | 0 | 3243.16 | 40653.45 | 0.4065 | 42.52 | 0.0004 | 0.4252 | -0.4248 | 0 | 100000 | TRUE | TRUE
2026-06-17 | 2412851 | 2025.1012 Airport South Logistics Bldg. B | TI | Spencer Anderson | ARCO Design/Build | ACTIVE | 128180 | 115280 | 103245.3 | 9868.5 | 97377 | 97782.06 | 1.0042 | 128718.36 | 25473.06 | 13463 | 0 | 25473.06 | 16934.94 | 0.1476 | 24.03 | 0.0002 | 0.2403 | -0.2401 | 11471.7 | 93376.8 | TRUE | TRUE
2026-06-17 | 2412835 | 2025.1011 Airport South Logistics Bldg. A | TI | Spencer Anderson | ARCO Design/Build | ACTIVE | 134480 | 115280 | 0 | 0 | 82800 | 42.24 | 0.0005 | 67.24 | 67.24 | 68.6 | 0 | 67.24 | -42.24 | 0 | 38.43 | 0.0003 | 0.3843 | -0.384 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2400949 | DS.2025.2243 5689 N Ohio Ridge Rd | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 7069.21 | 0 | 7069.21 | 7564.05 | 0 | 4853.4 | 0 | 0 | -7069.21 | 0 | 7069.21 | 0 | 2215.81 | 0.3134 | 100 | 0.0141 | 0 | 0 | 0 | -494.84 | FALSE | FALSE
2026-06-17 | 2400575 | DS.2025.2241 6915 SR 550 | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | 3247.36 | 0 | 3247.36 | 0 | 0 | 2345.39 | 0 | 0 | -3247.36 | 0 | 3247.36 | 0 | 901.97 | 0.2778 | 100 | 0.0308 | 0 | 0 | 0 | 3247.36 | FALSE | FALSE
2026-06-17 | 2394684 | 2025.1027 Indy Boat Co | TI | Trevor Anderson | Raley Wake, LLC | ACTIVE | 242452.3 | 24952.3 | 136345.9 | 136345.9 | 128453.53 | 124548.27 | 0.9696 | 235081.75 | 98735.85 | 86019.79 | 0 | 98735.85 | 24513.18 | 0.1645 | 47.02 | 0.0002 | 0.4702 | -0.47 | 12715.55 | 0 | TRUE | TRUE
2026-06-17 | 2394677 | MF.2025.1019 Town & Country Apartments (NY MF Project - 22 bldgs) | MF | Kelden Tyson | Marous Brothers Construction | ACTIVE | 8064307.39 | 327165.39 | 2583844.73 | 2028381.32 | 4716881.88 | 1661749.53 | 0.3523 | 2841055.49 | 257210.76 | 121205.35 | 0 | 257210.76 | 1058087.01 | 0.389 | 41.51 | 0 | 0.4151 | -0.4151 | 135991.81 | 555463.41 | TRUE | TRUE
2026-06-17 | 2389374 | DS.2025.2236 Courtyards of Russell Oaks 149,146 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 650.16 | 0 | 650.16 | 695.67 | 0 | 468.72 | 0 | 0 | -650.16 | 0 | 650.16 | 0 | 181.44 | 0.2791 | 100 | 0.1538 | 0 | 0 | 0 | -45.51 | FALSE | FALSE
2026-06-17 | 2389077 | DS.2025.2235 18 Store Estates | DW | (Unassigned) | Community Drywall | ACTIVE | 5273.96 | 0 | 5273.96 | 0 | 0 | 3825.13 | 0 | 0 | -5273.96 | 0 | 5273.96 | 0 | 1448.83 | 0.2747 | 100 | 0.019 | 0 | 0 | 0 | 5273.96 | FALSE | FALSE
2026-06-17 | 2388892 | DS.2025.2234 Lot 4 Store Estates | DW | (Unassigned) | Community Drywall | ACTIVE | 5095.88 | 0 | 5095.88 | 0 | 0 | 3662.33 | 0 | 0 | -5095.88 | 0 | 5095.88 | 0 | 1433.55 | 0.2813 | 100 | 0.0196 | 0 | 0 | 0 | 5095.88 | FALSE | FALSE
2026-06-17 | 2388766 | DS.2025.2233 49 Bills Blvd | DW | (Unassigned) | Kjt General Construction | ACTIVE | 2379.05 | 0 | 2379.05 | 0 | 0 | 1672.2 | 0 | 0 | -2379.05 | 0 | 2379.05 | 0 | 706.85 | 0.2971 | 100 | 0.042 | 0 | 0 | 0 | 2379.05 | FALSE | FALSE
2026-06-17 | 2383587 | 2025.1006 Keller Office | TI | Ben Garza | ARCO Design/Build | ACTIVE | 276600 | 242700 | 191272.5 | 0 | 151740.65 | 155439.2 | 1.0244 | 283349.04 | 92076.54 | 64075 | 0 | 92076.54 | 57085.8 | 0.2686 | 45.14 | 0.0002 | 0.4514 | -0.4512 | 21252.5 | 191272.5 | TRUE | TRUE
2026-06-17 | 2381339 | DS.2025.2228 Edgebrook Lot 72 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | 6184.17 | 0 | 6184.17 | 6617.06 | 0 | 4654.79 | 0 | 0 | -6184.17 | 0 | 6184.17 | 0 | 1529.38 | 0.2473 | 100 | 0.0162 | 0 | 0 | 0 | -432.89 | FALSE | FALSE
2026-06-17 | 2368894 | DS.2025.2222 Courtyards of Russell Oaks 55 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | 6474.74 | 0 | 6474.74 | 6927.97 | 0 | 4767.3 | 0 | 0 | -6474.74 | 0 | 6474.74 | 0 | 1707.44 | 0.2637 | 100 | 0.0154 | 0 | 0 | 0 | -453.23 | FALSE | FALSE
2026-06-17 | 2367104 | DS.2025.2220 17 Store Estates | DW | (Unassigned) | Community Drywall | ACTIVE | 4926.56 | 0 | 4926.56 | 2522.74 | 0 | 3565.7 | 0 | 0 | -4926.56 | 0 | 4926.56 | 0 | 1360.86 | 0.2762 | 100 | 0.0203 | 0 | 0 | 0 | 2403.82 | FALSE | FALSE
2026-06-17 | 2366840 | DS.2025.2217 Davidson Residence | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 18188.37 | 0 | 18188.37 | 19461.56 | 0 | 13255.73 | 0 | 0 | -18188.37 | 0 | 18188.37 | 0 | 4932.64 | 0.2712 | 100 | 0.0055 | 0 | 0 | 0 | -1273.19 | FALSE | FALSE
2026-06-17 | 2366626 | DS.2025.2215 44 Willow Springs | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 25349.24 | 0 | 25349.24 | 27123.69 | 0 | 18542.92 | 0 | 0 | -25349.24 | 0 | 25349.24 | 0 | 6806.32 | 0.2685 | 100 | 0.0039 | 0 | 0 | 0 | -1774.45 | FALSE | FALSE
2026-06-17 | 2363817 | DS.2025.2212 Scottsdale Lot 70 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | 6551.92 | 0 | 6551.92 | 7010.55 | 0 | 5066.83 | 0 | 0 | -6551.92 | 0 | 6551.92 | 0 | 1485.09 | 0.2267 | 100 | 0.0153 | 0 | 0 | 0 | -458.63 | FALSE | FALSE
2026-06-17 | 2363162 | DS.2025.2208 12921 Merlot Ln | DW | (Unassigned) | M&M Drywall | ACTIVE | 3783.98 | 0 | 3783.98 | 4048.86 | 0 | 2627.37 | 0 | 0 | -3783.98 | 0 | 3783.98 | 0 | 1156.61 | 0.3057 | 100 | 0.0264 | 0 | 0 | 0 | -264.88 | FALSE | FALSE
2026-06-17 | 2359929 | DS.2025.2207 Edgebrook Lot 219 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | 7143.52 | 0 | 7143.52 | 7643.57 | 0 | 5405.03 | 0 | 0 | -7143.52 | 0 | 7143.52 | 0 | 1738.49 | 0.2434 | 100 | 0.014 | 0 | 0 | 0 | -500.05 | FALSE | FALSE
2026-06-17 | 2354747 | DS.2025.2202 M&M Drywall Pickup 7-29 | DW | (Unassigned) | M&M Drywall | ACTIVE | 70.5 | 0 | 70.5 | 75.44 | 0 | 63.75 | 0 | 0 | -70.5 | 0 | 70.5 | 0 | 6.75 | 0.0957 | 100 | 1.4184 | 0 | 0 | 0 | -4.94 | FALSE | FALSE
2026-06-17 | 2350460 | DS.2025.2197 Edgebrook Lot 199 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | 6807.24 | 0 | 6807.24 | 7283.75 | 0 | 5249.46 | 0 | 0 | -6807.24 | 0 | 6807.24 | 0 | 1557.78 | 0.2288 | 100 | 0.0147 | 0 | 0 | 0 | -476.51 | FALSE | FALSE
2026-06-17 | 2350360 | DS.2025.2196 1718 Bellefontaine St | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | 5731.96 | 0 | 5731.96 | 6133.2 | 0 | 4347.15 | 0 | 0 | -5731.96 | 0 | 5731.96 | 0 | 1384.81 | 0.2416 | 100 | 0.0174 | 0 | 0 | 0 | -401.24 | FALSE | FALSE
2026-06-17 | 2349208 | DS.2025.2194 GSI House 10 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 4071.34 | 0 | 4071.34 | 4356.33 | 0 | 2729 | 0 | 0 | -4071.34 | 0 | 4071.34 | 0 | 1342.34 | 0.3297 | 100 | 0.0246 | 0 | 0 | 0 | -284.99 | FALSE | FALSE
2026-06-17 | 2346918 | DS.2025.2191 Edgebrook Lot 192 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | 7167.06 | 0 | 7167.06 | 7668.75 | 0 | 5419.06 | 0 | 0 | -7167.06 | 0 | 7167.06 | 0 | 1748 | 0.2439 | 100 | 0.014 | 0 | 0 | 0 | -501.69 | FALSE | FALSE
2026-06-17 | 2343287 | DS.2025.2189 1022 E 3rd Bloomington | DW | (Unassigned) | Kjt General Construction | ACTIVE | 3332.7 | 0 | 3332.7 | 0 | 0 | 2406.3 | 0 | 0 | -3332.7 | 0 | 3332.7 | 0 | 926.4 | 0.278 | 100 | 0.03 | 0 | 0 | 0 | 3332.7 | FALSE | FALSE
2026-06-17 | 2340132 | DS.2025.2187 Crawford Res, 880 Baywood Court | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 7213 | 0 | 7213 | 7717.91 | 0 | 4224.42 | 0 | 0 | -7213 | 0 | 7213 | 0 | 2988.58 | 0.4143 | 100 | 0.0139 | 0 | 0 | 0 | -504.91 | FALSE | FALSE
2026-06-17 | 2340035 | DS.2025.2186 Bloomington Triplex Unit 3 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 6148.53 | 0 | 6148.53 | 6578.93 | 0 | 4331.05 | 0 | 0 | -6148.53 | 0 | 6148.53 | 0 | 1817.48 | 0.2956 | 100 | 0.0163 | 0 | 0 | 0 | -430.4 | FALSE | FALSE
2026-06-17 | 2340013 | DS.2025.2185 Bloomington Triplex Middle Unit | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 3935.7 | 0 | 3935.7 | 4211.2 | 0 | 2826.14 | 0 | 0 | -3935.7 | 0 | 3935.7 | 0 | 1109.56 | 0.2819 | 100 | 0.0254 | 0 | 0 | 0 | -275.5 | FALSE | FALSE
2026-06-17 | 2339995 | DS.2025.2184 Bloomington Triplex Unit 1 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 5737.8 | 0 | 5737.8 | 6139.45 | 0 | 4054.36 | 0 | 0 | -5737.8 | 0 | 5737.8 | 0 | 1683.44 | 0.2934 | 100 | 0.0174 | 0 | 0 | 0 | -401.65 | FALSE | FALSE
2026-06-17 | 2339243 | DS.2025.2182 9220 Tower Rd | DW | (Unassigned) | Solano Masonry, Inc. | ACTIVE | 2697.75 | 0 | 2697.75 | 2886.59 | 0 | 1993.95 | 0 | 0 | -2697.75 | 0 | 2697.75 | 0 | 703.8 | 0.2609 | 100 | 0.0371 | 0 | 0 | 0 | -188.84 | FALSE | FALSE
2026-06-17 | 2337339 | DS.2025.2175 6891 State Road 257 | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | 316 | 0 | 316 | 0 | 0 | 145.8 | 0 | 0 | -316 | 0 | 316 | 0 | 170.2 | 0.5386 | 100 | 0.3165 | 0 | 0 | 0 | 316 | FALSE | FALSE
2026-06-17 | 2327047 | DS.2025.2169 Abbey Place 311 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 5048.01 | 0 | 5048.01 | 5401.37 | 0 | 3652.08 | 0 | 0 | -5048.01 | 0 | 5048.01 | 0 | 1395.93 | 0.2765 | 100 | 0.0198 | 0 | 0 | 0 | -353.36 | FALSE | FALSE
2026-06-17 | 2304400 | DS.2025.2150 V3 Holiday Farms | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 11827.1 | 0 | 0 | 0 | 0 | 15224.85 | 0 | 0 | 0 | 0 | 0 | 0 | -15224.85 | 0 | 100 | 0.0085 | 0 | 0 | 0 | 0 | FALSE | FALSE
2026-06-17 | 2303764 | 2025.1021 Convivio | TI | Shawn Welcher | The Peterson Company, LLC | ACTIVE | 87788.26 | 15788.26 | 87788.26 | 87788.26 | 63124.37 | 63124.37 | 1 | 87788.26 | 0 | 0 | 0 | 0 | 24663.89 | 0.2809 | 28.09 | 0.0003 | 0.2809 | -0.2806 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2303466 | 2025.999 Romet PWSI | TI | Tommy Cohoat | The Peterson Company, LLC | ACTIVE | 372490 | 14740 | 372490 | 372490 | 189800 | 190491.63 | 1.0036 | 373830.96 | 1340.96 | 0 | 0 | 1340.96 | 181998.37 | 0.4886 | 49.05 | 0.0001 | 0.4905 | -0.4903 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2302121 | DS.2025.2143 GSI Ranch | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 5864.13 | 0 | 5864.13 | 6274.62 | 0 | 4106.76 | 0 | 0 | -5864.13 | 0 | 5864.13 | 0 | 1757.37 | 0.2997 | 100 | 0.0171 | 0 | 0 | 0 | -410.49 | FALSE | FALSE
2026-06-17 | 2301410 | DS.2025.2138 51 Preserve | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | 5783.87 | 0 | 5783.87 | 6188.74 | 0 | 4328.55 | 0 | 0 | -5783.87 | 0 | 5783.87 | 0 | 1455.32 | 0.2516 | 100 | 0.0173 | 0 | 0 | 0 | -404.87 | FALSE | FALSE
2026-06-17 | 2296704 | DS.2025.2118 House 6 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | 3565.84 | 0 | 3565.84 | 3815.45 | 0 | 2398.54 | 0 | 0 | -3565.84 | 0 | 3565.84 | 0 | 1167.3 | 0.3274 | 100 | 0.028 | 0 | 0 | 0 | -249.61 | FALSE | FALSE
2026-06-17 | 2282848 | 2025.997 Belmont St Warehouse Clear Out 250-408 | TI | Spencer Anderson | DEEM, LLC | ACTIVE | 54090 | 38090 | 54090 | 54090 | 10911.31 | 23635.43 | 2.1661 | 117164.35 | 63074.35 | 0 | 0 | 63074.35 | 30454.57 | 0.563 | 79.83 | 0.0015 | 0.7983 | -0.7968 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2261041 | DS.2025.2072 Tom Carter Prince's Lake | DW | (Unassigned) | TC Indy | ACTIVE | 10104.28 | 1410.4 | 10104.28 | 10811.58 | 0 | 5309.73 | 0 | 0 | -10104.28 | 0 | 10104.28 | 0 | 4794.55 | 0.4745 | 100 | 0.0099 | 0 | 0 | 0 | -707.3 | FALSE | FALSE
2026-06-17 | 2250539 | 2025.1032 65 Commerce Park Building 7 | TI | Trevor Anderson | Compass Commercial Construction Group | ACTIVE | 133900 | 0 | 71314.2 | 0 | 92029.79 | 81690.55 | 0.8877 | 118863.03 | 47548.83 | 39618.78 | 0 | 47548.83 | -2452.55 | -0.031 | 31.27 | 0.0002 | 0.3127 | -0.3125 | 7923.8 | 71314.2 | TRUE | TRUE
2026-06-17 | 2248156 | 2025.994 Stotan Port Laredo Spec Offices | TI | Ben Garza | ARCO Design/Build | ACTIVE | 699328 | 121328 | 699328 | 584395.2 | 454026.48 | 454026.48 | 1 | 699328 | 0 | 0 | 0 | 0 | 245301.52 | 0.3508 | 35.08 | 0.0001 | 0.3508 | -0.3507 | 0 | 114932.8 | TRUE | TRUE
2026-06-17 | 2242353 | DS.2025.2045 Old Town Pickup | DW | (Unassigned) | Old Town Design Group | ACTIVE | 121.08 | 0 | 121.08 | 129.56 | 0 | 94.08 | 0 | 0 | -121.08 | 0 | 121.08 | 0 | 27 | 0.223 | 100 | 0.8259 | 0 | 0 | 0 | -8.48 | FALSE | FALSE
2026-06-17 | 2225641 | MF.2026.1050 AC Hotel | MF | Ben Garza | Holladay Construction Group | ACTIVE | 1244040 | 0 | 202650.67 | 0 | 837300 | 175699.76 | 0.2098 | 260999.59 | 58348.92 | 35883.03 | 0 | 58348.92 | 49467.65 | 0.2197 | 32.7 | 0 | 0.327 | -0.3269 | 22516.74 | 202650.67 | TRUE | TRUE
2026-06-17 | 2223116 | 2025.986 FedEx Hub | TI | Tommy Cohoat | Dalmatian Fire | ACTIVE | 6000 | 0 | 6000 | 6000 | 700 | 118.93 | 0.1699 | 1019.4 | -4980.6 | -4980.6 | 4980.6 | 0 | 5881.07 | 0.9802 | 88.33 | 0.0147 | 0.8833 | -0.8686 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2205083 | DS.2025.1967 MN - H2S | DW | (Unassigned) | Meyer Najem | ACTIVE | 11836.8 | 0 | 11836.8 | 0 | 0 | 8635.52 | 0 | 0 | -11836.8 | 0 | 11836.8 | 0 | 3201.28 | 0.2705 | 100 | 0.0084 | 0 | 0 | 0 | 11836.8 | FALSE | FALSE
2026-06-17 | 2196541 | 2025.1015 WBP Lot 4 | TI | Tommy Cohoat | Patch Development | ACTIVE | 175400 | 19500 | 175400 | 175400 | 73600 | 72620.15 | 0.9867 | 173067.18 | -2332.82 | -2335.13 | 2332.82 | 0 | 102779.85 | 0.586 | 58.04 | 0.0003 | 0.5804 | -0.5801 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2174851 | 2025.1001 Evolve Transporters | TI | Cole Garriott | Compass Commercial Construction Group | ACTIVE | 1317620 | 277640 | 1317620 | 1184517 | 787696.54 | 795731.39 | 1.0102 | 1331059.72 | 13439.72 | 0 | 0 | 13439.72 | 521888.61 | 0.3961 | 40.22 | 0 | 0.4022 | -0.4022 | 0 | 133103 | TRUE | TRUE
2026-06-17 | 2160928 | DS.2025.1895 IFD Pickup 3/25/25 | DW | (Unassigned) | Indianapolis Fire Department | ACTIVE | 718.08 | 0 | 718.08 | 0 | 0 | 587.52 | 0 | 0 | -718.08 | 0 | 718.08 | 0 | 130.56 | 0.1818 | 100 | 0.1393 | 0 | 0 | 0 | 718.08 | FALSE | FALSE
2026-06-17 | 2157624 | 2025.980 Avon Bldg. 1 Canopies & Pavilion | TI | Spencer Anderson | The Peterson Company, LLC | ACTIVE | 116280 | 0 | 116280 | 116280 | 40262.24 | 40530.89 | 1.0067 | 117059.08 | 779.08 | 0 | 0 | 779.08 | 75749.11 | 0.6514 | 65.37 | 0.0006 | 0.6537 | -0.6532 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2152299 | DS.2025.1882 Alexandria Building 24 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | 2829.01 | 0 | 0 | 0 | 0 | 2100.41 | 0 | 0 | 0 | 0 | 0 | 0 | -2100.41 | 0 | 100 | 0.0353 | 0 | 0 | 0 | 0 | FALSE | FALSE
2026-06-17 | 2117526 | 2025.993 Batesville Public Library | TI | Shawn Welcher | Meyer Najem | ACTIVE | 63852.15 | 1177.15 | 62675 | 2147 | 74275.84 | 74275.84 | 1 | 63852.15 | 1177.15 | 1177.15 | 0 | 1177.15 | -11600.84 | -0.1851 | -16.32 | -0.0003 | -0.1632 | 0.163 | 0 | 60528 | TRUE | TRUE
2026-06-17 | 2108038 | 2025.979 Groundbreakers | TI | Trevor Anderson | Patch Development | ACTIVE | 288504.91 | 65984.91 | 287665.4 | 287665.4 | 162334.99 | 162334.99 | 1 | 288504.91 | 839.51 | 839.51 | 0 | 839.51 | 125330.41 | 0.4357 | 43.73 | 0.0002 | 0.4373 | -0.4372 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2098776 | 2025.969 Carson | TI | Spencer Anderson | DEEM, LLC | ACTIVE | 287418 | 163418 | 287418 | 287418 | 155989.46 | 155814.41 | 0.9989 | 287101.84 | -316.16 | -322.54 | 316.16 | 0 | 131603.59 | 0.4579 | 45.73 | 0.0002 | 0.4573 | -0.4571 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2092684 | MF.2025.992 Young's Creek Apartments | MF | Kelden Tyson | Shiel Sexton | ACTIVE | 488752.35 | -308847.65 | 488752.35 | 216259.24 | 340853.31 | 340853.31 | 1 | 488752.35 | 0 | 0 | 0 | 0 | 147899.04 | 0.3026 | 30.26 | 0.0001 | 0.3026 | -0.3025 | 0 | 272493.11 | TRUE | TRUE
2026-06-17 | 2087575 | MF.2025.976 Firefly Youth Housing | MF | Spencer Anderson | Stenz Corp | ACTIVE | 250736.11 | 27736.11 | 225662.5 | 152537.5 | 180171.84 | 180171.84 | 1 | 250736.11 | 25073.61 | 0 | 0 | 25073.61 | 70564.27 | 0.2814 | 28.14 | 0.0001 | 0.2814 | -0.2813 | 25073.61 | 73125 | TRUE | TRUE
2026-06-17 | 2087565 | 2026.1052 Project Panther | TI | Spencer Anderson | ARCO Design/Build | ACTIVE | 900893 | 0 | 0 | 0 | 442417.21 | 24806.55 | 0.0561 | 50540.1 | 50540.1 | 50513.51 | 0 | 50540.1 | -24806.55 | 0 | 50.89 | 0.0001 | 0.5089 | -0.5089 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2067674 | DS.2025.1762 Jeff West Builders for Steve Raker | DW | (Unassigned) | Jeff West Homes | ACTIVE | 3911.43 | 84 | 3911.43 | 4185.23 | 0 | 2903.12 | 0 | 0 | -3911.43 | 0 | 3911.43 | 0 | 1008.31 | 0.2578 | 100 | 0.0256 | 0 | 0 | 0 | -273.8 | FALSE | FALSE
2026-06-17 | 2061037 | DS.2025.1759 Juan Lugo NC 01-22 | DW | (Unassigned) | Lugo Contracting, LLC | ACTIVE | 128322.88 | 0 | 128322.88 | 137305.48 | 0 | 100104.05 | 0 | 0 | -128322.88 | 0 | 128322.88 | 0 | 28218.83 | 0.2199 | 100 | 0.0008 | 0 | 0 | 0 | -8982.6 | FALSE | FALSE
2026-06-17 | 2040900 | MF.2025.977 Civic Square Condos | MF | Trevor Anderson | Novo Development Group, LLC | ACTIVE | 603098 | 35098 | 603098 | 542788.2 | 454386.68 | 453638.15 | 0.9984 | 602133.04 | -964.96 | -993.51 | 964.96 | 0 | 149459.85 | 0.2478 | 24.66 | 0 | 0.2466 | -0.2465 | 0 | 60309.8 | TRUE | TRUE
2026-06-17 | 2037261 | 2025.966 C5 Bullitt III Logistics Center Warehouse | TI | Trevor Anderson | The Peterson Company, LLC | ACTIVE | 415930 | 32099 | 415930 | 415930 | 253086.48 | 253397.03 | 1.0012 | 416429.12 | 499.12 | 0 | 0 | 499.12 | 162532.97 | 0.3908 | 39.15 | 0.0001 | 0.3915 | -0.3914 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2028240 | 2025.960 Langham Whiteland South Lockers | TI | Spencer Anderson | DEEM, LLC | ACTIVE | 72797 | 0 | 72797 | 72797 | 53046.04 | 53580.36 | 1.0101 | 73532.25 | 735.25 | 0 | 0 | 735.25 | 19216.64 | 0.264 | 27.13 | 0.0004 | 0.2713 | -0.2709 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2025315 | 2024.957 SanMar AWR | TI | Cole Garriott | The Peterson Company, LLC | ACTIVE | 34964 | 10398 | 34964 | 34964 | 17925.48 | 17925.48 | 1 | 34964 | 0 | 0 | 0 | 0 | 17038.52 | 0.4873 | 48.73 | 0.0014 | 0.4873 | -0.4859 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2012203 | 2024.953 Motorworks | TI | Tommy Cohoat | Precision Dry Wall | ACTIVE | 2605.74 | 405.74 | 2605.74 | 2605.74 | 1364.98 | 1364.98 | 1 | 2605.74 | 0 | 0 | 0 | 0 | 1240.76 | 0.4762 | 47.62 | 0.0183 | 0.4762 | -0.4579 | 0 | 0 | TRUE | TRUE
2026-06-17 | 2009228 | MF.2025.963 Home 2 Suites | MF | Kelden Tyson | Meyer Najem | ACTIVE | 580227.88 | 5227.88 | 580227.88 | 522205.09 | 408243.32 | 408243.32 | 1 | 580227.88 | 0 | 0 | 0 | 0 | 171984.56 | 0.2964 | 29.64 | 0.0001 | 0.2964 | -0.2964 | 0 | 58022.79 | TRUE | TRUE
2026-06-17 | 1989297 | DS.2024.1656 Juan Lugo 1202 NC | DW | (Unassigned) | Lugo Contracting, LLC | ACTIVE | 83195.75 | 0 | 83195.75 | 89019.45 | 0 | 67140.53 | 0 | 0 | -83195.75 | 0 | 83195.75 | 0 | 16055.22 | 0.193 | 100 | 0.0012 | 0 | 0 | 0 | -5823.7 | FALSE | FALSE
2026-06-17 | 1956827 | MF.2024.941 Oak Trace | MF | Dustin Hurt | Westfield Community Management, LLC | ACTIVE | 76730 | 15200 | 76730 | 76730 | 59188.79 | 59237.53 | 1.0008 | 76791.38 | 61.38 | 0 | 0 | 61.38 | 17492.47 | 0.228 | 22.86 | 0.0003 | 0.2286 | -0.2283 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1900804 | MF.2025.972 Union Flats - Fishers | MF | Ben Garza | Thompson Thrift Construction | ACTIVE | 3838166 | -11834 | 2726076.15 | 1584810 | 2682585.85 | 2343618.31 | 0.8736 | 3353021.82 | 626945.67 | 324207.58 | 0 | 626945.67 | 685355.19 | 0.2263 | 30.11 | 0 | 0.3011 | -0.3011 | 302897.35 | 1141266.15 | TRUE | TRUE
2026-06-17 | 1870076 | 2024.929 DEEM Warehouse | TI | Tommy Cohoat | DEEM, LLC | ACTIVE | 659384.05 | 610634.05 | 659384.05 | 659384.05 | 260000 | 257137.17 | 0.989 | 652130.83 | -7253.22 | -7260.4 | 7253.22 | 0 | 402246.88 | 0.61 | 60.57 | 0.0001 | 0.6057 | -0.6056 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1854607 | MF.2024.924 Monon Trail Elementary | MF | Dustin Hurt | LTB Construction, Inc. | ACTIVE | 4550 | 0 | 4550 | 4550 | 5200 | 1575 | 0.3029 | 1378.19 | -3171.81 | 0 | 3171.81 | 0 | 2975 | 0.6538 | -14.29 | -0.0031 | -0.1429 | 0.1397 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1842206 | 2024.920 SMC Mezzanine HVAC | TI | Trevor Anderson | DEEM, LLC | ACTIVE | 2028 | 0 | 2028 | 2028 | 945.21 | 945.21 | 1 | 2028 | 0 | 0 | 0 | 0 | 1082.79 | 0.5339 | 53.39 | 0.0263 | 0.5339 | -0.5076 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1839016 | MF.2025.1007 The Approach | MF | Kelden Tyson | KCG | ACTIVE | 5643379.34 | 283379.34 | 0 | 0 | 3375843.48 | 2174.78 | 0.0006 | 3386.03 | 3386.03 | 3635.57 | 0 | 3386.03 | -2174.78 | 0 | 40.18 | 0 | 0.4018 | -0.4018 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1820214 | DS.2024.1378 Ketchum Basement | DW | (Unassigned) | Mendoza | ACTIVE | 4398.77 | 0 | 4398.77 | 4706.68 | 0 | 2876.96 | 0 | 0 | -4398.77 | 0 | 4398.77 | 0 | 1521.81 | 0.346 | 100 | 0.0227 | 0 | 0 | 0 | -307.91 | FALSE | FALSE
2026-06-17 | 1819558 | DS.2024.1377 Warehouse Pickup 0710 - 2824 Sunnyfield Ct | DW | (Unassigned) | Imperial Design | ACTIVE | 574 | 0 | 574 | 614.18 | 0 | 392 | 0 | 0 | -574 | 0 | 574 | 0 | 182 | 0.3171 | 100 | 0.1742 | 0 | 0 | 0 | -40.18 | FALSE | FALSE
2026-06-17 | 1814679 | 2024.913 Walmart Phoenix | TI | Cole Garriott | DEEM, LLC | ACTIVE | 2945439.34 | 522628.34 | 2532252.91 | 2503340.4 | 1703791.05 | 1611541.57 | 0.9459 | 2786091.07 | 253838.16 | -27651.86 | 0 | 253838.16 | 1202072.77 | 0.4272 | 42.15 | 0 | 0.4215 | -0.4215 | 281361.43 | 28912.51 | TRUE | TRUE
2026-06-17 | 1806764 | MF.2025.975 The Eleven - Monon Square | MF | Shawn Welcher | Centric Projects, LLC | ACTIVE | 465610 | -4620 | 252211.41 | 0 | 319224.72 | 63773.71 | 0.1998 | 93028.88 | -159182.53 | -172467.59 | 159182.53 | 0 | 201711.98 | 0.7598 | 31.44 | 0.0001 | 0.3144 | -0.3143 | 13274.28 | 252211.41 | TRUE | TRUE
2026-06-17 | 1803611 | MF.2025.989-1 Springdale Cinema - Paint | MF | Ben Garza | MILHAUS Construction | ACTIVE | 875000 | 0 | 607050 | 55440 | 580310 | 435602.6 | 0.7506 | 656775 | 49725 | -17691.96 | 0 | 49725 | 238897.4 | 0.3542 | 33.68 | 0 | 0.3368 | -0.3368 | 67450 | 551610 | TRUE | TRUE
2026-06-17 | 1794757 | MF.2024.906 Shamrock Elementary LGI Classrooms | MF | Dustin Hurt | LTB Construction, Inc. | ACTIVE | 8830 | 0 | 8830 | 8830 | 6640 | 2612.75 | 0.3935 | 3474.61 | -5355.4 | -5355.51 | 5355.4 | 0 | 6217.25 | 0.7041 | 24.8 | 0.0028 | 0.248 | -0.2452 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1787241 | DS.2024.1346 10660 Pete Dye Ridge | DW | (Unassigned) | Promasters Drywall and Painting (Brian Figueroa) | ACTIVE | 1229.28 | 0 | 1229.28 | 1315.33 | 0 | 717.6 | 0 | 0 | -1229.28 | 0 | 1229.28 | 0 | 511.68 | 0.4162 | 100 | 0.0813 | 0 | 0 | 0 | -86.05 | FALSE | FALSE
2026-06-17 | 1779490 | MF.2024.903 Mirka Office Buildout | MF | Cole Garriott | DEEM, LLC | ACTIVE | 175330 | 4930 | 175330 | 175330 | 62924.02 | 62924.02 | 1 | 175330 | 0 | 0 | 0 | 0 | 112405.98 | 0.6411 | 64.11 | 0.0004 | 0.6411 | -0.6407 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1779189 | MF.2024.927 Jeffersonian Apartments | MF | Ben Garza | Stenz Corp | ACTIVE | 461337.65 | 6337.65 | 461337.65 | 415203.89 | 337818.47 | 337818.47 | 1 | 461337.65 | 0 | 0 | 0 | 0 | 123519.18 | 0.2677 | 26.77 | 0.0001 | 0.2677 | -0.2677 | 0 | 46133.76 | TRUE | TRUE
2026-06-17 | 1772287 | DS.2024 8503 N 600 W Fountaintown QUOTE | DW | (Unassigned) | TC Indy | ACTIVE | 2031.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0.0492 | 0 | 0 | 0 | 0 | FALSE | FALSE
2026-06-17 | 1735717 | 1234.567 Test Job | UN | (Unassigned) | Sample Client | ACTIVE | 1 | 0 | 0 | 0 | 2 | 10 | 5 | 5 | 5 | 1 | 0 | 5 | -10 | 0 | -100 | -100 | -1 | -99 | 0 | 0 | TRUE | FALSE
2026-06-17 | 1724469 | MF.2024.894 Hamilton County Jail Boiler Mechanical Pad | MF | Dustin Hurt | DEEM, LLC | ACTIVE | 3515 | 0 | 3515 | 3515 | 2600.05 | 2407.26 | 0.9259 | 3254.54 | -260.46 | -260.63 | 260.46 | 0 | 1107.74 | 0.3151 | 26.03 | 0.0074 | 0.2603 | -0.2529 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1710251 | MF.2024.892 The Lofts at Headwaters Park | MF | Ben Garza | J.C. Hart Company, Inc. | ACTIVE | 4286845.96 | 232955.96 | 3779782.52 | 3620296.13 | 3615074.96 | 3606896.8 | 0.9977 | 4276986.21 | 497203.69 | 77389.73 | 0 | 497203.69 | 592861.56 | 0.1412 | 15.67 | 0 | 0.1567 | -0.1567 | 419975.84 | 159486.39 | TRUE | TRUE
2026-06-17 | 1702352 | 2025.967 Bunge Project Flex | TI | Ben Garza | Bunge North America (East), LLC | ACTIVE | 993046 | 23418 | 993046 | 893741.4 | 452407.33 | 452407.33 | 1 | 993046 | 0 | 0 | 0 | 0 | 540638.67 | 0.5444 | 54.44 | 0.0001 | 0.5444 | -0.5444 | 0 | 99304.6 | TRUE | TRUE
2026-06-17 | 1683585 | DS.2024.1263 5188 Brighton Dr Whitestown | DW | (Unassigned) | Promasters Drywall and Painting (Brian Figueroa) | ACTIVE | 1759.2 | 0 | 1759.2 | 1882.34 | 0 | 1068.8 | 0 | 0 | -1759.2 | 0 | 1759.2 | 0 | 690.4 | 0.3925 | 100 | 0.0568 | 0 | 0 | 0 | -123.14 | FALSE | FALSE
2026-06-17 | 1669494 | 2024.912 Upland Columbus | TI | Tommy Cohoat | Bischoff Construction, LLC | ACTIVE | 116545 | 10820 | 116545 | 114525 | 73224 | 72786.47 | 0.994 | 115845.73 | -699.27 | -696.38 | 699.27 | 0 | 43758.53 | 0.3755 | 37.17 | 0.0003 | 0.3717 | -0.3714 | 0 | 2020 | TRUE | TRUE
2026-06-17 | 1658900 | DS.2024.1234 Pro Masters | DW | (Unassigned) | Promasters Drywall and Painting (Brian Figueroa) | ACTIVE | 2590.45 | 0 | 2590.45 | 2771.78 | 0 | 1898.89 | 0 | 0 | -2590.45 | 0 | 2590.45 | 0 | 691.56 | 0.267 | 100 | 0.0386 | 0 | 0 | 0 | -181.33 | FALSE | FALSE
2026-06-17 | 1607003 | MF.2024.928 Holliday Farms Assisted Living - Zionsville | MF | Ben Garza | Avenue Construction, Inc. | ACTIVE | 2731383.75 | 286258.75 | 2731383.75 | 2339017.44 | 1915724.8 | 1918484.8 | 1.0014 | 2735207.69 | 3823.94 | 0 | 0 | 3823.94 | 812898.95 | 0.2976 | 29.86 | 0 | 0.2986 | -0.2986 | 0 | 392366.31 | TRUE | TRUE
2026-06-17 | 1577552 | DS.2023.1141 Latitude Apartments | DW | (Unassigned) | Velocity Builders | ACTIVE | 844352.61 | 0 | 651215.03 | 651215.03 | 0 | 346117.87 | 0 | 0 | -651215.03 | 0 | 651215.03 | 0 | 305097.16 | 0.4685 | 100 | 0.0001 | 0 | 0 | 0 | 0 | FALSE | FALSE
2026-06-17 | 1551637 | 2023.847 Ireland Home | TI | Tommy Cohoat | Bischoff Construction, LLC | ACTIVE | 52636.92 | 19160 | 52636.92 | 52636.92 | 36345 | 40426.66 | 1.1123 | 58548.05 | 5911.13 | 0 | 0 | 5911.13 | 12210.26 | 0.232 | 30.95 | 0.0006 | 0.3095 | -0.3089 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1539188 | 2024.874 Noblesville HS Academic Addition & Renovation | TI | Trevor Anderson | The Peterson Company, LLC | ACTIVE | 154487 | -8530 | 154487 | 169451 | 200934.57 | 200934.57 | 1 | 154487 | 0 | 0 | 0 | 0 | -46447.57 | -0.3007 | -30.07 | -0.0002 | -0.3007 | 0.3005 | 0 | -14964 | TRUE | TRUE
2026-06-17 | 1536145 | MF.2023.840 Paint at 804 14th Ave Nashville | MF | Kelden Tyson | ZMX Inc. | ACTIVE | 280782.67 | 24407.67 | 280782.67 | 300524.51 | 228212.19 | 230735.13 | 1.0111 | 283899.36 | 3116.69 | 0 | 0 | 3116.69 | 50047.54 | 0.1782 | 18.72 | 0.0001 | 0.1872 | -0.1872 | 0 | -19741.84 | TRUE | TRUE
2026-06-17 | 1464707 | 2023.816 Upland Broad Ripple | TI | Tommy Cohoat | Bischoff Construction, LLC | ACTIVE | 14450 | 0 | 14450 | 14450 | 6350 | 11521.3 | 1.8144 | 26218.08 | 11768.08 | 0 | 0 | 11768.08 | 2928.7 | 0.2027 | 56.06 | 0.0039 | 0.5606 | -0.5567 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1461734 | 2023.839 Hamilton County National Guard Readiness Center | TI | Tommy Cohoat | Patterson Horth, Inc. | ACTIVE | 1538998.61 | 19111.61 | 1538998.61 | 1431787.62 | 1340800 | 1462377.28 | 1.0907 | 1678585.78 | 139587.17 | 0 | 0 | 139587.17 | 76621.33 | 0.0498 | 12.88 | 0 | 0.1288 | -0.1288 | 0 | 107210.99 | TRUE | TRUE
2026-06-17 | 1423094 | 2024.869 Prospect Lake Clean Water Center | TI | Cole Garriott | Patterson Horth, Inc. | ACTIVE | 427542 | 65378 | 427542 | 384787.8 | 279568.91 | 279568.91 | 1 | 427542 | 0 | 0 | 0 | 0 | 147973.09 | 0.3461 | 34.61 | 0.0001 | 0.3461 | -0.346 | 0 | 42754.2 | TRUE | TRUE
2026-06-17 | 1407590 | 2023.795 Upland Brewery Clay Terrace | TI | Tommy Cohoat | Bischoff Construction, LLC | ACTIVE | 101530 | 23430 | 101530 | 101530 | 41460 | 52294.94 | 1.2613 | 128059.79 | 26529.79 | 0 | 0 | 26529.79 | 49235.06 | 0.4849 | 59.16 | 0.0006 | 0.5916 | -0.5911 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1398846 | 2023.843 Walmart Frederick | TI | Cole Garriott | DEEM, LLC | ACTIVE | 2978233.94 | 839835.94 | 2978233.94 | 2978233.94 | 1743437.53 | 1743437.53 | 1 | 2978233.94 | 0 | 0 | 0 | 0 | 1234796.41 | 0.4146 | 41.46 | 0 | 0.4146 | -0.4146 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1383434 | MF.2023.785 Drywall at 804 14th Ave Nashville | MF | Kelden Tyson | ZMX Inc. | ACTIVE | 739513.88 | 58163.88 | 739513.88 | 728866.98 | 608078.16 | 610601.1 | 1.0041 | 742545.89 | 3032.01 | 0 | 0 | 3032.01 | 128912.78 | 0.1743 | 17.77 | 0 | 0.1777 | -0.1777 | 0 | 10646.9 | TRUE | TRUE
2026-06-17 | 1360035 | 2023.776 Keefe Group TI | TI | Tommy Cohoat | The Peterson Company, LLC | ACTIVE | 113525 | 0 | 113525 | 113525 | 92609.28 | 92269.93 | 0.9963 | 113104.96 | -420.04 | -415.99 | 420.04 | 0 | 21255.07 | 0.1872 | 18.42 | 0.0002 | 0.1842 | -0.1841 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1303390 | MF.2024.875 Purdue Student Housing | MF | Kelden Tyson | Marous Brothers Construction | ACTIVE | 6171928.99 | 805433.99 | 6171928.99 | 6171928.99 | 5187520.67 | 5197619.98 | 1.0019 | 6183655.66 | 11726.67 | 0 | 0 | 11726.67 | 974309.01 | 0.1579 | 15.95 | 0 | 0.1595 | -0.1595 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1161468 | 2022.690 Klarity, Mind, & Body | TI | Ted Wells | EquiTeam LLC | ACTIVE | 66336.42 | 6165 | 66336.43 | 66336.43 | 42004.23 | 36756.21 | 0.8751 | 58051 | -8285.43 | -8288.09 | 8285.43 | 0 | 29580.21 | 0.4459 | 36.68 | 0.0006 | 0.3668 | -0.3662 | -0.01 | 0 | TRUE | TRUE
2026-06-17 | 1151697 | 2023.731 Park 133 - ITS - TI Tenant Buildout | TI | Tommy Cohoat | The Peterson Company, LLC | ACTIVE | 759684 | 40783 | 759684 | 759684 | 406398 | 409683.37 | 1.0081 | 765837.44 | 6153.44 | 0 | 0 | 6153.44 | 350000.63 | 0.4607 | 46.5 | 0.0001 | 0.465 | -0.465 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1138743 | 2022.654 Upland Brewery Northside | TI | Tommy Cohoat | Seven Four Construction | ACTIVE | 175860.53 | 74360.53 | 175860.53 | 175860.53 | 139299.39 | 137342.59 | 0.986 | 173398.48 | -2462.05 | -2470.39 | 2462.05 | 0 | 38517.94 | 0.219 | 20.79 | 0.0001 | 0.2079 | -0.2078 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1138684 | MDG Office at Rucker | UN | (Unassigned) | MDG New Office | ACTIVE | 731215.63 | 216183 | 664658.63 | 664658.63 | 600 | 888658.79 | 1481.098 | 1083002007.16 | 1082337348.53 | 66557 | 0 | 1082337348.53 | -224000.16 | -0.337 | 99.92 | 0.0001 | 0.9992 | -0.999 | 0 | 0 | TRUE | FALSE
2026-06-17 | 1138659 | 2022.625 Walmart 7611 | TI | Cole Garriott | Massa Multimedia Architecture (MMA) | ACTIVE | 983441 | 306770 | 982141 | 982141 | 717571.28 | 717571.28 | 1 | 983441 | 1300 | 1300 | 0 | 1300 | 264569.72 | 0.2694 | 27.03 | 0 | 0.2703 | -0.2703 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1138651 | 2022.617 The Junction Phase II | TI | Ted Wells | EquiTeam LLC | ACTIVE | 304058.89 | 46226.67 | 304058.89 | 304058.89 | 185366 | 185366.13 | 1 | 304058.89 | 0 | 0 | 0 | 0 | 118692.76 | 0.3904 | 39.04 | 0.0001 | 0.3904 | -0.3902 | 0 | 0 | TRUE | TRUE
2026-06-17 | 1138649 | 2022.610 222 E. Ohio St. | UN | Ted Wells | Midwest Design Group - Misc | ACTIVE | 1 | 0 | 0 | 0 | 180 | 79341.07 | 440.7837 | 440.78 | 440.78 | 1 | 0 | 440.78 | -79341.07 | 0 | -100 | -100 | -179 | 79 | 0 | 0 | TRUE | FALSE
2026-06-17 | 1138478 | 2022.639 Radial TI - Avon Building 2 | TI | Tommy Cohoat | The Peterson Company, LLC | ACTIVE | 758779 | 2028 | 758779 | 758779 | 440538.37 | 514221.33 | 1.1673 | 885722.73 | 126943.73 | 0 | 0 | 126943.73 | 244557.67 | 0.3223 | 41.94 | 0.0001 | 0.4194 | -0.4194 | 0 | 0 | TRUE | TRUE

## » Fact_PL_Monthly
MonthEnd | Revenue | COGS | GrossProfit | OpEx | NetIncome | GrossMarginPct | NetMarginPct
2025-01-31 | 2041295.53 | 1705779.19 | 335516.34 | 917633.43 | -582117 | 0.1644 | -0.2852
2025-04-30 | 2424157.48 | 1668995.34 | 755162.14 | 836162.72 | -69968.27 | 0.3115 | -0.0289
2026-01-31 | 4471974.17 | 3167525.69 | 1304448.48 | 937191.25 | 186406.72 | 0.2917 | 0.0417
2026-02-28 | 4949310.29 | 3687884.25 | 1261426.04 | 794070.18 | 467881.55 | 0.2549 | 0.0945
2026-03-31 | 5290349.77 | 3616852.68 | 1673497.09 | 897079.72 | 790908.56 | 0.3163 | 0.1495
2026-04-30 | 4593904.49 | 3242912.67 | 1350991.82 | 713341.59 | 677429.81 | 0.2941 | 0.1475
2026-05-31 | 5042110.58 | 3317835.45 | 1724275.13 | 518231.9 | 1206135.01 | 0.342 | 0.2392

## » Fact_AR
Customer | Bucket | Amount | IsRetainage | AsOfDate
ACS-Affiliated Construction Services, Inc. | Current | 45416.23 | FALSE | 2026-06-17
ACS-Affiliated Construction Services, Inc. | 1-30 | 36620.15 | FALSE | 2026-06-17
ACS-Affiliated Construction Services, Inc. | 31-60 | 72880.67 | FALSE | 2026-06-17
ACS-Affiliated Construction Services, Inc. | 91+ | 144737.82 | FALSE | 2026-06-17
Arbor Homes | Current | 112439.58 | FALSE | 2026-06-17
Arbor Homes | 61-90 | 20386.58 | FALSE | 2026-06-17
Arbor Homes | 91+ | -12094.76 | FALSE | 2026-06-17
ARCO Design/Build | Current | 385369.33 | FALSE | 2026-06-17
ARCO Design/Build | 1-30 | 26117.77 | FALSE | 2026-06-17
ARCO Design/Build | 31-60 | 73818 | FALSE | 2026-06-17
ARCO Design/Build | 91+ | 22752 | FALSE | 2026-06-17
Avenue Construction, Inc. | Current | 387512.38 | FALSE | 2026-06-17
Avenue Construction, Inc. | 31-60 | 66047.2 | FALSE | 2026-06-17
Becknell Industries | Current | 13100 | FALSE | 2026-06-17
Becknell Industries | 91+ | 2500 | FALSE | 2026-06-17
Big Dawg Drywall | 1-30 | 5928.42 | FALSE | 2026-06-17
Big Dawg Drywall | 91+ | 7365.93 | FALSE | 2026-06-17
Bischoff Construction, LLC | Current | 4020 | FALSE | 2026-06-17
BW Facility Management, LLC | Current | 34444.01 | FALSE | 2026-06-17
Cargo Loop, LLC | Current | 10417 | FALSE | 2026-06-17
Centric Projects, LLC | Current | 174505.69 | FALSE | 2026-06-17
Centric Projects, LLC | 1-30 | 77705.72 | FALSE | 2026-06-17
Clark Construction | Current | 889172 | FALSE | 2026-06-17
Clark Construction | 1-30 | 129947 | FALSE | 2026-06-17
Community Drywall | 91+ | 13844.41 | FALSE | 2026-06-17
Compass Commercial Construction Group | Current | 352621.67 | FALSE | 2026-06-17
Compass Commercial Construction Group | 31-60 | 68841.54 | FALSE | 2026-06-17
Convivio Italian Artisan Cuisine (SPIGA Noblesville) | Current | 2555.2 | FALSE | 2026-06-17
Cornerstone Flooring | 61-90 | 7500 | FALSE | 2026-06-17
County Prestress & Precast, LLC | Current | 30500 | FALSE | 2026-06-17
County Prestress & Precast, LLC | 31-60 | 22000 | FALSE | 2026-06-17
Daniel T Swanson | 1-30 | 16000 | FALSE | 2026-06-17
DEEM, LLC | Current | 61895.38 | FALSE | 2026-06-17
DEEM, LLC | 1-30 | 2000 | FALSE | 2026-06-17
DEEM, LLC | 31-60 | 4225.5 | FALSE | 2026-06-17
DEEM, LLC | 61-90 | 28757.01 | FALSE | 2026-06-17
DEEM, LLC | 91+ | 5000.03 | FALSE | 2026-06-17
Diaz Gutter and Drywall, LLC | 91+ | 2399.42 | FALSE | 2026-06-17
DLR Group | 31-60 | 4500 | FALSE | 2026-06-17
Enviro-Max | 61-90 | 3500 | FALSE | 2026-06-17
Flores Drywall and Remodeling LLC | Current | 91048.9 | FALSE | 2026-06-17
Flores Drywall and Remodeling LLC | 1-30 | 15112.12 | FALSE | 2026-06-17
Forge Construction, LLC | Current | 3600 | FALSE | 2026-06-17
Garmong Construction Services | Current | 141648.31 | FALSE | 2026-06-17
Garmong Construction Services | 1-30 | 236453.93 | FALSE | 2026-06-17
GSI - Gregory Scott Inabnit LLC | 91+ | 52867.87 | FALSE | 2026-06-17
Holladay Construction Group | Current | 202650.67 | FALSE | 2026-06-17
Holladay Construction Group | 1-30 | 82260 | FALSE | 2026-06-17
Indianapolis Fire Department | 91+ | 768.35 | FALSE | 2026-06-17
Indiana Steel Fabricating | Current | 8000 | FALSE | 2026-06-17
J.C. Hart Company, Inc. | Current | 96132.92 | FALSE | 2026-06-17
J.C. Hart Company, Inc. | 1-30 | 63353.47 | FALSE | 2026-06-17
JRA Architecture, LLC | 1-30 | 6000 | FALSE | 2026-06-17
Kjt General Construction | 61-90 | 2072.89 | FALSE | 2026-06-17
Kjt General Construction | 91+ | 26152.31 | FALSE | 2026-06-17
Lauth Group, Inc. | 91+ | 5000 | FALSE | 2026-06-17
Marous Brothers Construction | Current | 119746.42 | FALSE | 2026-06-17
Marous Brothers Construction | 1-30 | 435716.98 | FALSE | 2026-06-17
Marous Brothers Construction | 31-60 | 0.01 | FALSE | 2026-06-17
MDG Holdings, LLC | 91+ | 4708.82 | FALSE | 2026-06-17
Meyer Najem | Current | 6267.5 | FALSE | 2026-06-17
Meyer Najem | 61-90 | 26925.21 | FALSE | 2026-06-17
Meyer Najem | 91+ | 188023.46 | FALSE | 2026-06-17
Michael Valentine | 91+ | 12430.13 | FALSE | 2026-06-17
MILHAUS Construction | Current | 509895 | FALSE | 2026-06-17
MILHAUS Construction | 1-30 | 206955 | FALSE | 2026-06-17
MILHAUS Construction | 31-60 | 510367.5 | FALSE | 2026-06-17
MILHAUS Construction | 61-90 | 256635 | FALSE | 2026-06-17
Mitsch Design | 91+ | 19000 | FALSE | 2026-06-17
Novo Development Group, LLC | Current | 60165.16 | FALSE | 2026-06-17
Novo Development Group, LLC | 31-60 | -1973.34 | FALSE | 2026-06-17
Old Town Construction | Current | 352057.58 | FALSE | 2026-06-17
Old Town Construction | 31-60 | 407993.89 | FALSE | 2026-06-17
Patch Development | Current | 15211.87 | FALSE | 2026-06-17
Patch Development | 1-30 | 44532.3 | FALSE | 2026-06-17
Patch Development | 31-60 | 1350 | FALSE | 2026-06-17
Patch Development | 91+ | 39000 | FALSE | 2026-06-17
Patterson Horth, Inc. | 91+ | 143724.99 | FALSE | 2026-06-17
Precision Dry Wall | Current | 26295.22 | FALSE | 2026-06-17
Precision Dry Wall | 1-30 | 16327.53 | FALSE | 2026-06-17
Priority Constructors | 91+ | 720.06 | FALSE | 2026-06-17
Pro Fix Drywaller, LLC | 91+ | 22972.34 | FALSE | 2026-06-17
Shiel Sexton | Current | 24028.81 | FALSE | 2026-06-17
Shiel Sexton | 31-60 | 248464.3 | FALSE | 2026-06-17
Skender Construction of Indiana LLC | Current | 647564.65 | FALSE | 2026-06-17
Skender Construction of Indiana LLC | 1-30 | 708983.51 | FALSE | 2026-06-17
Skender Construction of Indiana LLC | 31-60 | 134622.54 | FALSE | 2026-06-17
Skender Construction of Indiana LLC | 61-90 | 111708.94 | FALSE | 2026-06-17
Skender Construction of Indiana LLC | 91+ | 46273.32 | FALSE | 2026-06-17
Stenz Corp | Current | 9190.37 | FALSE | 2026-06-17
Stenz Corp | 1-30 | 9000 | FALSE | 2026-06-17
Stenz Corp | 31-60 | 36934.63 | FALSE | 2026-06-17
Stenz Corp | 61-90 | 18000 | FALSE | 2026-06-17
The ACTS Collaborative, LLC | Current | 28129.5 | FALSE | 2026-06-17
The Home Depot, Inc. | 91+ | 585.54 | FALSE | 2026-06-17
The Peterson Company, LLC | Current | 1164329.53 | FALSE | 2026-06-17
The Peterson Company, LLC | 1-30 | 54936.18 | FALSE | 2026-06-17
The Peterson Company, LLC | 31-60 | 702311.21 | FALSE | 2026-06-17
Thompson Thrift Construction | Current | 569642.4 | FALSE | 2026-06-17
Thompson Thrift Construction | 1-30 | 571623.75 | FALSE | 2026-06-17
Thompson Thrift Construction | 91+ | 51060 | FALSE | 2026-06-17
Total Drywall Solutions Inc | 91+ | 4485.21 | FALSE | 2026-06-17
Yaggi's White Glove Delivery, LLC | 91+ | 18935.33 | FALSE | 2026-06-17
ZMX Inc. | 91+ | 10646.9 | FALSE | 2026-06-17
(Retainage Receivable) | Retainage | 3136194.46 | TRUE | 2026-06-17

## » Fact_AP
Vendor | Bucket | Amount | AsOfDate
4BRO Construction LLC | Current | 8825.79 | 2026-06-17
6twenty-six inc | Current | 1337.5 | 2026-06-17
7R Lawn Solutions, LLC | 1-30 | 836 | 2026-06-17
84 Lumber | 91+ | -1222.78 | 2026-06-17
ABC Supply Interiors, Inc. (L&W) | Current | 18002.12 | 2026-06-17
ABC Supply Interiors, Inc. (L&W) | 91+ | -3711.8 | 2026-06-17
ABM Parking Services | Current | 180 | 2026-06-17
ADL Design & Construction LLC | 91+ | 6316.5 | 2026-06-17
Alejandro Gonzalez-Rubio | Current | 1650 | 2026-06-17
ARC Document Solutions, LLC | Current | 259.57 | 2026-06-17
Armstrong World Industries, Inc. | 91+ | -150.69 | 2026-06-17
AZS General Construction Corp | Current | 39860.36 | 2026-06-17
AZS General Construction Corp | 1-30 | 6800 | 2026-06-17
AZS General Construction Corp | 31-60 | 6663.8 | 2026-06-17
AZS General Construction Corp | 61-90 | 2568.19 | 2026-06-17
AZS General Construction Corp | 91+ | 7604.3 | 2026-06-17
BA Construction Remodeling LLC | Current | 12443 | 2026-06-17
Barahona Painting LLC | Current | 10397.46 | 2026-06-17
Best Way of Indiana, Inc. | Current | 2408.11 | 2026-06-17
Bro's Drywall LLC | Current | 7732 | 2026-06-17
Bro's Drywall LLC | 31-60 | 48 | 2026-06-17
Bro's Drywall LLC | 91+ | 24 | 2026-06-17
Brother's Carpentry (Gustavo Gutierrez) | Current | 145.05 | 2026-06-17
Brother's Carpentry (Gustavo Gutierrez) | 91+ | 652 | 2026-06-17
Browning Chapman, LLC | Current | 2550 | 2026-06-17
Castillo (Victor) Drywall & Scrap LLC | Current | 2471.9 | 2026-06-17
C&C Martinez Drywall LLC | Current | 38293.86 | 2026-06-17
C&C Martinez Drywall LLC | 61-90 | 3310.96 | 2026-06-17
C&C Martinez Drywall LLC | 91+ | 1305.46 | 2026-06-17
Central Indiana Hardware (CIH) | Current | 2952.13 | 2026-06-17
Cherokee Building Materials, Inc. (GMS) | 91+ | -627.67 | 2026-06-17
Chris Taylor | Current | 250 | 2026-06-17
Concentra | 61-90 | 125 | 2026-06-17
Construction Specialties, Inc. | Current | 2754.18 | 2026-06-17
CraneWorks ¦ CW Intermediate Holdco, LLC | Current | 789.4 | 2026-06-17
Deem | Current | 3325 | 2026-06-17
DIVISION 7 MTLS | Current | 1525.82 | 2026-06-17
Enterprise Rent a Car | Current | 227.01 | 2026-06-17
Escot Painting LLC | 61-90 | 7700 | 2026-06-17
Foundation Building Materials (FBM) | Current | 832567.56 | 2026-06-17
Foundation Building Materials (FBM) | 31-60 | -620.94 | 2026-06-17
Foundation Building Materials (FBM) | 91+ | -2979.13 | 2026-06-17
Garners Towing & Transport | 61-90 | 312.5 | 2026-06-17
Garza Towing LLC | 1-30 | 875 | 2026-06-17
Gauge Telematics, Inc | Current | 345 | 2026-06-17
GTO Drywall & Metal Framing LLC | Current | 3325.4 | 2026-06-17
GTO Drywall & Metal Framing LLC | 1-30 | 6089.4 | 2026-06-17
GTZ Builders, LLC (Paulo) | Current | 30842.4 | 2026-06-17
Haines, Jones, & Cadbury, LLC | Current | 18675.29 | 2026-06-17
Hilti | Current | 2689.56 | 2026-06-17
Home Depot | Current | 71539.66 | 2026-06-17
Home Depot (HD Pro) | Current | 739119.02 | 2026-06-17
Indianapolis Propane Exchange LLC | Current | 583.14 | 2026-06-17
Indy Crush Brothers, LLC (Indy Crusher) | 91+ | 10.8 | 2026-06-17
Indy Pro Painters Services, LLC | Current | 11669.8 | 2026-06-17
Indy Pro Painters Services, LLC | 31-60 | 1800 | 2026-06-17
Indy Pro Painters Services, LLC | 61-90 | 3822.5 | 2026-06-17
Indy Pro Painters Services, LLC | 91+ | 9740 | 2026-06-17
Interior Product Supply (IPS) GMS Co (Cherokee BM) | Current | 9710.52 | 2026-06-17
Interior Supply Inc (ISI) | Current | 129139.47 | 2026-06-17
Interior Supply Inc (ISI) | 31-60 | 13.37 | 2026-06-17
Internal Drywall Division | Current | 113560.43 | 2026-06-17
Iracheta Drywall LLC | Current | 25249.02 | 2026-06-17
Iracheta Drywall LLC | 91+ | 1972.98 | 2026-06-17
JC Drywall LLC (JCD) | Current | 70 | 2026-06-17
JC Drywall LLC (JCD) | 91+ | 3077.1 | 2026-06-17
Jordan Birge | Current | 2764.19 | 2026-06-17
Jose Antonio Gallegos Alvarez | Current | 54757.04 | 2026-06-17
Jose Antonio Gallegos Alvarez | 1-30 | 1260 | 2026-06-17
Jose Antonio Gallegos Alvarez | 31-60 | 1962.2 | 2026-06-17
Jose Antonio Gallegos Alvarez | 61-90 | 6076.3 | 2026-06-17
Jose Antonio Gallegos Alvarez | 91+ | 7185.34 | 2026-06-17
JR Woodworks and Custom Cabinets LLC | Current | 6010 | 2026-06-17
JR Woodworks and Custom Cabinets LLC | 1-30 | 3890 | 2026-06-17
Julio Juarez (Expenses) | Current | 400 | 2026-06-17
Kelley Bros Hardware Corp | 91+ | -369.15 | 2026-06-17
Kjt General Construction LLC (V) | Current | 8971.91 | 2026-06-17
Lanmor Services | Current | 2945.15 | 2026-06-17
LH Industrial | Current | 20346.53 | 2026-06-17
LH Industrial | 61-90 | -117.52 | 2026-06-17
Lion's Construction LLC | Current | 3942.55 | 2026-06-17
Lion's Construction LLC | 91+ | 617.1 | 2026-06-17
LL Herrera LLC | Current | 3056.61 | 2026-06-17
Lot Construction, LLC (Omar) | Current | 1858.7 | 2026-06-17
Lot Construction, LLC (Omar) | 31-60 | 1293.6 | 2026-06-17
Lowe's | Current | 303594.49 | 2026-06-17
Lowe's | 1-30 | 14199.9 | 2026-06-17
Lowe's | 31-60 | 20320.44 | 2026-06-17
Lowe's | 91+ | 76.41 | 2026-06-17
Luis Ruiz (Expenses) | 1-30 | 100 | 2026-06-17
MacAllister Rentals (R) | Current | 47500.09 | 2026-06-17
MacAllister Rentals (R) | 91+ | -133.75 | 2026-06-17
Mariona Construction LLC | Current | 5328.35 | 2026-06-17
Mendoza Construction LLC (V) | Current | 146738.27 | 2026-06-17
Mendoza Construction LLC (V) | 1-30 | 3000 | 2026-06-17
Mendoza Construction LLC (V) | 31-60 | 3736.5 | 2026-06-17
Mendoza Construction LLC (V) | 91+ | 9485.38 | 2026-06-17
Mendoza Innovations, LLC | 1-30 | 46637.84 | 2026-06-17
Mirabito Energy Products | Current | 110.13 | 2026-06-17
Mirabito Energy Products | 1-30 | 100.84 | 2026-06-17
Miracle Painting LLC - Jose Otoya | Current | 3054.15 | 2026-06-17
Nemix Painting & Construction LLC | Current | 60338.96 | 2026-06-17
Nemix Painting & Construction LLC | 1-30 | 1985.5 | 2026-06-17
Nemix Painting & Construction LLC | 61-90 | 11248.05 | 2026-06-17
Nemix Painting & Construction LLC | 91+ | 8485.76 | 2026-06-17
Oaks Dumpster Rental | Current | 960.22 | 2026-06-17
Ociel Medina (Gem Interiors) | Current | 6101.04 | 2026-06-17
Oliverio Mejia H, LLC | Current | 2821.6 | 2026-06-17
Oliverio Mejia H, LLC | 1-30 | 2385 | 2026-06-17
On-Site Supply | Current | 1143.4 | 2026-06-17
Osorio Construction LLC (Rene) | Current | 8015 | 2026-06-17
Pomp's Tire Service, Inc. | Current | 383.71 | 2026-06-17
Precise Tile and Stone LLC | Current | 3099.87 | 2026-06-17
Precision Doors & Hardware | 91+ | 6000 | 2026-06-17
Prime Drywall Services LLC | Current | 92882.96 | 2026-06-17
Prime Drywall Services LLC | 31-60 | 3000 | 2026-06-17
Prime Drywall Services LLC | 61-90 | 404.64 | 2026-06-17
Prime Drywall Services LLC | 91+ | 3200.56 | 2026-06-17
Professional Handling and Distribution | Current | 8356.22 | 2026-06-17
ProMasters Drywall & Painting | 1-30 | 1770 | 2026-06-17
Reliable Access LLC | 1-30 | 275 | 2026-06-17
RGT Construction LLC | 91+ | 346.5 | 2026-06-17
Riteway Tool & Fasteners | Current | 17855.06 | 2026-06-17
Riteway Tool & Fasteners | 91+ | -44.73 | 2026-06-17
RWR 504 Construction LLC | Current | 2280 | 2026-06-17
Sandra Yanett Ayala LLC | Current | 5476.52 | 2026-06-17
Sandra Yanett Ayala LLC | 31-60 | 2668.78 | 2026-06-17
Sandra Yanett Ayala LLC | 61-90 | 7456.06 | 2026-06-17
Saravia Drywall, LLC | Current | 11280 | 2026-06-17
Shaevitz Construction Inc. | Current | 2277.46 | 2026-06-17
Sherwin Williams | Current | 203177.5 | 2026-06-17
Sherwin Williams | 1-30 | 1839.06 | 2026-06-17
Sherwin Williams | 31-60 | -10.27 | 2026-06-17
Sherwin Williams | 61-90 | -486.97 | 2026-06-17
Sherwin Williams | 91+ | -494.67 | 2026-06-17
Southwest Solutions Group, Inc. | Current | 1080 | 2026-06-17
Sunbelt Rentals Inc. | Current | 1907.34 | 2026-06-17
The Best Tile Installation (Nagio Company LLC) | Current | 833.75 | 2026-06-17
Top Team Quality Building LLC | Current | 5378.2 | 2026-06-17
Top Team Quality Building LLC | 31-60 | 819.2 | 2026-06-17
United (GMS)/Cherokee Building Materials | Current | 177526.44 | 2026-06-17
United Rentals Inc. | Current | 50995.72 | 2026-06-17
Valley Interior Products (GMS) | Current | 302.7 | 2026-06-17
Valley Interior Products (GMS) | 91+ | -1141.64 | 2026-06-17
Victor Garza (Expenses) | 31-60 | 165.68 | 2026-06-17
White Cap, L.P. | Current | 467.79 | 2026-06-17

## » Fact_Cash
Date | CashBalance | LOCDrawn | LOCCapX | OperatingCF | InvestingCF | FinancingCF | NetCashChange | LOCLimit | AdvanceRate | EligibleAR
2026-06-17 | -54623.3 | 5440076.95 | 333834.01 | 1708994.16 | 212852.1 | -1650418.17 | 271428.09 | 8000000 | 0.8 | 12986875.87

## » Fact_Budget
DivKey | Period | ContractTotal | BudgetTotal | ActualCost | Invoiced
DW | Active | 2247021.73 | 0 | 1384395.09 | 2037196.92
MF | Active | 41385804.97 | 28976033.19 | 18096438.15 | 22703258.15
TI | Active | 23623992.86 | 14432142.97 | 13561203.47 | 20986986.32
UN | Active | 1481553.28 | 414032 | 1412587.72 | 1123244.28

## » Fact_BalanceSheet
Account | Section | Amount | AsOfDate
Cash | Assets | -54623.3 | 2026-06-17
Accounts Receivable | Assets | 12986875.87 | 2026-06-17
Retainage Receivable | Assets | 3136194.46 | 2026-06-17
Drywall Inventory | Assets | 593395.59 | 2026-06-17
WIP Underbillings | Assets | 2889941.58 | 2026-06-17
Other Current Assets (net) | Assets | 82113.84 | 2026-06-17
Fixed Assets | Assets | 694113.61 | 2026-06-17
Other Assets | Assets | 2223043.34 | 2026-06-17
Accounts Payable | Liabilities | 3655333.94 | 2026-06-17
Credit Cards | Liabilities | 15836.29 | 2026-06-17
Line of Credit (Forum 0874) | Liabilities | 5440076.95 | 2026-06-17
CapX Line of Credit (Forum 1708) | Liabilities | 333834.01 | 2026-06-17
WIP Overbillings | Liabilities | 1651664.83 | 2026-06-17
Other Current Liabilities (net) | Liabilities | 2747267.42 | 2026-06-17
Long-term Liabilities | Liabilities | 8372.29 | 2026-06-17
Total Equity | Equity | 8698669.26 | 2026-06-17

## » Dim_Job
Job | ProjectId | DivKey | PMName | Customer | Status | ContractType | City | State | DateActive | StartDate | EndDate
DS.2026.2440 Liberty Assisted Living 0612 | 2902164 | UN | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-06-16 | 2026-06-12
2026.1059 Westfield Community Schools | 2894730 | UN | Dustin Hurt | LTB Construction, Inc. | ACTIVE | FIXED_PRICE |  |  | 2026-06-11 | 2026-06-15
2026.1058 Patch McCordsville Building 1 | 2893583 | UN | Spencer Anderson | Patch Development | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | McCordsville | IN | 2026-06-11
DS.2026.2439 2335 Treesdale Circle | 2889499 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-06-09 | 2026-06-08
DS.2026.2438 10806 McPherson St | 2888259 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-06-09 | 2026-06-04
DS.2026.2437 970 Starkey Ave | 2888192 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-06-09 | 2026-06-03
MDG Warehouse Demising Wall | 2887165 | UN | (Unassigned) | MDG Real Estate LLC | ACTIVE | FIXED_PRICE | Noblesville | IN | 2026-06-08 | 2026-06-08
DS.2026.2436 25 Harper Estates | 2887151 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-06-08 | 2026-06-01
DS.2026.2435 21 Harper Estates | 2887141 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-06-08 | 2026-06-01
DS.2026.2434 19 Harper Estates | 2887107 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-06-08 | 2026-06-01
DS.2026.2433 Liberty Assisted Living 0529 | 2872036 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-06-01 | 2026-05-29
DS.2026.2432 Liberty Assisted LIving 0528 | 2872017 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-06-01 | 2026-05-28
DS.2026.2431 123 Centre Place | 2872004 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-06-01 | 2026-05-28
DS.2026.2430 119 Centre Place | 2871958 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-06-01 | 2026-05-28
DS.2026.2429 108 Centre Place | 2871926 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-06-01 | 2026-05-28
DS.2026.2428 9 Centre Place | 2871859 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-06-01 | 2026-05-28
DS.2026.2427 Dapp Garage | 2863766 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-05-27 | 2026-05-26
DS.2026.2426 121 Centre Place | 2863755 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-05-27 | 2026-05-22
DS.2026.2425 14 Parks | 2863752 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-05-27 | 2026-05-22
DS.2026.2424 10566 Coppergate | 2863728 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-05-27 | 2026-05-22
DS.2026.2423 10816 McPherson St | 2863715 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-05-27 | 2026-05-21
DS.2026.2422 10814 McPherson St | 2863703 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-05-27 | 2026-05-21
DS.2026.2421 Flores Ohio Job | 2863678 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-05-27 | 2026-05-20
DS.2026.2420 7508 Central Ave | 2852408 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-05-20 | 2026-05-18
DS.2026.2419 120 Centre Place | 2852375 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-05-20 | 2026-05-14
DS.2026.2418 118 Centre Place | 2844284 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-05-15 | 2026-05-13
DS.2026.2417 117 Centre Place | 2844272 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-05-15 | 2026-05-13
DS.2026.2416 52 Centre Place | 2844253 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-05-15 | 2026-05-13
DS.2026.2415 10826 McPherson St | 2844241 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-05-15 | 2026-05-15
DS.2026.2414 10824 McPherson St | 2844222 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-05-15 | 2026-05-13
DS.2026.2413 Precision Pickup 0501 | 2834059 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-05-11 | 2026-05-01
DS.2026.2412 10732 Heaven Cove Way | 2834016 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-05-11 | 2026-05-05
DS.2026.2411 Clark Remodel | 2818141 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-05-01 | 2026-04-30
2026.1053 Lot 32 Vacant TI | 2803284 | TI | Spencer Anderson | Holladay Construction Group | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Indianapolis | IN | 2026-05-06 | 2026-05-20 | 2026-07-16
DS.2026.2410 Courtyards of Russell Oaks 113 | 2796562 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-04-21 | 2026-04-17
DS.2026.2409 Precision Pickup 0410 | 2796526 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  |  | 2026-04-21 | 2026-04-10
DS.2026.2408 Courtyards of Westfield 107 | 2782708 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  |  | 2026-04-14 | 2026-04-13
DS.2026.2407 Courtyards of Russel Oaks 126 | 2782668 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-04-14 | 2026-04-08
DS.2026.2406 Premier Custom Homes Quote | 2763556 | UN | (Unassigned) | Premier Custom Homes | ACTIVE | FIXED_PRICE |  |  | 2026-04-09 | 2026-04-06
DS.2026.2405 21569 Anchor Bay Drive | 2762554 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-04-03 | 2026-04-03
2026.1051 Park 130 Building 8 | 2761732 | TI | Spencer Anderson | The Peterson Company, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Lebanon | IN | 2026-05-06 | 2026-08-01 | 2026-11-01
DS.2026.2404 Flores Sandhu Res | 2759560 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-04-02 | 2026-03-31
DS.2026.2403 Big Dawg Pickup 0327 | 2750306 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  |  | 2026-03-30 | 2026-03-27
DS.2026.2402 Courtyards of Cielo Ranch 17 | 2750278 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-03-30 | 2026-03-27
DS.2026.2401 Flores Kenneland | 2750126 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-03-30 | 2026-03-20 | 2026-03-20
DS.2026.2400 Courtyards of Russell Oaks 115 | 2733362 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-03-20 | 2026-03-19
DS.2026.2399 Courtyards of Russell Oaks 74 | 2733343 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-03-20 | 2026-03-19
DS.2026.2398 Courtyards of Ceilo Ranch 26 | 2733326 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-03-20 | 2026-03-18
2026.1047 Springdale Building 4 Demising Walls | 2726249 | TI | Tommy Cohoat | The Peterson Company, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Springdale | OH | 2026-04-29 | 2026-04-23 | 2026-05-29
DS.2026.2397 Courtyards of Cielo Ranch 26 | 2726122 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-03-17 | 2026-03-13
2026.1046 Automatic Distributors (Park 130 Bldg 6) | 2715709 | TI | Cole Garriott | The Peterson Company, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Whitestown | IN | 2026-03-18 | 2026-04-06 | 2026-06-30
2026.1045 First OnSite (Ameriplex) | 2712233 | TI | Spencer Anderson | Holladay Construction Group | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Indianapolis | IN | 2026-03-13 | 2026-03-17
DS.2026.2396 6252 West Turtle Hill Ct | 2703041 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-03-05 | 2026-03-03
DS.2026.2395 Courtyards of Westfield 103 | 2702940 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-03-05 | 2026-03-03
2026.1043 Deer Creek Building 1 | 2701256 | TI | Tommy Cohoat | Patch Development | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Noblesville | IN | 2026-03-10 | 2026-03-09
DS.2026.2394 5778 Marvie Drive | 2686749 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-02-25 | 2026-02-24
DS.2026.2393 Precision Pickup 0216 | 2684477 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-02-24 | 2026-02-16
2026.1056 Senator Banks Office | 2681998 | TI | Dustin Hurt | BW Facility Management, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Fishers | IN | 2026-05-08 | 2026-05-08 | 2026-07-08
DS.2026.2392 3705 Holiday Farms Blvd - Precision | 2676832 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-02-19 | 2026-02-18
DS.2026.2391 0218 Jose Iracheta | 2676780 | UN | (Unassigned) | Kjt General Construction | ACTIVE | FIXED_PRICE |  | IN | 2026-02-19 | 2026-02-18
DS.2026.2390 510 W Pine St | 2676758 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-02-19 | 2026-02-10
DS.2026.2389 Courtyards of Russell Oaks 145 | 2675379 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-02-19 | 2026-02-17
DS.2026.2388 Courtyards of Cielo Ranch 13 | 2675217 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-02-19 | 2026-02-10
DS.2026.2387 0204 Jose Irachetta | 2665957 | UN | (Unassigned) | Kjt General Construction | ACTIVE | FIXED_PRICE |  |  | 2026-02-13 | 2026-02-04
2026.1041 Whiteland Building 2 - Blackhawk | 2656341 | TI | Spencer Anderson | Patch Development | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Whiteland | IN | 2026-02-10 | 2026-03-30 | 2026-04-30
2026.1040 Lakeside Books | 2653588 | TI | Trevor Anderson | The Peterson Company, LLC | ACTIVE | FIXED_PRICE | Avon | IN | 2026-05-11 | 2026-02-07
DS.2026.2386 Courtyards of Russell Oaks 125 | 2653377 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-02-06 | 2026-02-05
DS.2026.2385 Courtyards of Russell Oaks 123 | 2653351 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-02-06 | 2026-02-05
DS.2026.2384 225 N St Ave | 2653309 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-02-06 | 2026-02-04
2026.1039 Upland Prospect Street | 2652271 | TI | Tommy Cohoat | Bischoff Construction, LLC | ACTIVE | FIXED_PRICE | Indianapolis | IN | 2026-02-06 | 2026-02-02 | 2026-02-20
DS.2026.2383 Courtyards of Cielo Ranch 37 | 2645199 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-02-03 | 2026-02-02
DS.2026.2382 Cohoat House | 2645179 | DW | (Unassigned) | Mendoza | ACTIVE | FIXED_PRICE |  | IN | 2026-02-03 | 2026-02-02
2026.1037 CV - Castle Rock | 2644918 | TI | Ben Garza | Bischoff Construction, LLC | ACTIVE | FIXED_PRICE | Castle Rock | CO | 2026-02-05 | 2026-02-02
2026.1036 Port Laredo Trade Center | 2644454 | TI | Ben Garza | ARCO Design/Build | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Laredo | TX | 2026-02-03 | 2026-02-05
DS.2026.2381 Hunt Addition | 2640941 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-02-02 | 2026-01-30
DS.2026.2380 Mike Valentine 0129 | 2637503 | DW | (Unassigned) | Michael Valentine | ACTIVE | FIXED_PRICE |  |  | 2026-01-29 | 2026-01-29
DS.2026.2379 124 S A Street | 2637443 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-01-29 | 2026-01-29
DS.2026.2378 Courtyards of Westfield 108 | 2637384 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-01-29 | 2026-01-29
DS.2026.2377 Courtyards of Cielo Ranch 38 | 2637358 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-01-29 | 2026-01-28
DS.2026.2376 5724 E Southport Rd | 2637329 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-01-29 | 2026-01-27
DS.2026.2375 1802 Alabama St | 2637311 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | FIXED_PRICE |  |  | 2026-01-29 | 2026-01-27
DS.2026.2374 Precision Pickup 0127 | 2636260 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-01-29 | 2026-01-27
DS.2026.2373 Precision Pickup 0120 | 2623919 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-01-22 | 2026-01-20
DS.2026.2372 Big Dawg Pickup 0115 | 2623903 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-01-22 | 2026-01-22
DS.2026.2371 13429 E 116th St | 2623826 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2026-01-22 | 2026-01-21
DS.2026.2370 Courtyards of Westfield 106 | 2623802 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-01-22 | 2026-01-22
DS.2026.2369 Courtyards of Westfield 111 | 2623780 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-01-22 | 2026-01-19
DS.2026.2368 Courtyards of Russell Oaks 60 | 2612889 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-01-16 | 2026-01-12
DS.2026.2367 Courtyards of Russell Oaks 126 | 2607541 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  |  | 2026-01-14 | 2026-01-12
DS.2026.2366 Courtyards of Cielo Ranch 15 | 2601418 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-01-12 | 2026-01-08
DS.2026.2365 GSI Sackstedor Bloomington | 2594757 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  |  | 2026-01-07 | 2026-01-06
DS.2026.2364 GSI 1-6 | 2594626 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2026-01-07 | 2026-01-06
DS.2026.2363 Courtyards of Westfield 96 | 2594581 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-01-07 | 2026-01-05
DS.2026.2362 Courtyards of Russel Oaks 127 | 2589539 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2026-01-05 | 2026-01-02
2026.1033 Avon Demising Wall | 2586526 | TI | Ben Garza | The Peterson Company, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Avon | IN | 2026-02-24 | 2026-03-02
DS.2025.2361 Courtyards of Westfield 104 | 2585536 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  |  | 2025-12-31 | 2025-12-31
DS.2025.2360 GSI Duplex Bloomington | 2584758 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-12-31 | 2025-12-29
DS.2025.2359 Courtyards of Westfield 105 | 2584752 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-12-31 | 2025-12-30
DS.2025.2358 Courtyards of Cielo Ranch 7 | 2584749 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-12-31 | 2025-12-24
DS.2025.2357 3704 South Whetstine Rd | 2584742 | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | FIXED_PRICE |  | IN | 2025-12-31 | 2025-12-23
Priority Way Office | 2579439 | UN | (Unassigned) | MDG Real Estate LLC | ACTIVE | FIXED_PRICE | Indianapolis | IN | 2026-03-09 | 2025-12-22 | 2026-03-31
DS.2025.2356 Courtyards of Ceilo Ranch 127 | 2579268 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-12-23 | 2025-12-22
DS.2025.2355 Courtyards of Ceilo Ranch 36 | 2579242 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-12-23 | 2025-12-22
DS.2025.2354 GSI Triplex | 2575648 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-12-19 | 2025-12-11
DS.2025.2353 Courtyards of Westfield 95 | 2575437 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  |  | 2025-12-19 | 2025-12-16
DS.2025.2352 Charlstown Manor Lot 86 | 2569388 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-12-16 | 2025-12-15
DS.2025.2351 Courtyards of Cielo Ranch 1 | 2569308 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-12-16 | 2025-12-15
DS.2025.2350 Courtyards of Westfield 95 | 2563362 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-12-12 | 2025-12-11
DS.2025.2349 208 N Washington Street | 2563168 | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | FIXED_PRICE |  | IN | 2025-12-18 | 2025-12-10
DS.2025.2348 133 First Ave NE | 2560326 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2025-12-10 | 2025-12-09
DS.2025.2347 807 Spruce St | 2560223 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | FIXED_PRICE |  |  | 2025-12-10 | 2025-12-09
DS.2025.2346 Jeff West House | 2552755 | DW | (Unassigned) | Jeff West Homes | ACTIVE | FIXED_PRICE |  | IN | 2025-12-05 | 2025-12-04
DS.2025.2345 S & W Homes | 2552722 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-12-05 | 2025-12-04
DS.2025.2344 Courtyards of Russel Okas 119 | 2552670 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-12-05 | 2025-12-03
DS.2025.2343 Big Dawg Pickup 12-4 | 2552143 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  |  | 2025-12-05 | 2025-12-04
DS.2025.2342 Courtyards of Westfield 116 | 2548777 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-12-03 | 2025-12-02
DS.2025.2341 8677 Bash St | 2548714 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-12-03 | 2025-12-01
DS.2025.2340 1573 Chatham Drive | 2545375 | DW | (Unassigned) | Iracheta Drywall | ACTIVE | FIXED_PRICE |  |  | 2025-12-02 | 2025-11-18
2025.1028 Northpoint | 2545100 | TI | Trevor Anderson | Patch Development | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Westfield | IN | 2025-12-29 | 2025-12-22
MF.2026.1044 Everstead Apartments | 2541102 | MF | Ben Garza | Grand Contracting | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Whitestown | IN | 2026-04-29 | 2026-05-04
2025.1026 HNTB Buildout (Salesforce Tower) | 2541097 | TI | Ben Garza | Skender Construction of Indiana LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Indianapolis | IN | 2025-12-08 | 2025-12-08 | 2026-05-15
2026.1034 Stella's Ice Cream Shop | 2541065 | TI | Shawn Welcher | The ACTS Collaborative, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Westfield | IN | 2026-02-27 | 2026-02-20
DS.2025.2339 1952 N Central Ave | 2540055 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-11-26 | 2025-11-26
DS.2025.2338 7655 W Julia Drive | 2538950 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-11-25 | 2025-11-24
DS.2025.2337 Courtyards of Cielo Ranch 7 | 2538818 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-11-25 | 2025-11-24
DS.2025.2336 Courtyards of Cielo Ranch 24 | 2538718 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-11-25 | 2025-11-24
DS.2025.2335 Courtyards of Cielo Ranch 23 | 2538410 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-11-25 | 2025-11-24
DS.2025.2334 Courtyards of Russell Oaks 61 | 2536742 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-11-24 | 2025-11-21
DS.2025.2333 7814 E Old US 50 | 2532793 | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | FIXED_PRICE |  |  | 2025-11-20 | 2025-11-19
DS.2025.2332 Courtyards of Westfield 109 | 2532772 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-11-20 | 2025-11-19
DS.2025.2331 Courtyards of Russell Oaks 65 | 2532740 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-11-20 | 2025-11-19
DS.2025.2330 GSI Stonecrest 11-18 | 2532662 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-11-20 | 2025-11-18
DS.2025.2329 Courtyards of Westfield Lot 90 | 2528354 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-11-18 | 2025-11-17
2026.1042 SND2 at ILP Bldg IV Whitestown | 2526957 | TI | Trevor Anderson | Compass Commercial Construction Group | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Whitestown | IN | 2026-02-23 | 2026-03-16 | 2026-06-23
DS.2025.2328 Walnut Townhouses | 2523333 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-11-14 | 2025-11-10
DS.2025.2327 Courtyards of Cielo Ranch 12 | 2522921 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-11-14 | 2025-11-13
DS.2025.2326 Courtyards of Russell Oaks 64 | 2521531 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-11-13 | 2025-11-12
2025.1024 Metro Lion | 2520350 | TI | Ben Garza | DEEM, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Indianapolis | IN | 2026-01-05 | 2025-11-14 | 2026-02-15
DS.2025.2325 6693 E 500 N | 2519527 | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | FIXED_PRICE |  | IN | 2025-11-12 | 2025-11-11
DS.2025.2324 6504 N 1200 E | 2519463 | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | FIXED_PRICE |  | IN | 2025-11-12 | 2025-11-11
DS.2025.2323 11890 E 800 N | 2519426 | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | FIXED_PRICE |  | IN | 2025-11-12 | 2025-11-11
DS.2025.2322 Courtyards of Russell Oaks 124 | 2517615 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-11-11 | 2025-11-06
DS.2025.2321 Courtyards of Cielo Ranch 33 | 2517594 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-11-11 | 2025-11-11
DS.2025.2320 Courtyards of Cielo Ranch 27 | 2517552 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-11-11 | 2025-11-06
DS.2025.2319 5288 Oak Grove Rd | 2510293 | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | FIXED_PRICE |  | IN | 2025-11-06 | 2025-11-05
DS.2025.2318 GSI Stonecrest 11-4 | 2508315 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-11-05 | 2025-11-04
DS.2025.2317 Courtyards of Ceilo Ranch 23 | 2508262 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-11-05 | 2025-11-04
2025.1023 Vikan Products BTS | 2505636 | TI | Cole Garriott | The Peterson Company, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Westfield | IN | 2025-11-06 | 2025-12-08 | 2026-03-31
DS.2025.2316 Courtyards of Cielo Ranch 8 | 2500441 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-31 | 2025-10-31
DS.2025.2315 GSI Brookville | 2499386 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-10-30 | 2025-10-30
DS.2025.2314 R18 Holiday Farms | 2498252 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-10-30 | 2025-10-27
DS.2025.2313 McDowell Residence | 2498183 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-10-30 | 2025-10-29
DS.2025.2312 Plantation Drive Flores | 2498101 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-10-30 | 2025-10-28
DS.2025.2311 15111 Mooring Cir W | 2498026 | DW | (Unassigned) | Mendoza | ACTIVE | FIXED_PRICE |  |  | 2025-10-30 | 2025-10-28 | 2025-10-28
DS.2025.2310 Courtyards of Cielo Ranch 12 | 2497952 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  |  | 2025-10-30 | 2025-10-28
DS.2025.2309 6936 Sun River Drive | 2491974 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-27 | 2025-10-27
DS.2025.2308 Courtyards of Westfield 112 | 2491878 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-27 | 2025-10-24
DS.2025.2307 Mendoza Drywall company-15535 Stony Creek Way | 2491611 | DW | (Unassigned) | Mendoza | ACTIVE | FIXED_PRICE |  |  | 2025-10-27 | 2025-10-24
DS.2025.2306 Courtyards of Russell Oaks 118 | 2488150 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-24 | 2025-10-22
DS.2025.2305 Courtyards of Russell Oaks 62 | 2488125 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-24 | 2025-10-22
DS.2025.2304 Charlstown Manor 10-22 | 2488086 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-10-24 | 2025-10-22
DS.2025.2303 Big Dawg Pickup 10-17 | 2481041 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  |  | 2025-10-21 | 2025-10-17
DS.2025.2302 14 E South St | 2480320 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-10-20 | 2025-10-20
DS.2025.2301 Courtyards of Cielo Ranch 39 | 2480064 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-20 | 2025-10-20 | 2025-10-20
DS.2025.2300 Courtyards of Cielo Ranch 10 | 2479977 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-20 | 2025-10-20
DS.2025.2299 4435 Strathmore Lane | 2475602 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-16 | 2025-10-15
DS.2025.2298 GSI Bloomington | 2475493 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-10-16 | 2025-10-15
DS.2025.2297 Courtyards of Cielo Ranch 28 | 2475432 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-16 | 2025-10-15
2025.1031 Pita Way | 2472092 | TI | Spencer Anderson | Kort Builders, Inc | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Westfield | IN | 2025-12-10 | 2025-12-01 | 2026-01-15
DS.2025.2296 4380 Strathmore Lane | 2469780 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  |  | 2025-10-14 | 2025-10-14
DS.2025.2295 Courtyards of Cielo Ranch 35 | 2469724 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-14 | 2025-10-14
DS.2025.2294 Courtyards of Cielo Ranch 9 | 2469631 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  |  | 2025-10-14 | 2025-10-14
DS.2025.2293 1248 Chatham Ridge Court | 2468636 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-10-13 | 2025-10-13
DS.2025.2292 Courtyards of Russell Oaks 121 | 2468607 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-13 | 2025-10-13
DS.2025.2291 Courtyards of Russell Oaks 63 | 2468570 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-13 | 2025-10-13
DS.2025.2290 Walnut Town Homes | 2468525 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-10-13 | 2025-10-10
DS.2025.2289 Courtyards of Westfield 118 | 2468496 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-13 | 2025-10-09
DS.2025.2288 Courtyards of Russell Oaks 120 | 2463881 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-09 | 2025-10-08
DS.2025.2286 Courtyards of Westfield 117 | 2459666 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-07 | 2025-10-07
DS.2025.2285 GSI - Rushville 5 | 2453104 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-10-03 | 2025-10-02
DS.2025.2284 Courtyards of Russell Oaks 59 | 2452961 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-10-03 | 2025-10-02
DS.2025.2281 Courtyards of Russell Oaks 117 | 2446907 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-09-30 | 2025-09-30
DS.2025.2280 GSI - E Crestwine Dr | 2446248 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-09-30 | 2025-09-30
DS.2025.2279 8810 Bergeson Drive | 2444852 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | FIXED_PRICE |  |  | 2025-09-29 | 2025-09-29
DS.2025.2278 Courtyards of Russell Oaks 52 | 2444545 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-09-29 | 2025-09-29
DS.2025.2275 Courtyards of Cielo Ranch 9 | 2441368 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  |  | 2025-09-26 | 2025-09-25
DS.2025.2274 Barndo 2 Frankfort | 2439356 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-09-25 | 2025-09-24
DS.2025.2272 Courtyards of Russell Oaks 48 | 2438113 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-09-25 | 2025-09-23
DS.2025.2271 Courtyards of Westfield 113 | 2438103 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-09-24 | 2025-09-23
DS.2025.2269 GSI Ranch Basement House 9-22 | 2433725 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-09-23 | 2025-09-22
DS.2025.2267 GSI Rushville Lot 17 | 2431674 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  |  | 2025-09-22 | 2025-09-18
DS.2025.2265 Courtyards of Westfield 42 | 2431619 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-09-22 | 2025-09-18
DS.2025.2264 Maratt Remodel | 2426990 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-09-18 | 2025-09-03
DS.2025.2262 Rushville 2 house pre rock | 2426804 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-09-18 | 2025-09-16
DS.2025.2258 Cavalier Res | 2426715 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-09-18 | 2025-09-15
DS.2025.2257 Courtyards of Russell Oaks 116 | 2426691 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  |  | 2025-09-22 | 2025-09-15
2025.1016 WBP Lot C | 2422257 | TI | Tommy Cohoat | Patch Development | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Noblesville | IN | 2025-09-16 | 2025-10-27 | 2025-12-31
2025.1013 Lucas Oil Corydon | 2414762 | TI | Shawn Welcher | Meyer Najem | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Corydon | IN | 2025-10-03 | 2025-09-26
2025.1012 Airport South Logistics Bldg. B | 2412851 | TI | Spencer Anderson | ARCO Design/Build | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Shepherdsville | KY | 2025-09-12 | 2026-01-12 | 2026-01-30
2025.1011 Airport South Logistics Bldg. A | 2412835 | TI | Spencer Anderson | ARCO Design/Build | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Shepherdsville | KY | 2025-09-12 | 2026-07-01 | 2026-09-01
DS.2025.2243 5689 N Ohio Ridge Rd | 2400949 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-09-02 | 2025-08-29
DS.2025.2241 6915 SR 550 | 2400575 | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | FIXED_PRICE |  | IN | 2025-09-02 | 2025-08-29
2025.1027 Indy Boat Co | 2394684 | TI | Trevor Anderson | Raley Wake, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Pendleton | IN | 2026-01-05 | 2026-03-15
MF.2025.1019 Town & Country Apartments (NY MF Project - 22 bldgs) | 2394677 | MF | Kelden Tyson | Marous Brothers Construction | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Binghamton | NY | 2025-10-16 | 2025-11-04 | 2026-12-04
DS.2025.2236 Courtyards of Russell Oaks 149,146 | 2389374 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-08-25 | 2025-08-21
DS.2025.2235 18 Store Estates | 2389077 | DW | (Unassigned) | Community Drywall | ACTIVE | FIXED_PRICE |  |  | 2025-08-25 | 2025-08-21
DS.2025.2234 Lot 4 Store Estates | 2388892 | DW | (Unassigned) | Community Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-08-25 | 2025-08-20
DS.2025.2233 49 Bills Blvd | 2388766 | DW | (Unassigned) | Kjt General Construction | ACTIVE | FIXED_PRICE |  | IN | 2025-08-25 | 2025-08-21
2025.1006 Keller Office | 2383587 | TI | Ben Garza | ARCO Design/Build | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Peru | IN | 2025-08-21 | 2025-10-15 | 2026-01-30
DS.2025.2228 Edgebrook Lot 72 | 2381339 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | FIXED_PRICE |  |  | 2025-08-20 | 2025-08-19
DS.2025.2222 Courtyards of Russell Oaks 55 | 2368894 | DW | (Unassigned) | Big Dawg Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-08-12 | 2025-08-12
DS.2025.2220 17 Store Estates | 2367104 | DW | (Unassigned) | Community Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-08-11 | 2025-08-08
DS.2025.2217 Davidson Residence | 2366840 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-08-11 | 2025-08-07
DS.2025.2215 44 Willow Springs | 2366626 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-08-11 | 2025-08-05
DS.2025.2212 Scottsdale Lot 70 | 2363817 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | FIXED_PRICE |  |  | 2025-08-08 | 2025-08-05
DS.2025.2208 12921 Merlot Ln | 2363162 | DW | (Unassigned) | M&M Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-08-08 | 2025-08-04
DS.2025.2207 Edgebrook Lot 219 | 2359929 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | FIXED_PRICE |  |  | 2025-08-06 | 2025-08-04
DS.2025.2202 M&M Drywall Pickup 7-29 | 2354747 | DW | (Unassigned) | M&M Drywall | ACTIVE | FIXED_PRICE |  | IN | 2025-08-04 | 2025-07-29 | 2025-07-29
DS.2025.2197 Edgebrook Lot 199 | 2350460 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | FIXED_PRICE |  |  | 2025-07-31 | 2025-07-30
DS.2025.2196 1718 Bellefontaine St | 2350360 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | FIXED_PRICE |  |  | 2025-07-31 | 2025-07-28
DS.2025.2194 GSI House 10 | 2349208 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-07-30 | 2025-07-24
DS.2025.2191 Edgebrook Lot 192 | 2346918 | DW | (Unassigned) | Pro Fix Drywaller, LLC | ACTIVE | FIXED_PRICE |  |  | 2025-07-29 | 2025-07-28
DS.2025.2189 1022 E 3rd Bloomington | 2343287 | DW | (Unassigned) | Kjt General Construction | ACTIVE | FIXED_PRICE |  |  | 2025-07-28 | 2025-07-23
DS.2025.2187 Crawford Res, 880 Baywood Court | 2340132 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-08-04 | 2025-07-23
DS.2025.2186 Bloomington Triplex Unit 3 | 2340035 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-07-24 | 2025-07-22
DS.2025.2185 Bloomington Triplex Middle Unit | 2340013 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-07-24 | 2025-07-22
DS.2025.2184 Bloomington Triplex Unit 1 | 2339995 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-07-24 | 2025-07-22
DS.2025.2182 9220 Tower Rd | 2339243 | DW | (Unassigned) | Solano Masonry, Inc. | ACTIVE | FIXED_PRICE |  | IN | 2025-07-24 | 2025-07-20
DS.2025.2175 6891 State Road 257 | 2337339 | DW | (Unassigned) | Total Drywall Solutions Inc | ACTIVE | FIXED_PRICE |  | IN | 2025-07-23 | 2025-07-23
DS.2025.2169 Abbey Place 311 | 2327047 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  |  | 2025-07-16 | 2025-07-11
DS.2025.2150 V3 Holiday Farms | 2304400 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  |  | 2025-07-01 | 2025-07-02
2025.1021 Convivio | 2303764 | TI | Shawn Welcher | The Peterson Company, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Noblesville | IN | 2025-10-28 | 2025-10-27 | 2026-01-05
2025.999 Romet PWSI | 2303466 | TI | Tommy Cohoat | The Peterson Company, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Indianapolis | IN | 2025-07-30 | 2025-07-30 | 2025-11-19
DS.2025.2143 GSI Ranch | 2302121 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-06-30 | 2025-06-27
DS.2025.2138 51 Preserve | 2301410 | DW | (Unassigned) | Flores Drywall and Remodeling LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-06-30 | 2025-06-27
DS.2025.2118 House 6 | 2296704 | DW | (Unassigned) | GSI - Gregory Scott Inabnit LLC | ACTIVE | FIXED_PRICE |  | IN | 2025-06-26 | 2025-06-17
2025.997 Belmont St Warehouse Clear Out 250-408 | 2282848 | TI | Spencer Anderson | DEEM, LLC | ACTIVE | FIXED_PRICE | Indianapolis | IN | 2025-06-25 | 2025-06-18 | 2025-06-30
DS.2025.2072 Tom Carter Prince's Lake | 2261041 | DW | (Unassigned) | TC Indy | ACTIVE | FIXED_PRICE |  |  | 2025-06-04 | 2025-06-04
2025.1032 65 Commerce Park Building 7 | 2250539 | TI | Trevor Anderson | Compass Commercial Construction Group | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Whitestown | IN | 2025-12-22 | 2026-04-15
2025.994 Stotan Port Laredo Spec Offices | 2248156 | TI | Ben Garza | ARCO Design/Build | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Laredo | TX | 2025-09-18 | 2025-09-22 | 2026-03-15
DS.2025.2045 Old Town Pickup | 2242353 | DW | (Unassigned) | Old Town Design Group | ACTIVE | FIXED_PRICE |  |  | 2025-05-22 | 2025-05-20
MF.2026.1050 AC Hotel | 2225641 | MF | Ben Garza | Holladay Construction Group | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Fishers | IN | 2026-04-28 | 2026-06-01
2025.986 FedEx Hub | 2223116 | TI | Tommy Cohoat | Dalmatian Fire | ACTIVE | FIXED_PRICE | Indianapolis | IN | 2025-05-09 | 2025-05-07 | 2025-05-16
DS.2025.1967 MN - H2S | 2205083 | DW | (Unassigned) | Meyer Najem | ACTIVE | FIXED_PRICE |  |  | 2025-04-29 | 2025-04-29 | 2025-04-29
2025.1015 WBP Lot 4 | 2196541 | TI | Tommy Cohoat | Patch Development | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Noblesville | IN | 2025-09-16 | 2025-09-29 | 2025-11-30
2025.1001 Evolve Transporters | 2174851 | TI | Cole Garriott | Compass Commercial Construction Group | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Noblesville | IN | 2025-08-08 | 2025-07-29 | 2026-04-30
DS.2025.1895 IFD Pickup 3/25/25 | 2160928 | DW | (Unassigned) | Indianapolis Fire Department | ACTIVE | FIXED_PRICE |  |  | 2025-03-31 | 2025-03-25 | 2025-03-25
2025.980 Avon Bldg. 1 Canopies & Pavilion | 2157624 | TI | Spencer Anderson | The Peterson Company, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Avon | IN | 2025-06-05 | 2025-07-01 | 2025-10-31
DS.2025.1882 Alexandria Building 24 | 2152299 | DW | (Unassigned) | Precision Dry Wall | ACTIVE | FIXED_PRICE |  | IN | 2025-03-25 | 2025-03-25 | 2025-03-25
2025.993 Batesville Public Library | 2117526 | TI | Shawn Welcher | Meyer Najem | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Batesville | IN | 2025-08-20 | 2025-10-01 | 2026-09-30
2025.979 Groundbreakers | 2108038 | TI | Trevor Anderson | Patch Development | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Indianapolis | IN | 2025-06-17 | 2025-07-01 | 2025-12-30
2025.969 Carson | 2098776 | TI | Spencer Anderson | DEEM, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Easton | PA | 2025-03-14 | 2025-04-14 | 2025-12-16
MF.2025.992 Young's Creek Apartments | 2092684 | MF | Kelden Tyson | Shiel Sexton | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Franklin | IN | 2025-12-16 | 2026-01-05 | 2026-05-18
MF.2025.976 Firefly Youth Housing | 2087575 | MF | Spencer Anderson | Stenz Corp | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Indianapolis | IN | 2025-09-10 | 2025-09-02 | 2026-03-17
2026.1052 Project Panther | 2087565 | TI | Spencer Anderson | ARCO Design/Build | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Homestead | PA | 2026-05-06 | 2026-05-15 | 2026-10-05
DS.2025.1762 Jeff West Builders for Steve Raker | 2067674 | DW | (Unassigned) | Jeff West Homes | ACTIVE | FIXED_PRICE |  |  | 2025-01-28 | 2025-01-27 | 2025-01-27
DS.2025.1759 Juan Lugo NC 01-22 | 2061037 | DW | (Unassigned) | Lugo Contracting, LLC | ACTIVE | FIXED_PRICE |  |  | 2025-01-22 | 2025-01-22 | 2025-01-22
MF.2025.977 Civic Square Condos | 2040900 | MF | Trevor Anderson | Novo Development Group, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Carmel | IN | 2025-09-23 | 2025-10-06 | 2026-03-31
2025.966 C5 Bullitt III Logistics Center Warehouse | 2037261 | TI | Trevor Anderson | The Peterson Company, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Shepherdsville | KY | 2025-07-10 | 2025-07-23 | 2025-12-31
2025.960 Langham Whiteland South Lockers | 2028240 | TI | Spencer Anderson | DEEM, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Whiteland | IN | 2025-02-20 | 2025-02-05 | 2025-08-31
2024.957 SanMar AWR | 2025315 | TI | Cole Garriott | The Peterson Company, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Ashland | VA | 2024-12-19 | 2024-12-16 | 2025-01-21
2024.953 Motorworks | 2012203 | TI | Tommy Cohoat | Precision Dry Wall | ACTIVE | FIXED_PRICE | Westfield | IN | 2024-12-23 | 2024-12-03 | 2024-12-20
MF.2025.963 Home 2 Suites | 2009228 | MF | Kelden Tyson | Meyer Najem | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Noblesville | IN | 2025-01-31 | 2025-02-07 | 2025-12-31
DS.2024.1656 Juan Lugo 1202 NC | 1989297 | DW | (Unassigned) | Lugo Contracting, LLC | ACTIVE | FIXED_PRICE |  |  | 2024-12-26 | 2024-12-02 | 2024-12-02
MF.2024.941 Oak Trace | 1956827 | MF | Dustin Hurt | Westfield Community Management, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Westfield | IN | 2024-10-25 | 2024-10-28 | 2025-03-31
MF.2025.972 Union Flats - Fishers | 1900804 | MF | Ben Garza | Thompson Thrift Construction | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Fishers | IN | 2025-06-27 | 2025-12-08 | 2026-12-31
2024.929 DEEM Warehouse | 1870076 | TI | Tommy Cohoat | DEEM, LLC | ACTIVE | FIXED_PRICE | Indianapolis | IN | 2024-09-10 | 2024-08-12 | 2025-11-03
MF.2024.924 Monon Trail Elementary | 1854607 | MF | Dustin Hurt | LTB Construction, Inc. | ACTIVE | COST_PLUS | Westfield | IN | 2024-08-07 | 2024-07-29 | 2024-08-09
2024.920 SMC Mezzanine HVAC | 1842206 | TI | Trevor Anderson | DEEM, LLC | ACTIVE | FIXED_PRICE | Noblesville | IN | 2024-08-01 | 2024-07-26 | 2024-07-31
MF.2025.1007 The Approach | 1839016 | MF | Kelden Tyson | KCG | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Westfield | IN | 2025-10-31 | 2026-04-01 | 2027-07-14
DS.2024.1378 Ketchum Basement | 1820214 | DW | (Unassigned) | Mendoza | ACTIVE | FIXED_PRICE |  |  | 2024-07-11 | 2024-07-12 | 2024-07-12
DS.2024.1377 Warehouse Pickup 0710 - 2824 Sunnyfield Ct | 1819558 | DW | (Unassigned) | Imperial Design | ACTIVE | FIXED_PRICE |  |  | 2024-08-05 | 2024-07-10 | 2024-07-10
2024.913 Walmart Phoenix | 1814679 | TI | Cole Garriott | DEEM, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Litchfield Park | AZ | 2024-08-05 | 2024-07-29 | 2026-01-30
MF.2025.975 The Eleven - Monon Square | 1806764 | MF | Shawn Welcher | Centric Projects, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Carmel | IN | 2026-04-28 | 2026-04-15 | 2026-06-26
MF.2025.989-1 Springdale Cinema - Paint | 1803611 | MF | Ben Garza | MILHAUS Construction | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Springdale | OH | 2025-08-06 | 2026-02-01 | 2026-10-01
MF.2024.906 Shamrock Elementary LGI Classrooms | 1794757 | MF | Dustin Hurt | LTB Construction, Inc. | ACTIVE | FIXED_PRICE | Westfield | IN | 2024-06-19 | 2024-06-22 | 2024-07-31
DS.2024.1346 10660 Pete Dye Ridge | 1787241 | DW | (Unassigned) | Promasters Drywall and Painting (Brian Figueroa) | ACTIVE | FIXED_PRICE |  |  | 2024-06-13 | 2024-06-12 | 2024-06-12
MF.2024.903 Mirka Office Buildout | 1779490 | MF | Cole Garriott | DEEM, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Plainfield | IN | 2025-01-21 | 2025-01-06 | 2025-04-08
MF.2024.927 Jeffersonian Apartments | 1779189 | MF | Ben Garza | Stenz Corp | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Lafayette | IN | 2024-12-19 | 2025-04-01 | 2025-09-30
DS.2024 8503 N 600 W Fountaintown QUOTE | 1772287 | DW | (Unassigned) | TC Indy | ACTIVE | FIXED_PRICE |  |  | 2024-05-31 | 2024-05-31 | 2024-05-31
1234.567 Test Job | 1735717 | UN | (Unassigned) | Sample Client | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Indianapolis | IN | 2024-11-04
MF.2024.894 Hamilton County Jail Boiler Mechanical Pad | 1724469 | MF | Dustin Hurt | DEEM, LLC | ACTIVE | FIXED_PRICE |  |  | 2024-04-24 | 2024-06-25 | 2024-08-16
MF.2024.892 The Lofts at Headwaters Park | 1710251 | MF | Ben Garza | J.C. Hart Company, Inc. | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Fort Wayne | IN | 2024-09-09 | 2024-08-01 | 2026-05-15
2025.967 Bunge Project Flex | 1702352 | TI | Ben Garza | Bunge North America (East), LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Morristown | IN | 2025-04-10 | 2025-03-01 | 2026-01-30
DS.2024.1263 5188 Brighton Dr Whitestown | 1683585 | DW | (Unassigned) | Promasters Drywall and Painting (Brian Figueroa) | ACTIVE | FIXED_PRICE |  |  | 2024-03-21 | 2024-03-21 | 2024-03-21
2024.912 Upland Columbus | 1669494 | TI | Tommy Cohoat | Bischoff Construction, LLC | ACTIVE | FIXED_PRICE | Columbus | IN | 2024-07-09 | 2024-06-25 | 2024-10-31
DS.2024.1234 Pro Masters | 1658900 | DW | (Unassigned) | Promasters Drywall and Painting (Brian Figueroa) | ACTIVE | FIXED_PRICE |  |  | 2024-02-29 | 2024-02-29 | 2024-02-29
MF.2024.928 Holliday Farms Assisted Living - Zionsville | 1607003 | MF | Ben Garza | Avenue Construction, Inc. | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Zionsville | IN | 2025-01-30 | 2025-03-01 | 2026-03-31
DS.2023.1141 Latitude Apartments | 1577552 | DW | (Unassigned) | Velocity Builders | ACTIVE | FIXED_PRICE |  |  | 2023-12-13 | 2023-12-13 | 2024-04-30
2023.847 Ireland Home | 1551637 | TI | Tommy Cohoat | Bischoff Construction, LLC | ACTIVE | FIXED_PRICE | Jeffersonville | IN | 2023-11-15 | 2023-11-15
2024.874 Noblesville HS Academic Addition & Renovation | 1539188 | TI | Trevor Anderson | The Peterson Company, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Noblesville | IN | 2024-03-12 | 2024-04-01 | 2025-12-31
MF.2023.840 Paint at 804 14th Ave Nashville | 1536145 | MF | Kelden Tyson | ZMX Inc. | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Nashville | TN | 2024-10-24 | 2024-10-24 | 2025-08-29
2023.816 Upland Broad Ripple | 1464707 | TI | Tommy Cohoat | Bischoff Construction, LLC | ACTIVE | FIXED_PRICE | Indianapolis | IN | 2023-09-19 | 2023-08-18
2023.839 Hamilton County National Guard Readiness Center | 1461734 | TI | Tommy Cohoat | Patterson Horth, Inc. | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Atlanta | IN | 2023-11-13 | 2024-06-04 | 2025-12-31
2024.869 Prospect Lake Clean Water Center | 1423094 | TI | Cole Garriott | Patterson Horth, Inc. | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Fort Lauderdale | FL | 2024-04-16 | 2025-01-20 | 2025-11-28
2023.795 Upland Brewery Clay Terrace | 1407590 | TI | Tommy Cohoat | Bischoff Construction, LLC | ACTIVE | FIXED_PRICE | Carmel | IN | 2023-07-18 | 2023-07-05
2023.843 Walmart Frederick | 1398846 | TI | Cole Garriott | DEEM, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Frederick | MD | 2024-01-19 | 2024-01-15 | 2025-05-30
MF.2023.785 Drywall at 804 14th Ave Nashville | 1383434 | MF | Kelden Tyson | ZMX Inc. | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Nashville | TN | 2023-11-01 | 2024-10-01 | 2025-08-29
2023.776 Keefe Group TI | 1360035 | TI | Tommy Cohoat | The Peterson Company, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Noblesville | IN | 2023-06-13 | 2023-06-13
MF.2024.875 Purdue Student Housing | 1303390 | MF | Kelden Tyson | Marous Brothers Construction | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | West Lafayette | IN | 2024-05-08 | 2024-04-18 | 2025-08-31
2022.690 Klarity, Mind, & Body | 1161468 | TI | Ted Wells | EquiTeam LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Indianapolis | IN | 2022-12-01 | 2022-12-12
2023.731 Park 133 - ITS - TI Tenant Buildout | 1151697 | TI | Tommy Cohoat | The Peterson Company, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Whitestown | IN | 2023-02-21 | 2023-02-20
2022.654 Upland Brewery Northside | 1138743 | TI | Tommy Cohoat | Seven Four Construction | ACTIVE | FIXED_PRICE |  |  | 2022-10-10 | 2022-09-26 | 2024-08-30
MDG Office at Rucker | 1138684 | UN | (Unassigned) | MDG New Office | ACTIVE | FIXED_PRICE |  |  | 2022-10-13 | 2022-10-13
2022.625 Walmart 7611 | 1138659 | TI | Cole Garriott | Massa Multimedia Architecture (MMA) | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Plainfield | IN | 2022-11-15 | 2022-08-08 | 2026-01-30
2022.617 The Junction Phase II | 1138651 | TI | Ted Wells | EquiTeam LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Logansport | IN | 2022-10-12
2022.610 222 E. Ohio St. | 1138649 | UN | Ted Wells | Midwest Design Group - Misc | ACTIVE | FIXED_PRICE | Indianapolis | IN | 2022-10-13 | 2022-10-13
2022.639 Radial TI - Avon Building 2 | 1138478 | TI | Tommy Cohoat | The Peterson Company, LLC | ACTIVE | FIXED_PRICE_WITH_AIA_BILLING | Avon | IN | 2022-10-12

## » Dim_Account
Account | Statement | Category | Subcategory | DivKey | Sort
Billable Expense Income | P&L | Revenue | Income | ALL | 1
Doors and Windows | P&L | Revenue | Income | ALL | 2
Drywall Division Delivery Income | P&L | Revenue | Drywall Service Income | DW | 3
Drywall Division Material Income | P&L | Revenue | Drywall Service Income | DW | 4
Drywall Sales Income | P&L | Revenue | Income | DW | 5
Drywall Service Income | P&L | Revenue | Income | DW | 6
Drywall Supply Arbor Income | P&L | Revenue | Drywall Service Income | DW | 7
Drywall Supply Century Income | P&L | Revenue | Drywall Service Income | DW | 8
Drywall Supply HD Boom Scatter Income | P&L | Revenue | Drywall Service Income | DW | 9
Drywall Supply Pulte Income | P&L | Revenue | Drywall Service Income | DW | 10
Drywall Tax | P&L | Revenue | Drywall Service Income | DW | 11
Engineering Project Income | P&L | Revenue | Income | EN | 12
Finishes | P&L | Revenue | Income | ALL | 13
Metals | P&L | Revenue | Income | ALL | 14
Sales | P&L | Revenue | Income | ALL | 15
Service/Fee Income | P&L | Revenue | Income | ALL | 16
Specialties | P&L | Revenue | Income | ALL | 17
Thermal and Moisture Control | P&L | Revenue | Income | ALL | 18
WIP Adj - Net change | P&L | Revenue | Income | ALL | 19
Wood and Plastics | P&L | Revenue | Income | ALL | 20
Cost of labor - Contractors | P&L | COGS | Cost of Goods Sold | ALL | 21
Cost of labor - Direct Labor | P&L | COGS | Cost of Goods Sold | ALL | 22
Drywall Project (Material) Expense - Internal | P&L | COGS | Job Site Expenses | DW | 23
Drywall Project (Tax) Expense - Internal | P&L | COGS | Job Site Expenses | DW | 24
Drywall Supply Arbor Expense | P&L | COGS | Cost of Goods Sold | DW | 25
Drywall Supply Century Expense | P&L | COGS | Cost of Goods Sold | DW | 26
Drywall Supply External Expense | P&L | COGS | Cost of Goods Sold | DW | 27
Drywall Supply Internal Expense | P&L | COGS | Cost of Goods Sold | DW | 28
Drywall Supply Pulte Expense | P&L | COGS | Cost of Goods Sold | DW | 29
Equipment Rental | P&L | COGS | Job Site Expenses | ALL | 30
Job Site Expenses | P&L | COGS | Cost of Goods Sold | ALL | 31
Per Diem Job Expense | P&L | COGS | Cost of Goods Sold | ALL | 32
Shipping, Freight & Delivery - COS | P&L | COGS | Cost of Goods Sold | ALL | 33
Vendor Discounts | P&L | COGS | Cost of Goods Sold | ALL | 34
Warranty Labor Expense | P&L | COGS | Cost of labor - Contractors | ALL | 35
Warranty Material Expense | P&L | COGS | Job Site Expenses | ALL | 36
Advertising & Marketing | P&L | Operating Expense | Expenses | ALL | 37
Ask My Accountant | P&L | Operating Expense | Expenses | ALL | 38
Bad Debt | P&L | Operating Expense | Expenses | ALL | 39
Bank Charges & Fees | P&L | Operating Expense | Expenses | ALL | 40
Bonus | P&L | Operating Expense | Payroll Expenses | ALL | 41
Bonus Accrual Expense | P&L | Operating Expense | Bonus & Commission Expense | ALL | 42
Car & Truck | P&L | Operating Expense | Expenses | ALL | 43
Charitable Contributions | P&L | Operating Expense | Expenses | ALL | 44
Charitable Contributions - Non-Deductible | P&L | Operating Expense | Charitable Contributions | ALL | 45
Commission | P&L | Operating Expense | Payroll Expenses | ALL | 46
Contractors | P&L | Operating Expense | Expenses | ALL | 47
DEF - Boom Truck | P&L | Operating Expense | Car & Truck | ALL | 48
DOT Boom Trucks Compliance | P&L | Operating Expense | Car & Truck | ALL | 49
Depreciation | P&L | Operating Expense | Expenses | ALL | 50
Drywall Division Labor - Subcontractors | P&L | Operating Expense | Expenses | DW | 51
Drywall Division Supplies Expense | P&L | Operating Expense | Expenses | DW | 52
Drywall Supply HD Boom Scatter Diesel - Boom Truck | P&L | Operating Expense | Fuel Diesel - Boom Truck | DW | 53
Drywall Supply HD Boom Scatter Expense | P&L | Operating Expense | Expenses | DW | 54
Drywall Supply HD Boom Scatter Labor | P&L | Operating Expense | Expenses | DW | 55
Drywall Supply HD Boom Scatter Travel | P&L | Operating Expense | Expenses | DW | 56
Dues & subscriptions | P&L | Operating Expense | Expenses | ALL | 57
Employee Benefits | P&L | Operating Expense | Payroll Expenses | ALL | 58
Entertainment | P&L | Operating Expense | Meals & Entertainment | ALL | 59
Equipment/Vehicle Rental | P&L | Operating Expense | Expenses | ALL | 60
Expenses — Unitemized | P&L | Operating Expense | Expenses | ALL | 61
Freight | P&L | Operating Expense | Expenses | ALL | 62
Fuel Diesel - Boom Truck | P&L | Operating Expense | Car & Truck | ALL | 63
Fuel Truck - Company Pickup | P&L | Operating Expense | Car & Truck | ALL | 64
Health Insurance | P&L | Operating Expense | Employee Benefits | ALL | 65
Insurance | P&L | Operating Expense | Expenses | ALL | 66
Interest Paid | P&L | Operating Expense | Expenses | ALL | 67
Job Supplies | P&L | Operating Expense | Expenses | ALL | 68
Legal & Professional Services | P&L | Operating Expense | Expenses | ALL | 69
Meals | P&L | Operating Expense | Meals & Entertainment | ALL | 70
Meals & Entertainment | P&L | Operating Expense | Expenses | ALL | 71
Melio Credit card fee | P&L | Operating Expense | Expenses | ALL | 72
Misc / Spot Bonus Expense | P&L | Operating Expense | Bonus & Commission Expense | ALL | 73
Office Supplies & Software | P&L | Operating Expense | Expenses | ALL | 74
Other Business Expenses | P&L | Operating Expense | Expenses | ALL | 75
Outsourced IT Services | P&L | Operating Expense | Expenses | ALL | 76
Outsourced Safety | P&L | Operating Expense | Expenses | ALL | 77
Payroll Fees | P&L | Operating Expense | Payroll Expenses | ALL | 78
Property Tax | P&L | Operating Expense | Expenses | ALL | 79
Reimbursable Expenses | P&L | Operating Expense | Expenses | ALL | 80
Rent & Lease | P&L | Operating Expense | Expenses | ALL | 81
Repairs & Maintenance | P&L | Operating Expense | Expenses | ALL | 82
Service - Boom Truck | P&L | Operating Expense | Car & Truck | ALL | 83
Service - Boom Truck 1103 Volvo | P&L | Operating Expense | Car & Truck | ALL | 84
Service - Boom Truck 1107 Western Star | P&L | Operating Expense | Car & Truck | ALL | 85
Service - Boom Truck 1109 Freightliner 16 | P&L | Operating Expense | Car & Truck | ALL | 86
Service - Boom Truck 1110 Peterbilt 18 | P&L | Operating Expense | Car & Truck | ALL | 87
Service - Boom Truck 1111 Freightliner | P&L | Operating Expense | Car & Truck | ALL | 88
Service - Boom Truck 1112 Peterbilt 17 | P&L | Operating Expense | Car & Truck | ALL | 89
Service - Company Truck | P&L | Operating Expense | Car & Truck | ALL | 90
Small Tools & Equipment | P&L | Operating Expense | Expenses | ALL | 91
Software Subscription/Use Fee | P&L | Operating Expense | Office Supplies & Software | ALL | 92
Taxes | P&L | Operating Expense | Payroll Expenses | ALL | 93
Taxes & Licenses | P&L | Operating Expense | Expenses | ALL | 94
Training & Education | P&L | Operating Expense | Expenses | ALL | 95
Travel | P&L | Operating Expense | Expenses | ALL | 96
Travel - Fuel | P&L | Operating Expense | Travel | ALL | 97
Travel - Meals | P&L | Operating Expense | Travel | ALL | 98
Uncategorized Expense | P&L | Operating Expense | Expenses | ALL | 99
Utilities | P&L | Operating Expense | Expenses | ALL | 100
Wage Accrual | P&L | Operating Expense | Bonus & Commission Expense | ALL | 101
Wages | P&L | Operating Expense | Payroll Expenses | ALL | 102
Credit Card Rewards | P&L | Other Income | Other Income | ALL | 103
Interest Earned | P&L | Other Income | Other Income | ALL | 104
Other Income | P&L | Other Income | Other Income | ALL | 105
Subletter Rent Income | P&L | Other Income | Other Income | ALL | 106
Subletter Utility Income | P&L | Other Income | Other Income | ALL | 107
Vendor Rebate Income | P&L | Other Income | Other Income | ALL | 108
Gain or Loss on Assets | P&L | Other Expense | Other Expenses | ALL | 109

## » Dim_Division
DivKey | Division | Sort | Color
TI | Tenant Improvement | 1 | #029CF5
MF | Multi-Family | 2 | #4F8FC7
DW | Drywall | 3 | #6E7585
EN | Engineering | 4 | #515967
UN | Unallocated | 9 | #3A4150

## » Dim_PM
PMName | ActiveJobs | Active
(Unassigned) | 221 | FALSE
Ben Garza | 15 | TRUE
Cole Garriott | 9 | TRUE
Dustin Hurt | 6 | TRUE
Kelden Tyson | 7 | TRUE
Shawn Welcher | 5 | TRUE
Spencer Anderson | 14 | TRUE
Ted Wells | 3 | TRUE
Tommy Cohoat | 18 | TRUE
Trevor Anderson | 10 | TRUE

## » Param_Cash
Param | Value | Note
LOC Limit | 8000000 | USER INPUT — Forum line-of-credit commitment (not in QuickBooks)
Advance Rate | 0.8 | USER INPUT — borrowing-base advance rate on eligible AR
Eligible AR | 12986875.87 | Defaulted to total trade AR; refine to eligible basis
LOC Drawn | 5440076.95 | REAL — QuickBooks balance sheet, Forum LOC (0874)
Cash Balance | -54623.3 | REAL — QuickBooks balance sheet cash

## Job Revenue 2026
Revenue Billed by Job — 2026 (Jan–May)
Knowify invoices by invoice date • 140 jobs with 2026 revenue • sorted largest first
Job | Jan 2026 | Feb 2026 | Mar 2026 | Apr 2026 | May 2026 | Total Jan-May
MF.2025.972 Union Flats - Fishers | 27090 | 229770 | 486459 | 841491 | 571623.75 | 2156433.75
MF.2025.1019 Town & Country Apartments (NY MF Project - 22 bldgs) | 246097.48 | 562089.22 | 675814.07 | 0 | 435716.98 | 1919717.75
2025.964 Avon Municipal Building | 363417.48 | 173192.63 | 226932.38 | 220010.73 | 236453.93 | 1220007.15
MF.2024.931 Wild Air | 166011.35 | 148756.83 | 226412.55 | 408053.89 | 126290.65 | 1075525.27
2025.1029 Resmed - Indy 500 | 41976.09 | 65098.75 | 104940.22 | 538961.21 | 217317.46 | 968293.73
MF.2025.989-2 Springdale Cinema - Drywall | 122512.5 | 224842.5 | 256635 | 344520 | 0 | 948510
2025.1024 Metro Lion | 231487.2 | 553922.8 | 0 | 1300 | 0 | 786710
2025.991 Walmart Republic | 65246.93 | 194391.63 | 141074.42 | 186798.6 | 0 | 587511.58
2025.978 Ardalan Plaza | 29270.16 | 88455.24 | 182393.32 | 58873.86 | 193598.5 | 552591.08
MF.2024.928 Holliday Farms Assisted Living - Zionsville | 75888.38 | 23629.34 | 56885.34 | 54038.62 | 338327.69 | 548769.37
2025.1001 Evolve Transporters | 290318.22 | 204675.12 | 10660.05 | 30489.3 | 1341 | 537483.69
2025.1023 Vikan Products BTS | 0 | 16087.5 | 95690.7 | 205262.77 | 198556.32 | 515597.29
2025.1030 Westfield Police HQ | 0 | 0 | 0 | 94815 | 420570 | 515385
MF.2024.892 The Lofts at Headwaters Park | 161432.46 | 114855.12 | 62543.7 | 89590.28 | 63353.47 | 491775.03
2025.990 Walmart Orlando | 55072.44 | 100249.47 | 127771.38 | 133941.78 | 74099.79 | 491134.86
MF.2025.992 Young's Creek Apartments | 127149.57 | 58491.67 | 30618 | 272493.11 | 0 | 488752.35
2026.1035 The Ark | 0 | 0 | 228065.58 | 86809.68 | 156749.71 | 471624.97
MF.2025.989-1 Springdale Cinema - Paint | 0 | 0 | 55440 | 165847.5 | 206955 | 428242.5
Priority Way Office | 0 | 0 | 413250 | 0 | 0 | 413250
2025.1026 HNTB Buildout (Salesforce Tower) | 40056.3 | 92546.64 | 111708.94 | 75748.68 | 92235.04 | 412295.6
2026.1042 SND2 at ILP Bldg IV Whitestown | 0 | 0 | 164669.04 | 68841.54 | 123216.76 | 356727.34
MF.2024.945 Encore Senior Living | 43797.38 | 94697.22 | 54087.55 | 91941.31 | 61193.27 | 345716.73
2024.950 Caterpillar Triple Crown | 9448.35 | 147545.92 | 38045.07 | 72880.67 | 36620.15 | 304540.16
2025.994 Stotan Port Laredo Spec Offices | 107527.5 | 25920 | 27180 | 0 | 114932.8 | 275560.3
MF.2026.1050 AC Hotel | 0 | 0 | 0 | 0 | 202650.67 | 202650.67
2026.1033 Avon Demising Wall | 0 | 0 | 181500 | 0 | 0 | 181500
2024.909 Andretti Global HQ | 40682 | 0 | 0 | 0 | 129947 | 170629
2026.1038 Artistic Composite Pallet Expansion | 0 | 0 | 104592.42 | 65920.59 | 0 | 170513.01
2025.1006 Keller Office | 0 | 0 | 0 | 0 | 168520.5 | 168520.5
2026.1041 Whiteland Building 2 - Blackhawk | 0 | 0 | 0 | 111888 | 44532.3 | 156420.3
2026.1047 Springdale Building 4 Demising Walls | 0 | 0 | 0 | 0 | 148800 | 148800
2025.1027 Indy Boat Co | 0 | 0 | 0 | 53062.2 | 83283.7 | 136345.9
2026.1043 Deer Creek Building 1 | 0 | 0 | 135000 | 0 | 0 | 135000
2026.1045 First OnSite (Ameriplex) | 0 | 0 | 0 | 128000 | 0 | 128000
2026.1037 CV - Castle Rock | 0 | 125451 | 0 | 0 | 2000 | 127451
2026.1046 Automatic Distributors (Park 130 Bldg 6) | 0 | 0 | 0 | 32697 | 91953 | 124650
2025.967 Bunge Project Flex | 0 | 11965.23 | 109085.8 | 0 | 0 | 121051.03
2026.1036 Port Laredo Trade Center | 0 | 0 | 73818 | 0 | 34657 | 108475
2025.1012 Airport South Logistics Bldg. B | 0 | 0 | 9868.5 | 26117.77 | 67259.03 | 103245.3
MF.2025.977 Civic Square Condos | 16373.48 | 2902.5 | 3275.1 | 0 | 61611.56 | 84162.64
MF.2025.975 The Eleven - Monon Square | 0 | 0 | 0 | 30587.39 | 47118.33 | 77705.72
2025.1032 65 Commerce Park Building 7 | 0 | 0 | 0 | 0 | 71314.2 | 71314.2
2025.981 Fort Ben - Foamcraft | 0 | 69374.88 | 0 | 0 | 0 | 69374.88
MF.2025.976 Firefly Youth Housing | 4050 | 0 | 18000 | 36934.63 | 9000 | 67984.63
2023.839 Hamilton County National Guard Readiness Center | 0 | 0 | 0 | 58016.76 | 0 | 58016.76
2025.1015 WBP Lot 4 | 31758.75 | 18902.5 | 0 | 5500 | 0 | 56161.25
2025.966 C5 Bullitt III Logistics Center Warehouse | 56050.1 | 0 | 0 | 0 | 0 | 56050.1
2026.1034 Stella's Ice Cream Shop | 0 | 0 | 22860 | 11250 | 18000 | 52110
2025.1016 WBP Lot C | 25903.13 | 0 | 0 | 0 | 13081.87 | 38985
2025.979 Groundbreakers | 5282.37 | 32067.74 | 0 | 0 | 0 | 37350.11
2025.1013 Lucas Oil Corydon | 0 | 22500 | 0 | 0 | 10000 | 32500
2024.913 Walmart Phoenix | 0 | 0 | 25857 | 3055.5 | 0 | 28912.5
2023.843 Walmart Frederick | 0 | 0 | 26200 | 0 | 0 | 26200
DS.2026.2404 Flores Sandhu Res | 0 | 0 | 20852.65 | 0 | 0 | 20852.65
2026.1056 Senator Banks Office | 0 | 0 | 0 | 0 | 20467.33 | 20467.33
DS.2026.2387 0204 Jose Irachetta | 0 | 20097.86 | 0 | 0 | 0 | 20097.86
2025.1025 Park 100 - Building 22 | 19640 | 0 | 0 | 0 | 0 | 19640
DS.2026.2376 5724 E Southport Rd | 18119.63 | 0 | 0 | 0 | 0 | 18119.63
2025.1028 Northpoint | 0 | 0 | 0 | 17415 | 0 | 17415
2025.993 Batesville Public Library | 6637.82 | 4425.21 | 6267.5 | 0 | 0 | 17330.53
DS.2026.2406 Premier Custom Homes Quote | 0 | 0 | 0 | 17262.74 | 0 | 17262.74
2024.929 DEEM Warehouse | 0 | 0 | 15645.5 | 0 | 0 | 15645.5
2025.1021 Convivio | 2250 | 12458.26 | 0 | 0 | 0 | 14708.26
DS.2026.2432 Liberty Assisted LIving 0528 | 0 | 0 | 0 | 0 | 12455.2 | 12455.2
DS.2026.2380 Mike Valentine 0129 | 12430.13 | 0 | 0 | 0 | 0 | 12430.13
DS.2026.2365 GSI Sackstedor Bloomington | 11604.16 | 0 | 0 | 0 | 0 | 11604.16
DS.2026.2401 Flores Kenneland | 0 | 0 | 11454.33 | 0 | 0 | 11454.33
2026.1040 Lakeside Books | 0 | 0 | 0 | 0 | 10020 | 10020
DS.2026.2412 10732 Heaven Cove Way | 0 | 0 | 0 | 0 | 10008.15 | 10008.15
2025.1031 Pita Way | 0 | 8770.5 | 974.5 | 0 | 0 | 9745
DS.2026.2433 Liberty Assisted Living 0529 | 0 | 0 | 0 | 0 | 9607.6 | 9607.6
2025.984 Whiteland Indiana Guard Shack | 0 | 0 | 0 | 0 | 9200 | 9200
DS.2026.2375 1802 Alabama St | 9073.56 | 0 | 0 | 0 | 0 | 9073.56
DS.2026.2389 Courtyards of Russell Oaks 145 | 0 | 8375.35 | 299.6 | 0 | 0 | 8674.95
DS.2026.2421 Flores Ohio Job | 0 | 0 | 0 | 0 | 8624.08 | 8624.08
DS.2026.2394 5778 Marvie Drive | 0 | 8586.04 | 0 | 0 | 0 | 8586.04
DS.2026.2392 3705 Holiday Farms Blvd - Precision | 0 | 8393.53 | 0 | 0 | 0 | 8393.53
DS.2026.2383 Courtyards of Cielo Ranch 37 | 0 | 7718.84 | 0 | 0 | 0 | 7718.84
DS.2026.2363 Courtyards of Westfield 96 | 7700.52 | 0 | 0 | 0 | 0 | 7700.52
DS.2026.2400 Courtyards of Russell Oaks 115 | 0 | 0 | 7645.75 | 0 | 0 | 7645.75
DS.2026.2378 Courtyards of Westfield 108 | 7637.37 | 0 | 0 | 0 | 0 | 7637.37
DS.2026.2410 Courtyards of Russell Oaks 113 | 0 | 0 | 0 | 7585.02 | 0 | 7585.02
DS.2026.2369 Courtyards of Westfield 111 | 7574.01 | 0 | 0 | 0 | 0 | 7574.01
DS.2026.2377 Courtyards of Cielo Ranch 38 | 7574.01 | 0 | 0 | 0 | 0 | 7574.01
DS.2026.2402 Courtyards of Cielo Ranch 17 | 0 | 0 | 7307.29 | 240.36 | 0 | 7547.65
DS.2026.2398 Courtyards of Ceilo Ranch 26 | 0 | 0 | 7276.63 | 0 | 0 | 7276.63
DS.2026.2368 Courtyards of Russell Oaks 60 | 7243.75 | 0 | 0 | 0 | 0 | 7243.75
DS.2026.2405 21569 Anchor Bay Drive | 0 | 0 | 0 | 7033.52 | 0 | 7033.52
DS.2026.2408 Courtyards of Westfield 107 | 0 | 0 | 0 | 6956.92 | 0 | 6956.92
DS.2026.2385 Courtyards of Russell Oaks 123 | 0 | 6812.24 | 0 | 0 | 0 | 6812.24
DS.2026.2371 13429 E 116th St | 6806.08 | 0 | 0 | 0 | 0 | 6806.08
2026.1039 Upland Prospect Street | 0 | 6500 | 0 | 0 | 0 | 6500
DS.2026.2386 Courtyards of Russell Oaks 125 | 0 | 6318.06 | 0 | 0 | 0 | 6318.06
DS.2026.2388 Courtyards of Cielo Ranch 13 | 0 | 6290.19 | 0 | 0 | 0 | 6290.19
DS.2026.2396 6252 West Turtle Hill Ct | 0 | 0 | 6268.5 | 0 | 0 | 6268.5
2025.983 DEEM Warehouse Drop Ceiling | 0 | 6200 | 0 | 0 | 0 | 6200
DS.2026.2399 Courtyards of Russell Oaks 74 | 0 | 0 | 6156.42 | 0 | 0 | 6156.42
DS.2026.2366 Courtyards of Cielo Ranch 15 | 6022.94 | 0 | 0 | 0 | 0 | 6022.94
DS.2026.2370 Courtyards of Westfield 106 | 5971.55 | 0 | 0 | 0 | 0 | 5971.55
DS.2026.2407 Courtyards of Russel Oaks 126 | 0 | 0 | 0 | 5928.42 | 0 | 5928.42
DS.2026.2418 118 Centre Place | 0 | 0 | 0 | 0 | 5520.75 | 5520.75
DS.2026.2416 52 Centre Place | 0 | 0 | 0 | 0 | 5520.75 | 5520.75
DS.2026.2425 14 Parks | 0 | 0 | 0 | 0 | 5520.75 | 5520.75
DS.2026.2426 121 Centre Place | 0 | 0 | 0 | 0 | 5520.75 | 5520.75
DS.2026.2403 Big Dawg Pickup 0327 | 0 | 0 | 5302.49 | 0 | 0 | 5302.49
DS.2026.2428 9 Centre Place | 0 | 0 | 0 | 0 | 4962.27 | 4962.27
DS.2026.2420 7508 Central Ave | 0 | 0 | 0 | 0 | 4323.31 | 4323.31
DS.2026.2384 225 N St Ave | 0 | 4271.93 | 0 | 0 | 0 | 4271.93
DS.2026.2417 117 Centre Place | 0 | 0 | 0 | 0 | 4070.62 | 4070.62
DS.2026.2419 120 Centre Place | 0 | 0 | 0 | 0 | 4070.62 | 4070.62
DS.2026.2372 Big Dawg Pickup 0115 | 3907.73 | 0 | 0 | 0 | 0 | 3907.73
DS.2026.2424 10566 Coppergate | 0 | 0 | 0 | 0 | 3882.79 | 3882.79
DS.2026.2411 Clark Remodel | 0 | 0 | 0 | 3764.86 | 0 | 3764.86
DS.2026.2364 GSI 1-6 | 3762.61 | 0 | 0 | 0 | 0 | 3762.61
DS.2026.2429 108 Centre Place | 0 | 0 | 0 | 0 | 3711.4 | 3711.4
DS.2026.2430 119 Centre Place | 0 | 0 | 0 | 0 | 3411.3 | 3411.3
DS.2026.2431 123 Centre Place | 0 | 0 | 0 | 0 | 3411.3 | 3411.3
DS.2026.2379 124 S A Street | 2632.63 | 0 | 0 | 0 | 0 | 2632.63
DS.2026.2414 10824 McPherson St | 0 | 0 | 0 | 0 | 2611.31 | 2611.31
DS.2026.2415 10826 McPherson St | 0 | 0 | 0 | 0 | 2611.31 | 2611.31
DS.2026.2423 10816 McPherson St | 0 | 0 | 0 | 0 | 2611.31 | 2611.31
DS.2026.2422 10814 McPherson St | 0 | 0 | 0 | 0 | 2611.31 | 2611.31
DS.2026.2390 510 W Pine St | 0 | 2495.07 | 0 | 0 | 0 | 2495.07
DS.2026.2391 0218 Jose Iracheta | 0 | 2072.89 | 0 | 0 | 0 | 2072.89
DS.2026.2427 Dapp Garage | 0 | 0 | 0 | 0 | 2024.87 | 2024.87
2024.912 Upland Columbus | 0 | 0 | 0 | 0 | 2020 | 2020
2025.999 Romet PWSI | 0 | 1940 | 0 | 0 | 0 | 1940
DS.2026.2381 Hunt Addition | 1601.79 | 0 | 0 | 0 | 0 | 1601.79
DS.2026.2374 Precision Pickup 0127 | 1151.37 | 0 | 0 | 0 | 0 | 1151.37
DS.2026.2413 Precision Pickup 0501 | 0 | 0 | 0 | 0 | 1096.76 | 1096.76
DS.2026.2382 Cohoat House | 0 | 1065.45 | 0 | 0 | 0 | 1065.45
DS.2026.2367 Courtyards of Russell Oaks 126 | 360.55 | 0 | 0 | 0 | 0 | 360.55
DS.2026.2397 Courtyards of Cielo Ranch 26 | 0 | 0 | 360.55 | 0 | 0 | 360.55
DS.2026.2362 Courtyards of Russel Oaks 127 | 299.6 | 0 | 0 | 0 | 0 | 299.6
DS.2026.2395 Courtyards of Westfield 103 | 0 | 0 | 270.41 | 0 | 0 | 270.41
DS.2026.2393 Precision Pickup 0216 | 0 | 252.01 | 0 | 0 | 0 | 252.01
DS.2026.2373 Precision Pickup 0120 | 167.78 | 0 | 0 | 0 | 0 | 167.78
DS.2026.2409 Precision Pickup 0410 | 0 | 0 | 0 | 107.86 | 0 | 107.86
2024.874 Noblesville HS Academic Addition & Renovation | -14964 | 0 | 0 | 0 | 0 | -14964
MF.2024.875 Purdue Student Housing | -40103.3 | 0 | 0 | 0 | 0 | -40103.3
TOTAL — all jobs | 2479001.91 | 3525424.88 | 4583415.25 | 4672034.07 | 5022777.27 | 20282653.38